SOFTWARE DEVELOPMENT PLAN (SDP)

FOR THE

JOINT PRIMARY AIRCRAFT TRAINING SYSTEM (JPATS)

GROUND BASED TRAINING SYSTEM (GBTS)

CONTRACT # KTFSSC797

SDRL G018

23 JULY 1997

Prepared By:

FlightSafety Services Corporation

3333 S. Bannock Street, # 100

Englewood, CO  80110-2432

Prepared For:

Raytheon Aircraft Company

Trainer Systems Division

9709 E. Central Avenue, Bldg. B-90

Wichita, KS  67201

DISTRIBUTION STATEMENT “D”:  Distribution authorized to Department of Defense, RAC, and DOD subcontractors only to protect technical or operational data or information from automatic dissemination under the International Exchange Program or by other means.  This protection covers information required solely for administrative or operational purposes, date of document as shown hereon 23 July 1997 ASC/YTK.

WARNING:  This document contains technical data whose export is restricted by the Arms Export Control Act (Title 22, U. S. C. 2751 et seq) or Executive Order 12470.  Violation of these export control laws is subject to severe criminal penalties.  Dissemination of this document is controlled under DOD Directive 5230.25.

# LIST OF EFFECTIVE PAGES

Insert latest change page, dispose of superseded pages.  Date(s) of issue for original and change pages:

Electronic filename of this document is as follows:  18230797.doc

| Rev'n | Date | Rev'n | Date | Rev'n | Date |
| --- | --- | --- | --- | --- | --- |
| Orig. | 23 July 1997 | D |  | H |  |
| A |  | E |  | I |  |
| B |  | F |  | J |  |
| C |  | G |  | K |  |

| Page No. | Change No. | Page No. | Change No. | Page No. | Change No. | Page No. | Change No. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| i-x 1-147 A1-A2 B1-B2 C1-C9 D1-D3 E1-E8 | Orig Orig Orig Orig Orig Orig |  |  |  |  |  |  |

# TABLE OF CONTENTS

LIST OF EFFECTIVE PAGES

TABLE OF CONTENTS

LIST OF FIGURES

LIST OF TABLES

1.0  SCOPE

1.1  IDENTIFICATION

1.2  SYSTEM OVERVIEW

1.2.1  PROJECT SUMMARY(SOW 5010)

1.2.2  APPLICABILITY

1.3  DOCUMENT OVERVIEW

1.4  RELATIONSHIP TO OTHER PLANS

2.0  REFERENCED DOCUMENTS (SOW 2020)

2.1  GOVERNMENT DOCUMENTS

2.2  NON-GOVERNMENT DOCUMENTS

3.0  OVERVIEW OF REQUIRED WORK (SOW 5020.1.9)

3.1  SYSTEM REQUIREMENTS AND CONSTRAINTS (SS 3.4.10.2)

3.1.1  AIRCREW TRAINING DEVICES (SOW 5010.3)

3.1.2  OPERATIONAL SUPPORT SEGMENT (SOW 5010.4)

3.1.2.1  Training Integration Management System. (SOW 5010.4.1)

3.1.2.1.1  TIMS Proof-of Concept Prototypes. (SOW 5010.4.1.1)

3.1.2.1.2  TIMS Interfaces. (SOW 5010.4.1.2)

3.1.2.2  Computer-Based Training System. (SOW 5010.4.2)

3.1.3  MODIFICATION AND UPDATE SUPPORT SYSTEM (SOW 5010.4.3)

3.2  REQUIREMENTS AND CONSTRAINTS ON PROJECT DOCUMENTATION (SOW 5020.3.2.4, 5050.3- 3.2)

3.3  SYSTEM LIFE CYCLE DATA

3.4  PROGRAM ACQUISITION STRATEGY

3.5  SCHEDULE REQUIREMENTS AND CONSTRAINTS

3.6  OTHER REQUIREMENTS AND CONSTRAINTS

3.6.1  CONFIGURATION MANAGEMENT SYSTEM REQUIREMENTS

3.6.2  TRACEABILITY SYSTEM REQUIREMENTS

3.6.3  VERIFICATION ENVIRONMENT REQUIREMENTS AND CONSTRAINTS

3.6.4  RISK MANAGEMENT REQUIREMENTS AND CONSTRAINTS

3.6.5  SUBCONTRACTOR MANAGEMENT (SOW 5020.2.2)

4.0  PLANS FOR PERFORMING GENERAL SOFTWARE DEVELOPMENT ACTIVITIES (SOW 5020.2.1)

4.1  SOFTWARE DEVELOPMENT PROCESS

4.1.1  FTD SOFTWARE DEVELOPMENT PROCESS

4.1.2  TIMS SOFTWARE DEVELOPMENT PROCESS

4.2  GENERAL PLANS FOR SOFTWARE DEVELOPMENT

4.2.1  SOFTWARE DEVELOPMENT METHODS

4.2.2  STANDARDS FOR SOFTWARE PRODUCTS

4.2.2.1  FTD Standards for Software Products

4.2.2.2  TIMS Standards for Software Products

4.2.3  REUSABLE SOFTWARE PRODUCTS

4.2.3.1  Incorporating Reusable Software Products

4.2.3.2  Developing Reusable Software Products

4.2.3.3  Feedback From Reuse of FTD Software in Follow-on Programs

4.2.4  HANDLING OF CRITICAL REQUIREMENTS

4.2.4.1  Safety Assurance

4.2.4.2  Security Assurance (SOW 7010.4.1)

4.2.4.3  Privacy Assurance

4.2.4.4  Assurance of Other Critical Requirements

4.2.5  COMPUTER HARDWARE RESOURCE UTILIZATION

4.2.6  RECORDING RATIONALE

4.2.7  ACCESS FOR ACQUIRER REVIEW. (SOW 5020.2.1.1)

5.0  DETAILED SOFTWARE DEVELOPMENT ACTIVITIES

5.1  PROJECT PLANNING AND OVERSIGHT (SOW 5020.1.9, 5020.1.1.7)

5.1.1  SOFTWARE DEVELOPMENT PLANNING. (SOW 5020.1.3)

5.1.2  CSCI TEST PLANNING (SOW 5020.1.3.1, 5030.5.1)

5.1.2.1 FTD Test Planning (SOW 5030.2-2.2.2)

5.1.2.2  TIMS Test Planning (SOW 5030.5-5.1.1)

5.1.2.3  Other CSCI Test Planning (SOW 5030.5.2, 5030.5.3, 5030.6)

5.1.3  SYSTEM TEST PLANNING (SOW 5030, 5030.1.5-1.7, 5030.7)

5.1.3.1  TIMS System Test Planning (SOW 5030.5.1.1)

5.1.4  SOFTWARE INSTALLATION PLANNING (SOW 5080-1.1, 5080.2.1-2.2, 5080.3 )

5.1.5  SOFTWARE TRANSITION PLANNING (SOW 5080.2.3, 6040-1.5 )

5.1.6  FOLLOWING AND UPDATING PLANS

5.2  ESTABLISHING A SOFTWARE DEVELOPMENT ENVIRONMENT

5.2.1  SOFTWARE ENGINEERING ENVIRONMENT (SEE)

5.2.1.1  FTD Software Engineering Environment

5.2.1.2  TIMS Software Engineering Environment

5.2.2  SOFTWARE TEST ENVIRONMENT

5.2.2.1  FTD Software Test Environment

5.2.2.2  TIMS Software Test Environment

5.2.3  SOFTWARE DEVELOPMENT LIBRARY

5.2.3.1  FTD SDL

5.2.3.2  TIMS SDL

5.2.4  SOFTWARE DEVELOPMENT FILES (SDFS)

5.2.5  NON-DELIVERABLE SOFTWARE

5.3  SYSTEM REQUIREMENTS ANALYSIS  (SOW 5020.1.1.11, 5020.1.7.1, 5020.1.7.2)

5.3.1  ANALYSIS OF USER INPUT

5.3.2  OPERATIONAL CONCEPT

5.3.3  SYSTEM REQUIREMENTS

5.4  SYSTEM DESIGN (SOW 5020.1.1.13, 5020.1.7.2)

5.4.1  SYSTEM-WIDE DESIGN DECISIONS

5.4.2  SYSTEM ARCHITECTURAL DESIGN

5.5  SOFTWARE REQUIREMENTS ANALYSIS  (SOW 5020.1.7.2)

5.6  SOFTWARE DESIGN (SOW 5020.1.1.14, 5020.1.1.15)

5.6.1  CSCI-WIDE DESIGN DECISIONS

5.6.2  CSCI ARCHITECTURAL DESIGN (SOW 5020.1.1.14)

5.6.3  CSCI DETAILED DESIGN (SOW 5020.1.1.15)

5.7  SOFTWARE IMPLEMENTATION AND UNIT TESTING (SOW 5020.1.3.1)

5.7.1  SOFTWARE IMPLEMENTATION

5.7.2  PREPARING FOR UNIT TESTING

5.7.3  PERFORMING UNIT TESTING

5.7.4  REVISION AND RETESTING

5.7.5  ANALYZING AND RECORDING UNIT TEST RESULTS

5.8  UNIT INTEGRATION AND TESTING (SOW 5020.1.3.1)

5.8.1  PREPARING FOR UNIT INTEGRATION AND TESTING

5.8.2  PERFORMING UNIT INTEGRATION AND TESTING

5.8.2.1  Performing TIMS Unit Integration and Testing

5.8.2.2  Performing FTD Unit Integration and Testing

5.8.3  REVISION AND RETESTING

5.8.4  ANALYZING AND RECORDING UNIT INTEGRATION AND TEST RESULTS

5.9  CSCI QUALIFICATION TESTING

5.9.1  INDEPENDENCE IN CSCI QUALIFICATION TESTING

5.9.1.1  Independence in CSCI Qualification Testing (FTD)

5.9.1.2  Independence in CSCI Qualification Testing (TIMS).

5.9.2  TESTING ON THE TARGET COMPUTER SYSTEM

5.9.2.1  Testing on the Target Computer System (FTD)

5.9.2.2  Testing on the Target Computer System (TIMS)

5.9.3  PREPARING FOR CSCI QUALIFICATION TESTING

5.9.4  DRY RUN OF CSCI QUALIFICATION TESTING

5.9.5  PERFORMING CSCI QUALIFICATION TESTING

5.9.5.1  Performing CSCI Qualification Testing (FTD)

5.9.5.2  Performing CSCI Qualification Testing (TIMS).  (SOW 5030.5.1)

5.9.6  REVISION AND RETESTING

5.9.7  ANALYZING AND RECORDING CSCI QUALIFICATION TEST RESULTS.  (SOW 5020.1.3.1, 5030.1.6)

5.10  CSCI/HWCI INTEGRATION AND TESTING (SOW 5030.1.3)

5.10.1  PREPARING FOR CSCI/HWCI INTEGRATION AND TESTING (SOW 5020.1.3.1)

5.10.2  PERFORMING CSCI/HWCI INTEGRATION AND TESTING.

5.10.2.1  Performing CSCI/HWCI Integration and Testing (FTDs). (SOW  5030.2.1, 5030.2.1.1, 5030.2.1.5)

5.10.2.2  Performing CSCI/HWCI Integration and Testing (TIMS).  (SOW 5030.5.1)

5.10.3  REVISION AND RETESTING

5.10.4  ANALYZING AND RECORDING CSCI/HWCI INTEGRATION AND TEST RESULTS.

5.11  SYSTEM QUALIFICATION TESTING (SOW 5030.2.1.6, 5030.5.1.1-5030.7)

5.11.1  INDEPENDENCE IN SYSTEM QUALIFICATION TESTING

5.11.2  TESTING ON THE TARGET COMPUTER SYSTEM (SOW 5030.2.1.6)

5.11.3  PREPARING FOR SYSTEM QUALIFICATION TESTING (SOW 5030.5.1, 5030.3.2.1.1)

5.11.4  DRY RUN OF SYSTEM QUALIFICATION TESTING

5.11.4.1  Dry Run of System Qualification Testing (FTDs)  (SOW 5030.2.1.6, 5030.2.1.7)

5.11.4.2  Dry Run of System Qualification Testing (TIMS) (SOW 5030.5.1.1)

5.11.5  PERFORMING SYSTEM QUALIFICATION TESTING  (SOW 5030.2.1.8)

5.11.5.1  Performing System Qualification Testing (FTDs)

5.11.5.2  Performing System Qualification Testing (TIMS)

5.11.5.2.1  On-Site Acceptance Testing (TIMS)

5.11.5.2.2  SLFE Support (TIMS)

5.11.5.2.3  TIMS Participation in GBTS Integration Testing.  (SOW 5030.7)

5.11.6  REVISION AND RETESTING

5.11.7  ANALYZING AND RECORDING SYSTEM QUALIFICATION TEST RESULTS

5.12  PREPARING FOR SOFTWARE USE (SOW 5.20.1.7.3)

5.12.1  PREPARING THE EXECUTABLE SOFTWARE

5.12.2  PREPARING VERSION DESCRIPTIONS FOR USER SITES

5.12.3  PREPARING USER MANUALS

5.12.4  INSTALLATION AT USER SITES (SOW 5080.2-2.6)

5.13  PREPARING FOR SOFTWARE TRANSITION (SOW 5020.1.3.3, 5080.2.1-2.6, SOW 5020.1.7.3)

5.13.1  PREPARING THE EXECUTABLE SOFTWARE

5.13.2  PREPARING SOURCE FILES

5.13.3  PREPARING VERSION DESCRIPTIONS FOR THE SUPPORT SITE

5.13.4  PREPARING THE “AS-BUILT” CSCI DESIGN AND OTHER SOFTWARE SUPPORT INFORMATION

5.13.5  UPDATING THE SYSTEM DESIGN DESCRIPTION

5.13.6  PREPARING SUPPORT MANUALS

5.13.7  TRANSITION TO THE DESIGNATED SUPPORT SITE

5.14  SOFTWARE CONFIGURATION MANAGEMENT (SOW 5020.2.5)

5.14.1  CONFIGURATION IDENTIFICATION (SOW 5020.1.7-1.7.3)

5.14.1.1  Formal Configuration Identification

5.14.1.2  Developmental Configuration Identification

5.14.2  CONFIGURATION CONTROL

5.14.2.1  TIMS Configuration Control

5.14.2.2  FTD Configuration Control

5.14.3  CONFIGURATION STATUS ACCOUNTING

5.14.4  CONFIGURATION AUDITS

5.14.5  PACKAGING, STORAGE, HANDLING, AND DELIVERY

5.15  SOFTWARE PRODUCT EVALUATION (5020.1.4.2)

5.15.1  IN-PROCESS AND FINAL SOFTWARE PRODUCT EVALUATIONS

5.15.2  SOFTWARE PRODUCT EVALUATION RECORDS, INCLUDING ITEMS TO BE RECORDED

5.15.3  INDEPENDENCE IN SOFTWARE PRODUCT EVALUATION

5.16  SOFTWARE QUALITY ASSURANCE (SOW 5020.1.4.2)

5.16.1  SOFTWARE QUALITY ASSURANCE EVALUATIONS

5.16.2  SOFTWARE QUALITY ASSURANCE RECORDS, INCLUDING ITEMS TO BE RECORDED

5.16.3  INDEPENDENCE IN SOFTWARE QUALITY ASSURANCE

5.17  CORRECTIVE ACTION (SOW 5030.1.4)

5.17.1  PROBLEM/CHANGE REPORTS

5.17.1.1  TIMS Problem/Change Reports

5.17.1.2  FTD Problem/Change Reports

5.17.2  CORRECTIVE ACTION SYSTEM

5.18  JOINT TECHNICAL AND MANAGEMENT REVIEWS(SOW 5020.1.1 - 1.1.16)

5.18.1  JOINT TECHNICAL REVIEWS (SOW 5020.1.1.1 - 1.1.16)

5.18.2  JOINT MANAGEMENT REVIEWS (SOW 5020.1.1 -1.1.1, 5020.1.1.7, 6020.1.1.1)

5.19  OTHER SOFTWARE DEVELOPMENT ACTIVITIES (SOW 5020)

5.19.1  RISK MANAGEMENT

5.19.1.1  Risk Identification

5.19.1.2  Risk Analysis.

5.19.1.3  Risk Planning

5.19.1.4  Risk Tracking and Control

5.19.1.5  RISK COMMUNICATION

5.19.2  SOFTWARE MANAGEMENT INDICATORS (SOW 5020.2.3-2.4)

5.19.3  SECURITY AND PRIVACY (SOW 7010.4.1)

5.19.4  SUBCONTRACTOR MANAGEMENT

5.19.5  INTERFACE WITH SOFTWARE INDEPENDENT VERIFICATION AND VALIDATION (IV&V) AGENTS

5.19.6  COORDINATION WITH ASSOCIATE DEVELOPERS

5.19.7  IMPROVEMENT OF PROJECT PROCESSES

5.19.8  OTHER ACTIVITIES

6.0  SCHEDULES AND ACTIVITY NETWORK  (SOW 5020.2.4)

7.0  PROJECT ORGANIZATION AND RESOURCES (SOW 5020.2.1)

7.1  PROJECT ORGANIZATION

7.1.2  TIMS PROJECT ORGANIZATION

7.2  PROJECT RESOURCES

7.2.1  PERSONNEL RESOURCES

7.2.1.1  FTD Personnel Resources

7.2.1.2  TIMS Personnel Resources

7.2.2  FACILITIES

7.2.3  ACQUIRER-FURNISHED EQUIPMENT AND OTHER RESOURCES

8.0  NOTES

8.1  ACRONYMS

APPENDIX A: SDP/MIL-STD 498 TAILORING CROSS-REFERENCE	A-

APPENDIX B:  FTD SUPPLEMENTAL SOFTWARE PLANNING DATA	B-

B.1  SOFTWARE SIZE ESTIMATES	B-

APPENDIX C:  TIMS SUPPLEMENTAL SOFTWARE PLANNING DATA	C-

C.1  SOFTWARE ARCHITECTURE	C-

C.2  SIZE ESTIMATES	C-

C.3  ESTIMATED USE OF CRITICAL COMPUTER RESOURCES	C-

C.4  PRELIMINARY TIMS DATABASE TECHNICAL ASSESSMENTS	C-

C.5  MANAGEMENT PRACTICES	C-

APPENDIX D:  SDP/SOW CROSS REFERENCE	D-

APPENDIX E:  ISO-9001 REQUIREMENTS COMPLIANCE MATRIX	E-

E.1  FLIGHTSAFETY ISO-9001 REQUIREMENTS COMPLIANCE MATRIX	E-

E.2  LOGICON ISO-9001 REQUIREMENTS COMPLIANCE MATRIX	E-

# LIST OF FIGURES

FIGURE 1.2-1  GBTS Hierarchy

FIGURE 1.2.1-1  Integrated Product Teams

FIGURE 3.0-1  Software Development Areas

FIGURE 3.0-2  Engineering Documentation Flow-Down

FIGURE 3.0-3  Operation and Support Documentation Flow-Down

FIGURE 3.0-4  Management Documentation Flow-Down

FIGURE 3.0-5  Formal Test Documentation Flow-Down

FIGURE 4.1.1-1  FTD Software Development Process.

FIGURE 4.1.2-1  TIMS Software Development Process Overview

FIGURE 5.1-1  GBTS Timeline

FIGURE 5.2.2-1  TIMS Development Environment

FIGURE 5.2.2-2  FTD Development & Initial Test Environment

FIGURE 5.2.2-3  FTD Advanced Test Environment

FIGURE 5.3-1  Process Flow Diagram for System Requirements Analysis

FIGURE 5.3.2-1  Operational Concept Definition Cycle - Detailed Steps

FIGURE 5.4-1  Process Flow for System Design

FIGURE 5.4-2  Develop/Refine System Design - Detailed Steps

FIGURE 5.5-1  Process Flow Diagram for Software Requirements Analysis

FIGURE 5.5-2  TIMS Object Oriented Requirements Engineering

FIGURE 5.6.-1  Process Flow  Diagram for Software Architectural Design

FIGURE 5.6.2-2  TIMS Object Oriented Design -- Detailed Steps

FIGURE 5.6.3-1  Process Flow Diagram for Detailed Design

FIGURE 5.7-1  Processes Flow Diagram For Code and Unit Test

FIGURE 5.8.1-1  Process Flow Diagram for Preparation for Integration and Test

FIGURE 5.8.2-1  Process Flow Diagram for Integration and Test

FIGURE 5.9-1  Process Flow Diagram for CSCI Qualification Test

FIGURE 5.10.1-1  Process Flow Diagram for CSCI/HWCI Integration and Test

FIGURE 5.11-1  Process Flow Diagram for System Testing

FIGURE 5.14.2-1  GBTS CCB Membership

FIGURE 5.16.2-1  Blank FSI Quality Assurance Inspection/Evaluation Checklist

FIGURE 5.16.2-2  Sample TIMS QER Form

FIGURE 7.1-1  FSI-SSD FTD IPT Project Organization

FIGURE 7.1.2-1.  Logicon Organization

FIGURE 7.1.2-2  Logicon TIMS IPT Organization

FIGURE C.1-1  TIMS Architecture	C-

# LIST OF TABLES

TABLE 4.1-1  FTD Software Engineering Processes

TABLE 4.1-2  TIMS/OSS Software Engineering Processes

TABLE 4.1.2-1  TIMS Software Development Activities by Increment & Phase

TABLE 4.2.1-1  TIMS Software Development Process Documents

TABLE 4.2.3.1-1  FTD Deployment COTS and Reuse Products

TABLE 4.2.3.1-2  FTD Simulation Applications Reuse Products and Sources

TABLE 4.2.3.1-3  TIMS Deployment Reuse Products

TABLE 5.2.1.1-1a  FTD SEE Software Tools

TABLE 5.2.1.1-2  FTD Subdirectories of the project directory

TABLE 5.2.1.2-1  TIMS SEE Software Tools

TABLE 5.2.1.2-1  SEE Hardware Items

TABLE 5.3.3-1  Sample of TIMS-specific prototyping activities

TABLE 5.3.3-2  Overview of Prototyping Activities

TABLE 5.5-1  TIMS Object Oriented Software Requirements Analysis Methodology

TABLE 5.6.2-1  TIMS Software Architecture Design Object Oriented Methodology

TABLE 5.6.3-1  TIMS Software Detailed Design Object Oriented Methodology

TABLE 5.7-1  Code and Unit Test Methodology

TABLE 5.8.1-1  Preparation for integration and test methodology

TABLE 5.14-1  FTD Configuration Management Procedures

TABLE 5.14-2  TIMS Configuration Management Procedures

TABLE 5.14.1-1  GBTS Configuration Baseline Documentation

TABLE 5.14.1-2  Identification of Developmental Configuration Baselines

TABLE 5.15.1-1  FlightSafety QA Product Evaluation Checklists (used on FTD products)

TABLE 5.15.1-2  Logicon QA Product Evaluation Checklists (used on TIMS products)

TABLE 5.15.1-3  Software Products and Associated Evaluation Criteria

TABLE 5.16-1  FTD SQA Procedures

TABLE 5.16-2  TIMS SQA Procedures

TABLE 5.17.1-1  Categories to be used for classifying problems in software products

TABLE 5.17.1-2  Priorities To Be Used For Classifying Problems

TABLE 5.17.1-3  Categories to be used for classifying problems in FTD software products

TABLE 5.18.1-1  Formal Reviews

TABLE 5.19.1-1  Taxonomy of Software Development Risks

TABLE 5.19.2-1  Management Indicators

TABLE 7.2.1-1  FTD IPT Development Staff Loading by Phase (Averages)

TABLE 7.2.1-2  FTD IPT Qualifications

TABLE 7.2.1-3  FTD IPT Functional Responsibilities

TABLE 7.2.1-4  TIMS IPT Development Staff Loading by Phase

TABLE 7.2.1-5  TIMS IPT Qualifications

TABLE 7.2.1-6  TIMS IPT Functional Responsibilities

TABLE 7.2.2-1  Facility Locations

TABLE A.1-1 MIL-STD-498 TAILORING	A-

TABLE B.1-1  FTD CTC/IOS Sizing Estimates	B-

TABLE C.2-1  TIMS Software Modules	C-

TABLE C.3-1  TIMS Computer Transactions Estimates	C-

TABLE C.5-1  TIMS Management Procedures, Directives, and Guidelines	C-

TABLE E-1  FlightSafety ISO-9001 Requirements Compliance Matrix	E-

TABLE E-1  FlightSafety ISO-9001 Requirements Compliance Matrix	E-

TABLE E-2  Logicon ISO-9001 Requirements Compliance Matrix	E-

# 1.0  SCOPE

## 1.1  IDENTIFICATION

This Software Development Plan (SDP), prepared in accordance with DI-IPSC-81427 and submitted as Subcontract Data Requirements List (SDRL) sequence number G018, establishes the plans and guidelines for software development and support activities performed during the Joint Primary Aircrew Training System (JPATS) Ground Based Training System (GBTS) program.  Computer Software Configuration Items covered by this SDP are:

- Training Integrated Management System

- Operational Flight Trainer

- Instrument Flight Trainer

- Unit Training Device

## 1.2  SYSTEM OVERVIEW

The GBTS is organized as shown in Figure 1.2-1.  The GBTS will be deployed at all, or any combination, of the Air Force Bases (AFBs) and Naval Air Stations (NASs) listed below (depending on specific contractual actions):

- Randolph AFB

- Laughlin AFB

- Columbus AFB

- Vance AFB

- Sheppard AFB

- NAS Pensacola

- NAS Corpus Christi

- NAS Whiting

- NAS Kingsville

- NAS Meridian

- Hondo AF

- United States Air Force Academy

### 1.2.1  PROJECT SUMMARY(SOW 5010)

Raytheon Aircraft Company (Raytheon) is the prime contractor for JPATS under USAF Contract No. F33657-94-C-0006.  FlightSafety is the prime subcontractor to Raytheon for the GBTS portion of JPATS.  The GBTS program includes the design, development, test, and installation of the GBTS components in accordance with the System Specifications (SS), the Program Unique Specification Document (PUSD) and the requirements of  the Statement of Work (SOW) 630-96-GBTS-01.  The GBTS end-items include:

  - Development Courseware

  - Conversion Courseware

  - Aircrew Training Devices (ATDs)

    - Flight Crew Training Devices (FTDs)

    - Procedural Training Devices (PTDs).

  - Operational Support System (OSS)

    - Training Integrated Management System (TIMS)

    - Computer Based Training System (CBTS)

    - Modification and Update Support System (MUSS)

      - TIMS Support System (TIMSSS)

      - ATD Support System (ATDSS)

      - Courseware Support System (CSS).

The GBTS project is managed by FlightSafety’s JPATS GBTS Program Management Office (PMO).  End-items are produced by Integrated Product Teams (IPTs) consisting of members from RAC, FlightSafety, and major subcontractors; Logicon for the TIMS, APEX for Conversion Courseware.  The GBTS PMO consists of FlightSafety Program Manager (PM), Deputies, leaders of the four primary IPTs, Process Managers from he Product Support Team (PST), and representatives from RAC and the government.  Two the IPTs have responsibility for software development:  the OSS IPT, led by Logicon, will develop software for the TIMS and the ATD IPT, led by FlightSafety’s Simulation Systems Division, (SSD), will develop software for flight training devices. The IPTs are supported by  process managers with GBTS-wide responsibilities.  Figure 1.2.1-1 provides an overview of the  GBTS program organization.

| OFT = Operational Flight Trainer | EPT = Emergency Procedures Trainer | CAI = Computer Aided Instruction |
| --- | --- | --- |
| IFT = Instrument Flight Trainer | EST = Ejection Seat Trainer | CBTS = Computer Based Training System |
| UTD = Unit Training Device | PPT = Parachute Procedures Trainer |  |

FIGURE 1.2-1  GBTS Hierarchy

FIGURE 1.2.1-1  Integrated Product Teams

### 1.2.2  APPLICABILITY

This plan is applicable to software development activities within the TIMS, CBTS, MUSS and FTD components of the JPATS GBTS.  Courseware development and conversion is not addressed within this SDP.

## 1.3  DOCUMENT OVERVIEW

The purpose of this document is to identify the uniform specifications for software development, documentation and verification on the JPATS GBTS program.  The SDP provides a documented methodology by which the GBTS practices and procedures will be applied consistently and uniformly throughout the life cycle of the system.  Appendix C contains a SDP to SOW cross reference and Appendix D has an ISO-9001 cross reference.

The objective of this document is to provide a quality solution to software development and to insure a high degree of reliability and maintainability through the use of a systematic approach to design and development.  The use of measurable milestones and metrics provides management visibility into the complex activities to be performed.

Exceptions to this plan may occur only as directed by the contract, or by the project manager with the concurrence of Raytheon Aircraft Company (Raytheon).

## 1.4  RELATIONSHIP TO OTHER PLANS

The SDP is a subset of the FlightSafety GBTS team’s engineering practices and policies and is to be utilized in conjunction with the following plans:

| Configuration Management Plan (CMP) and Software Configuration Management Plan (SCMP) | Detail plans and procedures for Software Configuration Management (SCMP) are set forth in the SCMP. The SCMP is included as an appendix to the GBTS CMP. The SCMP will satisfy the requirements of Section 5.14 of MIL-STD-498. |
| --- | --- |
| Courseware Development Plan | The Courseware Development Plan covers the design, development and production of the courseware products. This plan includes the requirements for the selection, integration and testing of computer software products which support and enable the development and delivery of courseware. |

| Integrated Management Plan (IMP) | The IMP defines key program events, their entry criteria and their success criteria. The SDP supports the IMP and those key events by insuring that software related entry and success criteria are met. |
| --- | --- |
| Integrated Test Plan (ITP) | The ITP defines detailed plans for integrated hardware/software and integrated system level component testing. This SDP defines requirements for software product evaluations, as well as unit, component, stand-alone Computer Software Configuration Item (CSCI) software testing, and post-integration testing software support |
| Quality Assurance Program Plan (QAPP) | The QAPP provides procedures for conducting quality evaluations. The SDP defines or references standards to be met during those evaluations, and invokes their conduct via requirements for walk-throughs, product audits, reviews and other evaluations. |
| Site Activation Plan (SAP) | The SAP defines processes for planning activations, performing installations, manning, and activating operating sites. This SDP defines the methods for transitioning software operation and support to those using sites. |
| System Engineering Management Plan (SEMP) | The SEMP defines system-level plans for requirements analysis and allocation, program planning and control, integrated hardware/software test requirements, and integrated system level component test requirements. This SDP defines plans for software requirements analysis, allocation, pre-integration software testing, and post-integration testing software support. |
| System Safety Plan (SSP) | The SSP identifies hazards and hazard alleviating actions. This SDP insures that the alleviating factors are included in the requirements analysis implemented in the applicable software products. |

# 2.0  REFERENCED DOCUMENTS (SOW 2020)

The following documents, in full or as tailored for this contract, are applicable to this plan.  Non-Government documents are available through the Subcontract Data Requirements List (SDRL) and the Data Accession List.

## 2.1  GOVERNMENT DOCUMENTS

| Number | Revision | Date | Title |
| --- | --- | --- | --- |
| IEEE Std 1074-1991 |  |  | IEEE Standard for Developing Software Life Cycle Processes |
| MIL-STD-498 |  |  | Software Development and Documentation dated 5 December 1994 |
| MIL-STD-882C |  |  | System Safety Program Requirements |
| MIL-STD-973 |  |  | Configuration Management |
| MIL-STD-1521B |  |  | Technical Reviews and Audits for Systems, Equipment, and Computer Software. |

## 2.2  NON-GOVERNMENT DOCUMENTS

| Number | Revision | Date | Title |
| --- | --- | --- | --- |
| JPATS-SOW-GBTS |  |  | Statement of Work for the JPATS GBTS |
| JPATS-SS-GBTS |  |  | System Specification for the JPATS GBTS |
| JPATS-PUSD-TIMS |  |  | Program Unique Specification Document: for the Training Integrated Management System (TIMS) Component of the JPATS GBTS |
| JPATS-PUSD-FTD |  |  | Program Unique Specification Document: for the Flight Training Device (FTD) Component of the JPATS GBTS |
| JPATS-PUSD-CBTS |  |  | Program Unique Specification Document: for the Computer Based Training System (CBTS) Component of the JPATS GBTS |
| JPATS-PUSD-MUSS |  |  | Program Unique Specification Document: for the Modification and Update Support System (MUSS) Component of the JPATS GBTS |
| SEPP-1000 |  |  | FlightSafety Services Corporation Software Engineering Practices/Procedures Manual |
| QAM-1000 |  |  | FlightSafety Services Corporation Quality Assurance Manual |
| LEIB |  |  | Logicon Engineering Instruction Binder (LEIB) |
| LSIS890297A |  | 31 March 96 | Logicon Quality Assurance Program, Volumes 1-2 |
| LSIS900213B |  | 31 March 96 | Logicon Configuration Management Program, Volumes 1-2 |
| SPC-94093-CMC | Version 1.0 | 10 Oct. 95 | Ada 95 Quality and Style: Guidelines for Professional Programmers |
| ANSI/STD.X3.135-1986 |  |  | Structured Query Language |
| SPC-91076-MC | Version 03.00 | 5 Dec. 93 | Evolutionary Spiral Process Model Guidebook |
|  |  | ©Microsoft Press, 1992 | The Windows Interface: An Application Design Guide |
|  |  | ©Microsoft Press, 1995 | Programming the Windows 95 User Interface |
|  |  | ©Microsoft Press, 1992 | Dynamics of Software Development |
| CMU/SEI-93-TR-6 |  |  | Taxonomy-Based Risk Identification |

# 3.0  OVERVIEW OF REQUIRED WORK (SOW 5020.1.9)

The objectives of the GBTS portion of the JPATS program is to design, develop, test, deploy, and support a GBTS in accordance with the SOW, SS, and PUSDs.  The GBTS must complement the aircraft in training Air Force and Navy undergraduate aviators.  The Operational Support Segment of the GBTS will support undergraduate flight training command-wide for Air Education and Training Command (AETC) and Chief of Naval Air Training (CNATRA).

There are two IPTs overseeing this development: the Aircrew Training Devices (ATD) IPT and the Operational Support System (OSS) IPT.  This SDP represents a combined effort of the IPTs in developing a software methodology and reporting system which will effectively manage and control all software development activities.  Figure 3.0-1 shows the inter-relationship between the IPTs and the development areas.  The JPATS GBTS software development efforts are focused primarily within two of the areas:  the Flight Training Devices (FTD) and the Training Integrated Management System (TIMS).  Commercial Off The Shelf  (COTS) software will be used for the other three areas:  the Procedural Training Devices (PTD), the Modification Update Support System (MUSS), and the Computer Based Training System (CBTS).

Each of the Computer Software Configuration Items (CSCIs) and/or Hardware Configuration Item (HWCI)/CSCI combinations addressed within this SDP will have a corresponding Program Unique Specification Document (PUSD).  The PUSD contains the requirements from the System Specification (SS), aircraft and technical requirements and the derived requirements, both at the system and subsystem levels.  Additionally the PUSD will contain a summary of the test and evaluation criteria, together with the evaluation methodology that will be utilized to verify each  performance requirement.  The PUSD will be refined during the system design synthesis phase and will represent the product of the mission and functional analyses, the design allocation, tradeoff analyses, and optimized system engineering activities.

The SEMP, as discussed in Section 1.4, defines the system-level plans for requirements analysis and allocation, program planning and control, integrated hardware/software test requirements, and integrated system level component test requirements.  This SDP defines the plans for software requirements analysis, allocation, pre-integration software testing, and post-integration testing support.

The GBTS Product Support Teams (PSTs, see Fig. 1.2.1-1) and individual IPTs will verify that requirements are flowed down from the SEMP and the PUSD into the appropriate software  documents.  Figures 3.0-2 through 3.0-5 show the documents to be produced.  These documents outline the software engineering, management, operations & support, and the program testing for the JPATS GBTS program.

## 3.1  SYSTEM REQUIREMENTS AND CONSTRAINTS (SS 3.4.10.2)

The FlightSafety team will utilize COTS software wherever feasible.  Operating systems will be COTS.  Other GBTS software will be written in Query Language (SQL) in accordance with ANSI/STD.X3.135-1986 or other languages as documented within this SDP.  Software will be robust and fault tolerant.  All development software will be object oriented.  The software will be modular with minimal dependence of the operation of one module on the internal details of other modules.  Items subject to frequent change will be modifiable without source code changes or recompilation.  COTS software will not be modified, except for tailoring and reconfiguration as allowed by the original provider.

FIGURE 3.0-1  Software Development Areas

All software will function correctly on two different-vendor hardware platforms without any modifications to source code.  Recompilation of the unmodified source code for the new target processors will be allowed.  Functions of the Operational Support System will be operable from any node on the network provided the required hardware is installed.

Detailed system level requirements and constraints are provided within the appropriate PUSD.  The following contract requirements will be enforced for GBTS software development activities.

### 3.1.1  AIRCREW TRAINING DEVICES (SOW 5010.3)

The ATD IPT will  oversee the design, development, install and test of the Operational Flight Trainer (OFT), Instrument Flight Trainer (IFT), the Unit Training Device (UTD), Ejection Seat Trainer (EST), the Egress Procedures Trainer (EPT) and the Parachute Procedures Trainer (PPT) in accordance with the System

Specifications (SS) and the applicable PUSD.  The FTD IPT, under the ATD IPT, will produce the OFT, IFT and UTD.  The remaining ATD products do not contain software.  The FTD IPT will also provide the ATD Support System (ATDSS) component of the MUSS.

### 3.1.2  OPERATIONAL SUPPORT SEGMENT (SOW 5010.4)

The OSS IPT will oversee the design, development, installation, and testing of the Operational Support Segment consisting of the TIMS, CBTS and MUSS in accordance with the SS and the applicable component PUSDs.  The CBTS is a subset of the TIMS containing only COTS software and courseware which is not covered by this plan.  The MUSS components are COTS or Non-Development Item (NDI) software systems consisting of the  ATDSS, TIMS Support System (TIMS-SS) and Courseware Support System (CSS).

The OSS IPT will  review the analysis of AETC and CNATRA operations reports outlining the proposed reports and displays.  The OSS IPT will additionally review the analysis of the Headquarters, Groups, Wings, Squadrons, Flights, and ancillary operations equipment needs to evaluate if the proposed quantities are correct for operations.  The OSS IPT will update, refine, and streamline this operational concept as the system design matures.  The operational concept will focus on the user interface to enhance different users' performance of their duties using the new system.

The TIMS IPT will produce the CBTS, CSS and TIMS-SS in conjunction with the TIMS product.  The TIMS IPT will perform the software development efforts associated with the OSS IPT.

#### 3.1.2.1  Training Integration Management System. (SOW 5010.4.1)

The OSS IPT will oversee the design, development, integration, installation and testing of all hardware, software, data services and facilities required to produce the TIMS.  The OSS IPT will review the findings of the analysis of the current flight training operations using the TIMS As-Is Object-Oriented Model (YT-93-1573).  The  IPT will also develop and document a concept of operations for the TIMS, integrated with the functions of the CBTS and MUSS components.  The IPT will use prototypes as part of the development effort.  The IPT will generate a System/Subsystem Design Description (SSDD).  The IPT will provide prototypes at two Government designated operational locations for field evaluation.  The IPT will conduct TIMS requirements data gathering and prototype analysis activities in the San Antonio, TX area.

##### 3.1.2.1.1  TIMS Proof-of Concept Prototypes. (SOW 5010.4.1.1)

TIMS IPT will develop TIMS proof-of-concept prototypes during requirements analysis and design.  User-interface, scheduling, and network performance and design concepts will be prototyped.  The prototypes will be used to define the applicable portions of the TIMS allocated baseline.

##### 3.1.2.1.2  TIMS Interfaces. (SOW 5010.4.1.2)

The TIMS IPT will generate an Interface Requirements Specification (IRS) for the TIMS.  The TIMS interfaces to external systems will be identified in the IRS.  The TIMS IPT will provide a plan for the definition, development, and implementation of the TIMS external interfaces.  For each external interface, the plan identifies:

- a cognizant organization and individual responsible for information about the data from the external system

- the specific responsibilities and tasks for the cognizant organization

- the time frames for those tasks

- the overall schedule and IMP activities.  (DI-IPSC-81434/T)

FIGURE 3.0-2  Engineering Documentation Flow-Down

FIGURE 3.0-3  Operation and Support Documentation Flow-Down

FIGURE 3.0-4  Management Documentation Flow-Down

FIGURE 3.0-5  Formal Test Documentation Flow-Down

#### 3.1.2.2  Computer-Based Training System. (SOW 5010.4.2)

The OSS IPT will oversee the identification, design, integration, procurement, testing and installation of the CBTS, in accordance with the SS and applicable PUSD.  The equipment will consist of only off-the-shelf, commercially available items.

### 3.1.3  MODIFICATION AND UPDATE SUPPORT SYSTEM (SOW 5010.4.3)

The OSS IPT will oversee the development, production, installation and testing of the MUSS, in accordance with the SS and applicable PUSD.  The MUSS will be comprised of integrated, communications networked components, and functions of the ATDSS, the CSS, and the TIMS-SS.  The OSS and FTD IPTs will provide a separate users manual for operation of each of the MUSS elements:  CSS, ATDSS, and TIMS-SS.  (DI-IPSC-81443/T)

## 3.2  REQUIREMENTS AND CONSTRAINTS ON PROJECT DOCUMENTATION (SOW 5020.3.2.4, 5050.3- 3.2)

The  IPTs will provide software documentation for all GBTS software, including COTS, to include the following: computer software source code listings (excluding COTS); vendor supplied operating system; software user manuals; software test descriptions (TIMS only); interface requirements specifications (TIMS only), and software product specifications.  Documentation for COTS software will be delivered by the vendor, but will be referenced in the documentation for the configuration item in which it is assigned.  Management and support data will be provided in accordance with the SDRLs.  The GBTS Program Office will also provide Raytheon and the Government with access to paper and electronic copies of internal documents which were produced to manage the GBTS program and to design, develop, and test the GBTS.  Data Accession List requirements will be flowed down to major suppliers and a electronic listing of subcontractor's data will be available upon request.  All word processing data will be developed using MS Windows Word 6.0 or MS Windows Excel 4.0.  Figures 3.0-2 through 3.0-5, in Section 3.0, show the documentation to be produced for the JPATS GBTS.

## 3.3  SYSTEM LIFE CYCLE DATA

The components of this software development effort vary in the depth of complexity and the point of origin in the software life cycle model.  The FTDs follow a long-term single pass build approach, or Grand Design, approach for software development, .The TIMS more closely represent a rapid-build, incremental  approach.  Each follows the same general guidelines for development but with a different time line.

Software development for the Flight Training Devices will begin with an existing baseline.  Previous corporate simulation projects provide a firm foundation for the functional and allocated baselines within the development process.  Based on this experience, FlightSafety has an existing software architecture for FTDs.  New devices follow this basic architecture and software modules are developed or modified based upon the systems and performance of the specific aircraft being simulated.  In this case, the Beech Mk II Aircraft.  Specific flight parameters and aerodynamics are outlined within the PUSD for the  aircraft during the design phase.  Each FTD will go through the normal software development phases only once.  However, due to the reusable nature of FTD software modules, a given module may have previously been through the Software Life Cycle (SLC) many  times.

The TIMS CSCI begins this program during the early stages of the system concept phase and follows a rapid progression throughout the system life-cycle.  System requirements will be progressively  defined and refined  through the use of rapid prototyping tools and incremental development.

CBTS software consists of a computer-based training (CBT) authoring language and courseware authoring tools.  Both are COTS.  The CBT authoring language was selected on the basis of a rigorous trade study (see Appendix F, Volume 1 of this proposal).  Pending government approval the CBT authoring language will be Authorware. Using COTS software for the CBTS significantly reduces the system time line. The design and coding phases, therefore, are reduced to a verification and validation of system interface parameters.

The Modification Update Support System (MUSS) is the delivery of the tools used during the development stages of the FTDs, the CSS and the TIMS and the incorporation of them into a support package for the on-site management of the JPATS GBTS.  Therefore the majority of effort on this CSCI will occur during the installation and site planning phases of development.  The development process will serve to fully test the ability of the software to meet the program objectives.

## 3.4  PROGRAM ACQUISITION STRATEGY

Not applicable.

## 3.5  SCHEDULE REQUIREMENTS AND CONSTRAINTS

Schedule requirements and constraints associated with the GBTS basic and optional Contract Line Items are set forth in the  Master Integrated Program Schedule (MIPS).  The MIPS outlines criteria for determining measurable program progress, status reporting and corrective procedures.

## 3.6  OTHER REQUIREMENTS AND CONSTRAINTS

### 3.6.1  CONFIGURATION MANAGEMENT SYSTEM REQUIREMENTS

Each software development entity will operate a configuration management (CM) system which will interface with and be compatible with the CM processes and products employed by the Raytheon JPATS program office.  The COTS “ClearCase” tool is used by all GBTS IPTs for automated CM.

### 3.6.2  TRACEABILITY SYSTEM REQUIREMENTS

Each software development entity will maintain a traceability matrix for their developed software.  The system employed will interface with and be compatible with the traceability maintenance processes and products employed by the Raytheon JPATS program office.  GBTS IPTs employ the COTS “Dynamic Object Oriented Requirements System” (DOORS) tool for requirements traceability.

### 3.6.3  VERIFICATION ENVIRONMENT REQUIREMENTS AND CONSTRAINTS

All requirements flow down to software from the development specifications.  All derived requirements will be traced to an activity or trade study.  Verification will be achieved and documented in DOORS.  The DOORS database is available to Raytheon and the Government.

### 3.6.4  RISK MANAGEMENT REQUIREMENTS AND CONSTRAINTS

The procedures and practices outlined in the SEMP will be followed for software risk management.

### 3.6.5  SUBCONTRACTOR MANAGEMENT (SOW 5020.2.2)

Where subcontractors are used to produce project software and its documentation, the prime GBTS contract requirements will be imposed on the subcontracted portion of the software development effort.  Project requirements will be passed down via a statement of work, development specification, schedule and SDRL requirements.  Subcontractors and subcontract activities are be integrated into the appropriate IPTs.

The GBTS team performs supplier Quality Assurance (QA) reviews prior to selecting any vendor or subcontractor in accordance with QAM-1000 procedure numbers Q-3515 and Q-3520.

The contractor/subcontractor relationship of Logicon and FlightSafety as applicable to software development is defined in Section 7.1 of this plan.

# 4.0  PLANS FOR PERFORMING GENERAL SOFTWARE DEVELOPMENT ACTIVITIES (SOW 5020.2.1)

Software development activities for the FTDs will be performed at the FlightSafety’s Simulation System Division in Broken Arrow, OK.  TIMS software development activities will be performed at Colorado Springs, CO.  TIMS  field evaluations will be conducted at two government-determined sites.

The following pages provide a complete and integrated approach to plan, develop, implement and support  JPATS GBTS software development. This section includes both general and detailed planning for software development across the JPATS GBTS program.  It provides a general approach for software development including development life cycle methodology, the development environment, and the minimum acceptable standards and procedures for development.

## 4.1  SOFTWARE DEVELOPMENT PROCESS

Primary objectives for the  software engineering process are:

- to consistently manage technical performance within the constraints of the specific task work statements while producing a quality product

- to minimize technical, staffing, cost and schedule risks associated with developing a software product; and

- to fulfill all contractual requirements with respect to developing the software product.

To  achieve these goals the FTD IPT uses a Grand Design build approach and the TIMS IPT employs an incremental build approach.  The FTD’s single pass approach to software development represents an increment in FlightSafety’s development of software models for approximately 15 different types of Flight simulators per year, where the software architectures of the various simulators are identical or nearly identical.  The TIMS multiple passes incremental build throughout the life cycle  allows requirements to be re-evaluated against progressively mature designs.  Tables 4.1-1 and 4.1-2 describe the software development process entry and exit criteria for FTD and TIMS software respectively.  These criteria are used for incremental and grand design software development efforts with deliverable tailoring as set forth in SDP Appendix A.

The following sections describe the level of detail required for each of the CSCIs.

### 4.1.1  FTD SOFTWARE DEVELOPMENT PROCESS

The FTD CSCIs are embedded software systems within three end items: the Operational Flight Trainer (OFT), Instrument Flight Trainer (IFT), and the Unit Training Device (UTD).  The three types of end items differ only in selected areas:  1) The UTD has no visual system nor is it equipped with a dynamic seat, and 2) the OFT’s visual is a 5 channel wide field of view unit, while the IFT’s visual is a single channel narrow field of view unit.

| FTD Related System Requirements Analyses |  |  |  |  |
| --- | --- | --- | --- | --- |
| Process Products | Process Entry Criteria |  | Process Exit Criteria |  |
| - Ops concept - System Requirements - System External Interfaces documented - System Requirements Review (SRR) - Traceability between SS and SOW - SRR |  | - Authorization by IPT Leader - Start of contract - Preliminary SDP defined, documented, reviewed, and approved |  | - System/subsystem and external interface requirements defined, documented, reviewed, and approved (SS, PUSD, prelim. IRS) - System Requirements Review (SRR) completed per contract and SDP - All peer reviews completed - System and system interface requirements placed under program configuration control per SDP - Authorization by IPT Leader |
| FTD Related System Design |  |  |  |  |
| Process Products |  | Process Entry Criteria |  | Process Exit Criteria |
| - System Design Review(SDR) - Component Specification Review (CSR) - Traceability between system requirements and system design components (SS to PUSD, SS to SSDD) - Updates to system requirements |  | - Authorization by IPT Leader - Preliminary system/subsystem requirements and external interfaces defined |  | - TIMS system/subsystem top-level design defined, documented, reviewed, and approved (SSDD) - System Design Review (SDR) completed per contract and SDP - Component level system requirements (PUSD) refined, defined, reviewed and approved at Component Specification Reviews(CSR) - Authorization by IPT Leader |
| FTD Software Requirements Analysis |  |  |  |  |
| Process Products |  | - Process Entry Criteria |  | Process Exit Criteria |
| - Software, data, and interface requirements - Traceability between software and system/subsystem requirements - Updates to requirements and traceability matrices - Software Specification Review (SSR) |  | - Authorization by IPT Leader - Preliminary system/subsystem and external interface requirements defined, documented, and reviewed - Preliminary system/subsystem allocation of requirements to hardware, software, and personnel defined, documented, and reviewed |  | - Software and interface requirements defined, documented, reviewed, and approved (SRS, IRS) - Preliminary STP reviewed - Software Specification Review (SSR), evaluations, and audits completed per contract and SDP - All peer reviews completed - Software and interface requirements placed under program configuration control per SDP - Authorization by IPT Leader |
| FTD Software Architectural Design |  |  |  |  |
| Process Products |  | - Process Entry Criteria |  | Process Exit Criteria |
| - Software, interfaces, database and adaptation overall design, and architectural design - Design-to-requirements traceability matrix - Updates to design and traceability matrices - Preliminary Design review (PDR) |  | - Authorization by IPT Leader - Preliminary system/subsystem allocation of requirements to hardware, software, and personnel defined, documented, and reviewed - Preliminary software and interface requirements defined, documented, and reviewed |  | - Software, interface, and database overall design decisions and architectural design defined, documented, reviewed, and approved (design in SPS) - STP documented, reviewed and approved - Preliminary Design Review (PDR), evaluations, and audits completed per contract and SDP - All peer reviews completed per SDP - Software architectural design placed under development configuration control per the SDP - Authorization by IPT Leader |

TABLE 4.1-1  FTD Software Engineering Processes

| FTD Detailed Design |  |  |
| --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |
| - Software, interfaces, database and adaptation detailed design - Design-to-requirements traceability matrix updates - Updates to design and traceability matrices - Critical Design review (CDR) | - Authorization by IPT Leader - Software overall design decisions and preliminary architectural design defined, documented, and reviewed | - Software, interfaces, and database detailed design defined, documented, reviewed, and approved per contract (design in SPS) - Critical Design Review (CDR), evaluations, and audits completed per contract, and SDP - All peer reviews completed per the SDP - All accepted software requirements and design problem reports resolved per SDP-defined priority thresholds - Software detailed design placed under development configuration control per the SDP - Authorization by IPT Leader |
| FTD Code and Unit Test |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |
| - Unit-tested software code, databases, files, data, and procedures - Unit test cases, procedures, data, and results - Updates to software, databases, files, data, and procedures - Updates to unit test cases, procedures, data, and results | - Authorization by IPT Leader - Software unit detailed design defined, documented, and reviewed - Software unit interface and database detailed design defined, documented, and reviewed | - Software design implemented in software code and unit-tested per the SDP for current increment. - Data definitions, databases, and files created, populated, and tested per the SDP - Unit test results recorded in Software Development Files per the SDP - All software code and unit test reviews, evaluations, and audits completed per the contract, SDP, and program Quality Evaluation Plan - All peer reviews completed per the SDP - All requirements, design, and code and unit test problem reports resolved per priority thresholds defined in the SDP - Unit source code, data definitions, databases, files, deliverable data, and procedures placed under development configuration control per the SDP and CM Plan - Authorization by IPT Leader |

TABLE 4.1-1  FTD Software Engineering Processes (Continued)

| FTD Preparation for Integration and Test |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria |  | Process Exit Criteria |
| - Unit Integration plan, test case descriptions, and procedures - Unit Integration environment - CSCI/HWCI Integration plan, test case descriptions, and procedures - CSCI/HWCI Integration environment - CSCI Qualification test plan, test case descriptions, and test procedures - Acceptance Test Plan, Test Case descriptions, and Test Procedures - System test environment - Updates to integration and test plans, test case descriptions, and test procedures |  | - Authorization by IPT Leader - Preliminary system/subsystem and external interface requirements defined, documented, and reviewed - Preliminary system/subsystem allocation of requirements to hardware, software, and personnel defined, documented, and reviewed - SDP defined, documented, reviewed, and approved. | - Software, interface, and database detailed design defined, documented, reviewed, and approved per the contract - Software integration plan, test case descriptions, and integration procedures defined, documented, reviewed, and approved by IPT Lead and placed under development configuration control - Software integration environment established - TIMS Software CSCI qualification test case descriptions, and test procedures defined, documented, reviewed, and approved for current increment (STD). FTD test case descriptions and test procedures defined, documented and reviewed (DTP). Test description and procedures placed under configuration control. - Software test environment established - System Test Plan, test case descriptions, and test procedures defined, documented, reviewed, and approved. The System Test Plan and Test Procedures placed under configuration control. - System test environment established - All preparations for software test reviews, evaluations, and audits completed per the contract and SDP - All peer reviews completed per the SDP - All preparation for integration and test documentation problem reports resolved per priority thresholds defined in the SDP - Authorization by IPT Leader |

TABLE 4.1-1  FTD Software Engineering Processes (Continued)

| FTD Unit Integration and Test |  |  |
| --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |
| - Integrated and tested software items (code, data definitions, databases, files, data, and procedures) - Integration and test results - Updates to integration and test plans, test case descriptions, and test procedures | - Authorization by IPT Leader - Unit source code, data definitions, databases, files, data, and procedures developed, unit tested, and under development configuration control - Preliminary build/make and adaptation procedures and required supporting integration environment exist - SDP defined, documented, reviewed, and approved - Software integration plan defined, documented, reviewed, and approved by IPT Leader - Software integration test case descriptions defined, documented, and approved - Preliminary software integration procedures defined, documented, and reviewed - Preliminary Software Qualification Test Plan defined, documented, reviewed, and approved | - Software units integrated and tested per the SDP - All data definitions, databases, and files created, populated, and tested per the SDP - All build/make and adaptation procedures integrated and tested per the SDP - Increment integration results recorded per the SDP and summarized in internal test reports for each increment. - All peer reviews completed per the SDP - All software design, code and unit test, and integration problem reports resolved per priority thresholds defined in the SDP - Software unit source code, build/make procedures, data definitions, databases, files, and deliverable data placed under program configuration control per the SDP - Authorization by IPT Leader |
| FTD Unit/Component Qualification Test |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |
| - Tested software items (code, data definitions, databases, files, data, and procedures) - Test results and test report - Updates to test plans, test case descriptions, and test procedures - Test reviews | - Authorization by IPT Leader - Source code developed, unit tested, integrated, and under program configuration control - Data definitions, databases, files, and data developed, unit tested, integrated, and under program configuration control - Build/make procedures defined, tested, and under program configuration control - Required supporting test environment exists and is under configuration control - SDP defined, documented, reviewed, and approved - Software Test Plan (STP) defined, documented, reviewed, approved, and under CM control - Software qualification test case descriptions and procedures (STD) defined, documented, reviewed, approved, and under CM control | - Software tested per the STP. Increment qualification test results recorded in a interim test report per the SDP. Results summarized and reported in a Software Test Report per the SDP. - Software, data definitions, databases, files, and data tested per the STP. - Build/make and adaptation procedures tested per the Software Test Plan - All peer reviews completed per the SDP - All software design, code, unit test, integration, and qualification test problem reports resolved per priority thresholds defined in the SDP. - Source code, build/make and adaptation procedures, data definitions, databases, files, and deliverable data under program configuration control per the SDP - Authorization by IPT Leader |

TABLE 4.1-1  FTD Software Engineering Processes (Continued)

| FTD Component HW/SW Integration and Test |  |  |  |  |
| --- | --- | --- | --- | --- |
| Process Products |  | - Process Entry Criteria | Process Exit Criteria |  |
| - Individually integrated and tested software/hardware components (code, data definitions, databases, files, data, equipment, and procedures) - Integration and test results - Updates to integration and test plans, test case descriptions, and test procedures |  | - Authorization by IPT Leader - Unit source code, data definitions, databases, files, data, and procedures developed, unit tested, and under development configuration control - Preliminary build/make and adaptation procedures and required supporting integration environment exist - GBTS SW/HW integration plan defined, documented, reviewed, and approved - Software/hardware integration test case descriptions defined, documented, and approved - Preliminary software integration procedures defined, documented, and reviewed - Preliminary System Development Test Procedures defined, documented, reviewed, and approved | - All software units integrated and tested per SDP at the GBTS in-plant test site. Test results recorded. Results summarized and recorded in internal test report for inclusion in the GBTS in-plant test report. - All data definitions, databases, and files created, populated, and tested per SDP - All build/make and adaptation procedures integrated and tested - All peer reviews completed per the SDP - All software/hardware design, code and unit test, and integration problem reports resolved per priority thresholds defined in the SDP - Software unit source code, build/make procedures, data definitions, databases, files, and hardware equipment and deliverable data placed under program configuration control per the SDP - Authorization by IPT Leader |  |
| FTD Component Integration and Test |  |  |  |  |
| Process Products |  | - Process Entry Criteria |  | Process Exit Criteria |
| - Integrated and tested ATD. - System test results and test report. - Updates to test plans, test case descriptions, and test procedures - System Test reviews | - Authorized by IPT Leader. - Component source code developed, unit tested, integrated, and under program configuration control - Data definitions, databases, files, and data developed, unit tested, integrated, and under program configuration control - Build/make procedures defined, tested, and under program configuration control - Required supporting test environment exists and is under configuration control - System Test Plan defined, documented, reviewed, and approved - System development test case descriptions and procedures defined, documented, reviewed, and approved |  | - Software/hardware tested per the ATD Development Test Plan (DTP) - Data definitions, databases, files, and data tested per the ATD DTP - Build/make and adaptation procedures tested per the DTP - Acceptance test results recorded in a system test report per the SDP - All peer reviews completed per the SDP - All software/hardware design, code, unit test, integration, and qualification test problem reports resolved per priority thresholds defined in the SDP and Program Configuration Control Board direction - Source code, build/make and adaptation procedures, data definitions, databases, files, equipment and deliverable data under program configuration control per the SDP - Authorization by IPT Leader |  |

TABLE 4.1-1  FTD Software Engineering Processes (Continued)

| FTD Qualification Test |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Tested software/ hardware items (code, data definitions, databases, files, data, equipment and procedures) - System Test results and test report - Updates to System test plans, test case descriptions, and test procedures - System Test reviews | - Authorization by IPT Leader - System developmental testing completed and corrective actions completed. - Build/make procedures defined, tested, and under program configuration control - Required supporting test environment exists and is under configuration control - System Test Plan defined, documented, reviewed, and approved - System acceptance test case descriptions and procedures defined, documented, reviewed, and approved | - Software/hardware tested per the ATD Acceptance Test Plan (ATP) - Data definitions, databases, files, and data tested per the ATD ATP - Build/make and adaptation procedures tested per the ATP - Acceptance test results recorded in a system qualification test report per the SDP - All peer reviews completed per the SDP - All software/hardware design, code, unit test, integration, and qualification test problem reports resolved per priority thresholds defined in the SDP and Program Configuration Control Board direction - Source code, build/make and adaptation procedures, data definitions, databases, files, equipment and deliverable data under program configuration control per the SDP - Authorization by IPT Leader |  |
| FTD Software Support (Installation, Transition) |  |  |  |
| Process Products | - Process Entry Criteria |  | Process Exit Criteria |
| - Updates to software, databases, files, data, procedures, and supporting material - Updates to unit test cases, procedures, data, and results | - Authorization by IPT Leader Unit source code, data definitions, databases, files, deliverable data, and procedures placed under development configuration control per the SDP - Software/documentation problem report dispositioned for resolution | - All code, data definitions, databases, files, deliverable data, and procedure problem reports resolved (implemented, tested, and documentation updates completed) per the SDP-defined priority thresholds and/or Configuration Control Board disposition - All peer reviews completed per the SDP - All final deliverable code, data definitions, databases, files, deliverable data, procedures, and documentation reviewed, evaluated, and audited per the SDP - All deliverable software documentation completed, reviewed, and approved by the contracting agency per the contract and the SDP - All deliverable source code, data definitions, databases, files, deliverable data, procedures, and documentation placed under product configuration control per the contract, SDP, and CM Plan - All internal program/organizational software documentation completed, reviewed, and approved - Authorization by IPT Leader |  |

TABLE 4.1-1  FTD Software Engineering Processes (Continued)

| TIMS/OSS System Requirement Analysis |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Ops concept - System Requirements - System External Interfaces documented - System Requirements Review (SRR) - Traceability between SS and SOW - SRR | - Authorization by IPT Leader - Start of contract - Preliminary SDP defined, documented, reviewed, and approved |  | - System/subsystem and external interface requirements defined, documented, reviewed, and approved (SS, PUSD, prelim. IRS) - System Requirements Review (SRR) completed per contract and SDP - All peer reviews completed - System and system interface requirements placed under program configuration control per SDP - Authorization by IPT Leader |
| TIMS/OSS System Design |  |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - System Design Review(SDR) - Component Specification Review (CSR) - Traceability between system requirements and system design components (SS to PUSD, SS to SSDD) - Updates to system requirements | - Authorization by IPT Leader - Preliminary system/subsystem requirements and external interfaces defined - . |  | - TIMS system/subsystem top-level design defined, documented, reviewed, and approved (SSDD) - System Design Review (SDR) completed per contract and SDP - Component level system requirements (PUSD) refined, defined, reviewed and approved at Component Specification Reviews(CSR) - Authorization by IPT Leader |
| - Software, data, and interface requirements - Traceability between software and system/subsystem requirements - Updates to requirements and traceability matrices - Software Specification Review (SSR) | - Authorization by IPT Leader - Preliminary system/subsystem and external interface requirements defined, documented, and reviewed - Preliminary system/subsystem allocation of requirements to hardware, software, and personnel defined, documented, and reviewed |  | - Software and interface requirements defined, documented, reviewed, and approved (SRS, IRS) - Preliminary STP reviewed - Software Specification Review (SSR), evaluations, and audits completed per contract and SDP - All peer reviews completed - Software and interface requirements placed under program configuration control per SDP - Authorization by IPT Leader |
| TIMS/OSS Software Requirements Analysis |  |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Software, data and interface requirements - Traceability between software and system/subsystem requirements - Updates to requirements and traceability matrices - Software Specification review (SSR) | - Authorization by IPT Leader - Preliminary system/subsystem and external interface requirements defined, documented, and reviewed - Preliminary system/subsystem allocation of requirements to hardware, software, and personnel, defined, documented and reviewed. |  | - Software and interface requirements defined, documented, reviewed, and approved (SRS, IRS) - Preliminary STP reviewed - Software Specification Review (SSR), evaluations, and audits completed per contract and SDP - All peer reviews completed per SDP - Software and interface requirements placed under program configuration control per the SDP - Authorization by IPT Leader |

TABLE 4.1-2  TIMS/OSS Software Engineering Processes

| TIMS/OSS Software Architectural Design |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Software, interfaces, database and adaptation overall design, and architectural design - Design-to-requirements traceability matrix - Updates to design and traceability matrices - Preliminary Design review (PDR) | - Authorization by IPT Leader - Preliminary system/subsystem allocation of requirements to hardware, software, and personnel defined, documented, and reviewed - Preliminary software and interface requirements defined, documented, and reviewed |  | - Software, interface, and database overall design decisions and architectural design defined, documented, reviewed, and approved (design in SPS) - STP documented, reviewed and approved - Preliminary Design Review (PDR), evaluations, and audits completed per contract and SDP - All peer reviews completed per SDP - Software architectural design placed under development configuration control per the SDP - Authorization by IPT Leader |
| TIMS/OSS Detailed Design |  |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Software, interfaces, database and adaptation detailed design - Design-to-requirements traceability matrix updates - Updates to design and traceability matrices - Critical Design review (CDR) | - Authorization by IPT Leader - Software overall design decisions and preliminary architectural design defined, documented, and reviewed |  | - Software, interfaces, and database detailed design defined, documented, reviewed, and approved per contract (design in SPS) - Critical Design Review (CDR), evaluations, and audits completed per contract, and SDP - All peer reviews completed per the SDP - All accepted software requirements and design problem reports resolved per SDP-defined priority thresholds - Software detailed design placed under development configuration control per the SDP - Authorization by IPT Leader |
| TIMS/OSS Code and Unit Test |  |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Unit-tested software code, databases, files, data, and procedures - Unit test cases, procedures, data, and results - Updates to software, databases, files, data, and procedures - Updates to unit test cases, procedures, data, and results | - Authorization by IPT Leader - Software unit detailed design defined, documented, and reviewed - Software unit interface and database detailed design defined, documented, and reviewed |  | - Software design implemented in software code and unit-tested per the SDP for current increment. - Data definitions, databases, and files created, populated, and tested per the SDP - Unit test results recorded in Software Development Files per the SDP - All software code and unit test reviews, evaluations, and audits completed per the contract, SDP, and Quality Assurance Program Plan - All peer reviews completed per the SDP - All requirements, design, and code and unit test problem reports resolved per priority thresholds defined in the SDP - Unit source code, data definitions, databases, files, deliverable data, and procedures placed under development configuration control per the SDP and CM Plan - Authorization by IPT Leader |

TABLE 4.1-2  TIMS/OSS Software Engineering Processes (Continued)

| TIMS/OSS Preparation for Integration and Test |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Unit Integration plan, test case descriptions, and procedures - Unit Integration environment - CSCI/HWCI Integration plan, test case descriptions, and procedures - CSCI/HWCI Integration environment - CSCI Qualification test plan, test case descriptions, and test procedures - Acceptance Test Plan, Test Case descriptions, and Test Procedures - System test environment - Updates to integration and test plans, test case descriptions, and test procedures | - Authorization by IPT Leader - Preliminary system/subsystem and external interface requirements defined, documented, and reviewed - Preliminary system/subsystem allocation of requirements to hardware, software, and personnel defined, documented, and reviewed - SDP defined, documented, reviewed, and approved. |  | - Software, interface, and database detailed design defined, documented, reviewed, and approved per the contract - Software integration plan, test case descriptions, and integration procedures defined, documented, reviewed, and approved by IPT Lead and placed under development configuration control - Software integration environment established - TIMS Software CSCI qualification test case descriptions, and test procedures defined, documented, reviewed, and approved for current increment (STD). FTD test case descriptions and test procedures defined, documented and reviewed (DTP). Test description and procedures placed under configuration control. - Software test environment established - System Test Plan, test case descriptions, and test procedures defined, documented, reviewed, and approved. The System Test Plan and Test Procedures placed under configuration control. - System test environment established - All preparations for software test reviews, evaluations, and audits completed per the contract and SDP - All peer reviews completed per the SDP - All preparation for integration and test documentation problem reports resolved per priority thresholds defined in the SDP - Authorization by IPT Leader |

TABLE 4.1-2  TIMS/OSS Software Engineering Processes (Continued)

| TIMS/OSS Unit Integration and Test |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Integrated and tested software items (code, data definitions, databases, files, data, and procedures) - Integration and test results - Updates to integration and test plans, test case descriptions, and test procedures | - Authorization by IPT Leader - Unit source code, data definitions, databases, files, data, and procedures developed, unit tested, and under development configuration control - Preliminary build/make and adaptation procedures and required supporting integration environment exist - SDP defined, documented, reviewed, and approved - Software integration plan defined, documented, reviewed, and approved by IPT Leader - Software integration test case descriptions defined, documented, and approved - Preliminary software integration procedures defined, documented, and reviewed - Preliminary Software Test Plan defined, documented, reviewed, and approved |  | - Software units integrated and tested per the SDP - All data definitions, databases, and files created, populated, and tested per the SDP - All build/make and adaptation procedures integrated and tested per the SDP - Increment integration results recorded per the SDP and summarized in internal test reports for each increment. - All peer reviews completed per the SDP - All software design, code and unit test, and integration problem reports resolved per priority thresholds defined in the SDP - Software unit source code, build/make procedures, data definitions, databases, files, and deliverable data placed under program configuration control per the SDP - Authorization by IPT Leader |
| TIMS/OSS CSCI Qualification Test |  |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Tested software items (code, data definitions, databases, files, data, and procedures) - Test results and test report - Updates to test plans, test case descriptions, and test procedures - Test reviews - Functional and physical configuration audits | - Authorization by IPT Leader - Source code developed, unit tested, integrated, and under program configuration control - Data definitions, databases, files, and data developed, unit tested, integrated, and under program configuration control - Build/make procedures defined, tested, and under program configuration control - Required supporting test environment exists and is under configuration control - SDP defined, documented, reviewed, and approved - Software Test Plan (STP) defined, documented, reviewed, approved, and under CM control - Software qualification test case descriptions and procedures (STD) defined, documented, reviewed, approved, and under CM control |  | - Software tested per the STP and STD. Increment qualification test results recorded in a interim test report per the SDP. Final in-plant qualification test results recorded. Results summarized and reported in a Software Test Report per the SDP. - Software, data definitions, databases, files, and data tested per the STP and STD. - Build/make and adaptation procedures tested per the Software Test Plan - All peer reviews completed per the SDP - All software design, code, unit test, integration, and qualification test problem reports resolved per priority thresholds defined in the SDP and Program Configuration Control Board direction - Source code, build/make and adaptation procedures, data definitions, databases, files, and deliverable data under program configuration control per the SDP - Functional Configuration Audit (FCA) completed per the SDP and contract - Authorization by IPT Leader |

TABLE 4.1-2  TIMS/OSS Software Engineering Processes (Continued)

| TIMS/OSS CSCI/HWCI Integration and Test |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Integrated and tested software/hardware items (code, data definitions, databases, files, data, equipment, and procedures) - Integration and test results - Updates to integration and test plans, test case descriptions, and test procedures | - Authorization by IPT Leader - Unit source code, data definitions, databases, files, data, and procedures developed, unit tested, and under development configuration control - Preliminary build/make and adaptation procedures and required supporting integration environment exist - GBTS SW/HW integration plan defined, documented, reviewed, and approved - Software/hardware integration test case descriptions defined, documented, and approved - Preliminary software integration procedures defined, documented, and reviewed - Preliminary System Test Plan defined, documented, reviewed, and approved |  | - All software units integrated and tested per SDP at the GBTS in-plant test site. Test results recorded. Results summarized and recorded in internal test report for inclusion in the GBTS in-plant test report. - All data definitions, databases, and files created, populated, and tested per SDP - All build/make and adaptation procedures integrated and tested - All peer reviews completed per the SDP - All software/hardware design, code and unit test, and integration problem reports resolved per priority thresholds defined in the SDP - Software unit source code, build/make procedures, data definitions, databases, files, and hardware equipment and deliverable data placed under program configuration control per the SDP - Authorization by IPT Leader |
| TIMS/OSS System Qualification Test |  |  |  |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Tested software/ hardware items (code, data definitions, databases, files, data, equipment and procedures) - System Test results and test report - Updates to System test plans, test case descriptions, and test procedures - System Test reviews | - Authorization by IPT Leader - Source code developed, unit tested, integrated, and under program configuration control - Data definitions, databases, files, and data developed, unit tested, integrated, and under program configuration control - Build/make procedures defined, tested, and under program configuration control - Required supporting test environment exists and is under configuration control - System Test Plan defined, documented, reviewed, and approved - System qualification test case descriptions and procedures defined, documented, reviewed, and approved |  | - Software/hardware tested per the System Qualification Plan - Data definitions, databases, files, and data tested per the System Qualification Plan - Build/make and adaptation procedures tested per the System Qualification Plan - Qualification test results recorded in a system qualification test report per the SDP - All peer reviews completed per the SDP - All software/hardware design, code, unit test, integration, and qualification test problem reports resolved per priority thresholds defined in the SDP and Program Configuration Control Board direction - Source code, build/make and adaptation procedures, data definitions, databases, files, equipment and deliverable data under program configuration control per the SDP - Authorization by IPT Leader |

| TIMS/OSS Software Support (Installation, Transition) |  |  |  |
| --- | --- | --- | --- |
| Process Products | - Process Entry Criteria | Process Exit Criteria |  |
| - Updates to software, databases, files, data, procedures, and supporting material - Updates to unit test cases, procedures, data, and results | - Authorization by IPT Leader Unit source code, data definitions, databases, files, deliverable data, and procedures placed under development configuration control per the SDP - Software/documentation problem report dispositioned for resolution |  | - All code, data definitions, databases, files, deliverable data, and procedure problem reports resolved (implemented, tested, and documentation updates completed) per the SDP-defined priority thresholds and/or Configuration Control Board disposition - All peer reviews completed per the SDP - All final deliverable code, data definitions, databases, files, deliverable data, procedures, and documentation reviewed, evaluated, and audited per the SDP - All deliverable software documentation completed, reviewed, and approved by the contracting agency per the contract and the SDP - All deliverable source code, data definitions, databases, files, deliverable data, procedures, and documentation placed under product configuration control per the contract, SDP, and CM Plan - All internal program/organizational software documentation completed, reviewed, and approved - Authorization by IPT Leader |

TABLE 4.1-2  TIMS/OSS Software Engineering Processes (Continued)

With the visual system and the remaining subsystems, the three end items consist of the following hardware/software subsystems:

- Host Computer:  Central real time system control and air vehicle simulation.

- Instructor Operator Station (IOS):  “Onboard” instructor to trainer interface and control.

- Digital Control Loading System (DCLS):  High speed control loading real time simulation, includes dynamic seat for the OFT and IFT.

- Input/Output (I/O) Controller: Digital/Analog and Analog/Digital interface between cockpit, IOS and host computer

- Avionics Drivers System: Graphics generation units  for cockpit LCD instrumentation.

- Remote Instructor Station (RIS):  “Off board” instructor interface to TIMS and IOS.

- Visual system (OFT and IFT only):  Special purpose digital system for storing, sorting, processing and displaying visual database data.

Due to the similarity of the components within the end items, the three end items are planned for development simultaneously.  Each of the subsystems listed above will progress through parallel “mini” integrations and testing cycles prior to complete system integration.  All subsystems except for the visual will be developed and provided by FSI-SSD.  The visual systems will be  provided by FSI-VSS.  End item integration will be carried out at FSI-SSD.  Figure 4.1.1-1 shows the planned software development phases for the FTDs.

The FTD IPT works with the JPATS community to refine system requirements and system design.  The FTD IPT design approach is to divide the FTD CSCI into groupings of modules and Computer Software Units (CSUs) according to the domain-specific approach commonly used in training simulator programs.  This approach takes advantage of a pre-existing software infrastructure (simulation module organization and structure, real-time schedulers, database architectures, I/O protocols), reusable software, and a standard division into software units which corresponds to real-world aircraft subsystems.  This division also reflects the division of FSI SSD’s software department into groups: Flight Dynamics, Engines, Aircraft Systems, Navigation/Visual, Autoflight, Computer Systems, Graphical Information Systems, etc.  The result of using this approach is to concentrate more of the effort toward detailed design, coding, integration and testing, since

architecture design is largely pre-defined and optimized for the simulation application domain, and the performance requirements are clearly defined by the usage and characteristics of the aircraft being simulated.

FIGURE 4.1.1-1  FTD Software Development Process.

The development process is initiated by a unified “single entity” front end system requirements and design effort led by the GBTS and FTD IPT System Engineering personnel.  FTD Software Engineering personnel participate in all of these efforts, but act as extensions of the System and Project Engineering offices.

System analysis is followed by a unified FTD Software Requirements Analysis effort led by the FTD Project Engineer and conducted by the Software Engineering personnel.

The FTD software design phase reflects the decomposition of the FTD system into its major building block components, with further decomposition into individual hardware/software component groupings taking place during initial implementation and test.  Software design efforts and component implementation and test efforts are conducted by the Software Engineering personnel acting under the guidance of the FTD Project Engineer.

Unit HW/SW Integration and Test will occur on a stand alone basis for each individual HW/SW component, which will then be qualified for integration into the ATD ensemble via the Component Qualification process phase.  Subsequent to component qualification, the individual components will be integrated into the ATD aggregate via the ATD Integration & Test phase.  During this phase, the components are individually tested in the integrated ATD environment.  These efforts are conducted by Software Engineering personnel working in conjunction with FTD hardware (Mechanical, Electrical and Controls departments) engineering, FTD Test, and FTD Product Assurance personnel.

ATD Integrated Test phase consists of full system in-plant development testing conducted by the FTD IPT and the GBTS Program Office in preparation for formal qualification (customer acceptance) testing.  Software engineering personnel support FTD IPT and GBTS Program Office Test & Evaluation personnel in the conduct of this phase.

System Qualification consists of the formal customer acceptance conducted on-site by RAC and the Government, as well as the System Level Formative Evaluation (SLFE) phase.  Software Engineering personnel support these efforts on an as needed basis.

Preparations for software support and software transition are conducted by simulation Software Engineering and software Configuration Management personnel in support of the Site Activation IPT, which has primary responsibility for transition to support during the Contractor Logistics Support program phase.

### 4.1.2  TIMS SOFTWARE DEVELOPMENT PROCESS

The TIMS IPT plans to build the TIMS software using a modified Rapid Development Methodology (RDM).  National Aeronautics and Space Administration’s (NASA) Jet Propulsion Lab pioneered the RDM model (ref. Rapid Development Methodology Applied to Software Intensive Projects, by Lynn G. Gref and William H. Spuck, Jet Propulsion Laboratory, Pasadena, California  for a detailed description of the original RDM model).  A Logicon/JPL team used RDM in a large Department of Defense (DOD) distributed information systems project.  The modified RDM methodology (not to be confused with rapid prototyping) is primarily an incremental development methodology with some features of the evolutionary spiral methodology life cycle.  The five tenets of the modified RDM model for this project are:

- Raytheon, the Government customer, FlightSafety and Logicon form a cohesive TIMS IPT.  The TIMS IPT agrees to build the system in a series of regular increments.  Each increment goes through its own life cycle (planning, requirements analysis and definition, design, implementation, integration and test).  Each increment is self containing.  Each subsequent increment incorporates and builds on the previous increment.  The NASA RDM model has operational deployment of each increment.  TIMS has modified the model to eliminate fielding each increment to operational sites to control costs.  However, each increment (code, documentation, support tools, etc.) is ready for final system integration and deployment even though it is not officially deployed.  The incremental build approach provides a stand-alone product at the end of each increment.  The increment approach reduces TIMS software development risk by providing FlightSafety, Raytheon, and Government representatives with a yardstick to use in evaluating progress.  This RDM approach includes full configuration management, documentation, and testing for each increment and prevents these items from becoming “late add-ons”.

- The modified RDM life-cycle model incorporates concepts from the evolutionary spiral model by encouraging a feedback mechanism (ref. SPC-91076-MC Version 03.00.05 December 1993, Evolutionary Spiral Process Model Guidebook for details).  The TIMS IPT actively solicits and obtains feedback from users, Subject Matter Experts (SMEs), and other interested parties in the undergraduate flight training (UFT)community for each increment.  The TIMS IPT then incorporates the feedback into the requirements analysis phase for the next increment.  Thus, RDM allows the flexibility needed to incorporate new technology or the inevitable change to requirements.

- The TIMS IPT involves the JPATS community throughout the software development process to build consensus.  The TIMS IPT utilizes the Integrated Product Development (IPD) process to hold technical interchange meetings.  The TIMS IPT also uses prototyping, display modeling, and demonstrations to involve interested parties.  During initial analysis and design, the team (with input from the JPATS community) prioritizes and assigns complexity/risk values to each requirement.  Then the TIMS IPT (with input from interested parties) maps the requirements to the planned incremental builds.  This approach builds consensus, synchronizes expectations and allows Raytheon and the Government to measure progress and assess the impact of changes.  As requirements are added or changed, the TIMS IPT again involves all interested parties to re-map the requirements to the remaining increments using the priority, complexity, and risk measurements.

- The TIMS IPT implements the system with progressive formality so as to achieve everything needed to sustain the final delivery.  The TIMS IPT integrates each increment with available hardware and other systems as early as possible.  Each increment has full Configuration Management (CM) problem tracking and metrics collection.  Metrics are designed to give the appropriate management information and become increasingly precise indicators of progress.

- In addition to the increment builds, the TIMS IPT does frequent, regular integration builds throughout the integration and test phases of the development.  This approach provides early visibility as to the progress and reliability of the product; the approach is explained in further detail in Section 5.8, Unit Integration and Testing

The TIMS IPT plans to do the TIMS software development using three incremental builds to facilitate early demonstration of capabilities and early integration and test.  During the initial pass through the mini-life cycle, the TIMS IPT, working with the users and other members of the TIMS IPT, identifies the system requirements, system design, and software requirements.  The TIMS IPT, with inputs from UFT participants from AETC and CNATRA, prioritizes, categorizes and assigns the software requirements to three increments at the end of the software requirements analysis phase.  The software requirements are baselined and used to propose an overall software design.  The entire focus during the first phases is on consensus building and alignment of expectations for all parties.  The IPT concept greatly facilitates this process, since its very structure is designed to pull the various elements needed for successful software development together.

The exact requirements for the three increments are defined by the system and software requirements analysis process.  However, a preliminary example of a possible increment mapping result is as follows:

- The first increment provides a computerized grease board for the scheduling inputs and includes the major parts of an electronic gradebook.  The scheduling function is entirely manual in this increment.

- The second increment provides the following scheduling enhancements:  operator input error checking, prompts and suggestions for inputs, and an evaluation of the quality of the schedule.  This increment also provides some report functions and interfaces to external systems.

- The third increment provides the automatic schedule generation function, all parts of the electronic gradebook, all report functions, configuration management and update features, and the rest of the required elements.

Figure 4.1.2-1 provides a high-level representation of the planning and activities for the suggested three increments.  Table 4.1.2-1 summarizes the TIMS software development in terms of the phases, tasks for each increment, major deliverables, and major reviews and audits identified in the GBTS MIPS.  Section 6 of the SDP describes details on the TIMS release schedule and milestones.

During the initial system requirements analysis phase, the TIMS IPT plans to do site visits and extensive prototyping, including display models and demonstrations of COTS tools to involve all interested participants, obtain feedback, and derive complete and accurate requirements.  TIMS requirements and prototype analysis data gathering is performed at San Antonio, TX and at a subset of JPATS operational locations.  The proof-of-

concept prototypes help define the preliminary design concepts for critical areas.  At the end of the system requirements analysis and system design phases, the TIMS IPT updates the System Specification and TIMS Prime Item Development Specification (PUSD).

## 4.2  GENERAL PLANS FOR SOFTWARE DEVELOPMENT

The majority of the new 3GL software for the JPATS GBTS will be developed utilizing the Ada 95 (FTDs and scheduling engine modifications in TIMS) and C++ (FTDs and rest of TIMS) programming languages.  The utilization of Ada and C++  provides a flexibility not found within other languages such as FORTRAN.  An Ada development approach encourages software developers to work and think in terms of the application domain through most of the software life cycle.  It is only when the inherent concepts of the application are identified, organized, and understood that the details of data structures and functions can be addressed effectively.  The greater emphasis on the essential properties of an object/package forces engineers to think more carefully and more deeply about what a package is and does, with the result that the system is usually cleaner, more general, and more robust than it would be if the emphasis were only on the use of the data and operations.  C++ is becoming the de facto industry standard for Windows programming.

### 4.2.1  SOFTWARE DEVELOPMENT METHODS

Each IPT documents requirements with the Computer Aided Software Engineering (CASE) tool Dynamic Object Orientated Requirements System (DOORS), which provides a two-way traceability between the software requirements, the system-level requirements, the design, the code components, and the test cases.  Traceability requirements are documented in the System Engineering Management Plan (SEMP).

Software QA is controlled at the lowest level consistent with the baseline status of applicable products.  Each IPT will employ procedures consistent with the normal operating practices of its constituent company.  Those procedures are documented herein and/or in separate plans.  For products at less than system level (i.e., less than Functional, Allocated or Product) baseline status, the GBTS PMO will monitor the IPTs for compliance with QA procedures and is afforded the opportunity to participate in IPT internal QA reviews.  The GBTS PMO will provide QA review and approval for all products which are at or being promoted to system level baseline status.

Software CM is controlled at the lowest level consistent with the baseline status of applicable products.  Each IPT will employ procedures consistent with the normal operating practices of its constituent company.  However, those procedures  will support the use of the CM tool ClearCase by each IPT as a GBTS-wide common CM tool for controlling and statusing software products.  The specific procedures to be used by the GBTS PMO and each IPT will be documented herein and/or in separate plans.  For products at less than

FIGURE 4.1.2-1  TIMS Software Development Process Overview

| TIMS System & Software Development Cycle |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase | Increment 1 | Increment 2 | Increment 3 | Sustainment |
| System Requirements Analysis | - Functional baseline established by SS and PUSD submitted with proposal. - Analyze system rqmts. Updated SS and PUSD. Develop preliminary TIMS IRS. - Site visits to document data needed for reports and displays, analysis of current headquarters, groups, wings, squadrons, flight, and ancillary operations. - Prototyping & demos to clarify understanding of reqs. - SRR -- SS & PUSD reviewed and controlled | - Analyze system rqmts changes due to Software change Requests (SCRs). Update SS and PUSD as required. | - Analyze system rqmts changes due to SCRs. Update SS and PUSD as required. | - Analyze system rqmts changes due to SCRs. Update SS and PUSD as required. |
| System Design | - Eval. arch. alternatives and document TIMS system design in an SSDD. - System Reqs mapped to hardware and software - Prototyping & demos to clarify reqs & design issues - SDR -- SSDD reviewed and controlled | - Analyze system design changes due to SCRs. Update TIMS SSDD as required. | - Analyze system design changes due to SCRs. Update TIMS SSDD as required. | - Analyze system design changes due to SCRs. Update TIMS SSDD as required. |
| SW Req. Analysis | - Prototyping and demos to clarify and derive software reqs. - Derive and define SW req. for all of TIMS - Prioritize and categorize reqs; map reqs. to each increment - SSR -- SRS, IRS, & STP reviewed & controlled. - TIMS Allocated Baseline established with authenticated SS, PUSD, SRS, and IRS. | - Analyze & update SW reqs due to SCRs. - Re-prioritizes and map reqs. to remaining increments. | - Analyze & update SW reqs due to SCRs. - Re-prioritizes and map reqs. to remaining increment. | - Analyze & update SW reqs due to SCRs. |
| Preliminary architectural design | - Develop prel. design for all of TIMS - Prototype/ model design - Define functional interfaces and constraints - PDR & review prel. SDD, IDD. | - Analyze design changes due to SCRs. - Update design documents as req. | - Analyze design changes due to SCRs. - Update design documents as req. | - Analyze design changes due to SCRs. - Update design documents as req. |

TABLE 4.1.2-1  TIMS Software Development Activities by Increment & Phase

| TIMS System & Software Development Cycle |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase | Increment 1 | Increment 2 | Increment 3 | Sustainment |
| Detailed design | - Develop detailed design for all of TIMS - Prototype design as req. - CDR & review SDD, IDD and STD - SDD, IDD, controlled after CDR | - Analyze design changes due to SCRs. - Update design documents as req. | - Analyze design changes due to SCRs. - Update design documents as req. | - Analyze design changes due to SCRs. - Update design documents as req. |
| Code and unit test | - Generate code for increment - Prepare & conduct unit testing for increment - Conduct peer reviews - Initialize SDFs - Conduct prototyping as req. | - Generate code for increment - Prepare & conduct unit testing for increment - Conduct peer reviews - Update SDFs - Conduct prototyping as req. - Modify code and retest due to SCRs/PRs for previous increment | - Generate code for increment - Prepare & conduct unit testing for increment - Conduct peer reviews - Update SDFs - Conduct prototyping as req. - Modify code and retest due to SCRs/PRs for previous increment | - Modify code and retest due to SCRs/PRs |
| Unit integ. & test | - Frequent builds (at least bi-weekly) as units become available and CM controlled. Concurrent with unit coding and testing. - Prep. SPS, SUM documentation for current increment - Detailed increment formal test procedures developed, reviewed and placed under control - Build testing uses a subset of current increment’s CSCI formal test procedures and other integration tests - Integration test results collected and documented in integration test folders - PRs/DRs entered into corrective action system - Interim internal integration test report | - Frequent builds (at least bi-weekly) as units become available and CM controlled. - Prep. SPS, SUM docs. for current increment - Detailed increment formal test procedures developed, reviewed and placed under control - Informal regression testing for ECR/PR changes - Build testing uses a subset of current increment’s CSCI formal test procedures and other integration tests - Integration test results collected and documented in integration test folders - PRs/DRs entered into corrective action system - Interim internal integration test report | - Frequent builds (at least bi-weekly) as units become available and CM controlled. - Prep. SPS, SUM for current increment - Detailed increment formal test procedures developed, reviewed and placed under control. - Informal regression testing for ECR/PR changes - Build testing uses a subset of current increment’s CSCI formal test procedures and other integration tests - Integration test results collected and documented in integration test folders - PRs/DRs entered into corrective action system - Interim internal integration test report | - Updated code integrated into CSCI. - Regression tests identified and performed at support site. |

TABLE 4.1.2-1  TIMS Software Development Activities by Increment & Phase (Continued)

| TIMS System & Software Development Cycle |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase | Increment 1 | Increment 2 | Increment 3 | Sustainment |
| TIMS CSCI testing (increments) | - Internal IPT test readiness meeting; review of increment internal integration and test report. - Increment tested using current increment’s CSCI formal test procedures. - SQA certifies and maintains test results - PRs/DRs entered into corrective action system - Raytheon, FlightSafety, and Government invited, but not required to witnesses tests. - Interim internal test report | - Internal IPT test readiness meeting - Increment tested using current increment’s CSCI formal test procedures and identified regression tests from previous increment’s formal test procedures - SQA certifies and maintains test results - PRs/DRs entered into corrective action system - Raytheon, FlightSafety, and Government invited, but not required to witnesses tests. - Interim internal test report | - Internal IPT test readiness meeting - Increment tested using current increment’s CSCI formal test procedures and identified regression tests from previous increment’s formal test procedures. - SQA certifies and maintains test results - PRs/DRs entered into corrective action system - Raytheon, FlightSafety, and Government invited, but not required to witnesses tests. - Interim internal test report |  |
| TIMS CSCI formal test (final completed TIMS version) |  |  | - TIMS CSCI TRR - Formal TIMS CSCI tests conducted at TIMS in-plant development facility using final complete set of CSCI formal test procedures documented in STD. - SQA certifies test results - PRs/DRs entered into corrective action system - Raytheon, FlightSafety, and/or Government representatives required to witnesses tests. - TIMS CSCI STR generated - TIMS FCA conducted | - Regression tests performed for customer at support site facility |
| TIMS CSCI/HWCI integ. & test |  |  | - TIMS tested using subset of formal TIMS CSCI test procedures and TIMS system test procedures and identified regression tests - Integration test results documented in test folders - PRs/DRs entered into corrective action system - Interim internal test report - QA certifies test results |  |

TABLE 4.1.2-1  TIMS Software Development Activities by Increment & Phase (Continued)

| TIMS System & Software Development Cycle |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase | Increment 1 | Increment 2 | Increment 3 | Sustainment |
| TIMS System Test |  |  | - Formal TRR - GBTS (including TIMS) fielded at Randolph AFB. GBTS tested using a subset of formal test procedures & operational hardware configuration equipment. - QA certifies test results - STR generated | - After completion of Randolph AFB installation and testing, GBTS incrementally installed and acceptance tested at all other sites. - For maintenance updates, TIMS updated and tested in MUSS environment. Testing at MUSS performed by support staff. - After MUSS testing, TIMS fielded and tested at operational sites. Testing at operational sites performed by Government users as required. |

TABLE 4.1.2-1  TIMS Software Development Activities by Increment & Phase (Continued)

system level (i.e., less than Functional, Allocated or Product) baseline status, the GBTS configuration manager

will monitor the IPTs for compliance with CM procedures.  The GBTS configuration manager will provide CM review and approval for all products which are at or being promoted to system level baseline status.  TABLE 4.2.1-1  TIMS Software Development Process Documents lists the organizational documents which define the Logicon software development processes, methods and procedures.  Appendix C contains a compliance traceability matrix that demonstrates complete coverage of International Standards Organization ISO-9001 requirements.  The software development process, procedures, and tools are further defined in the detailed context of activities described in Sections 5.1 through 5.19.

| Logicon Engineering Instruction Binder (LEIB) | Defines the organizational software development processes to help ensure the efficient and cost-effective production of high quality software. The binder contains policies, practices, directives, procedures, standards, guidelines, and software engineering forms. At the beginning of the project, the TIMS IPT creates a tailored TIMS Project Instruction Binder (PIB) from this organizational document to reflect the unique contract requirements and the Software Engineering Environment (SEE). |
| --- | --- |
| Quality Assurance Program, Volumes 1-2 LSIS890297 | Defines policies, directives, and procedures for software development and QA. Covers planning corrective action system, software development process and evaluations, software engineering process and product evaluations, software CM evaluations, management evaluations, and data management (DM) evaluations. |
| Configuration Management Program Volumes 1-2 LSIS900213 | Defines policies, directives, procedures for CM. Covers software configuration management planning, identification, configuration control, status accounting, and audits. |

TABLE 4.2.1-1  TIMS Software Development Process Documents

### 4.2.2  STANDARDS FOR SOFTWARE PRODUCTS

The IPT software developers comply with the following standards for the user interfaces:

- The Windows Interface: An Application Design Guide, Microsoft Press, 1992 - provides guidelines for Win 3.1 interfaces, including applications targeted for older versions of NT.

- Programming the Windows 95 User Interface, Microsoft Press, 1995 - provides information on the Win 95 interface shell for applications targeted for Windows 95 and the newer versions of NT.

#### 4.2.2.1  FTD Standards for Software Products

The FTD IPT uses FlightSafety’s Software Engineering Procedures and Practices Manual (SEPP) for software development efforts.  This standard is based on the Ada Quality & Style: Guidelines for Professional Programmers and guidelines developed by the Software Productivity Consortium.  SEPP-1000 procedure 4.03 provides the Ada design and coding standards to be used for the FTD CSCI.  Organization of Ada software packages, tasks, procedures, and source files will be performed in accordance with the software architecture description contained in procedure 4.03.  The FTD development  utilizes established group and package designation focusing their design efforts on the export requirements for each package.  Graphical representations of Ada software architecture use  the modified Booch symbology.

#### 4.2.2.2  TIMS Standards for Software Products

The IPT teams analyze software requirements using the Object Oriented Modeling Technique (OMT) developed by James Rumbaugh.  The TIMS IPT uses LEIB Software Engineering Standard for Ada Programming (SES-004) for all new Ada development.  This standard is based on the guidelines developed by

the Software Productivity Consortium.  Reuse code is treated as a “black box” with any interfaces following the new code guidelines.

### 4.2.3  REUSABLE SOFTWARE PRODUCTS

Throughout the program, software engineers and IPT members will perform analysis and evaluation of existing Government Furnished Equipment (GFE) software, COTS products, and other software to determine the reusability.  Trade studies will be used to determine acceptable reuse evaluating the following criteria:

- The ability of the reused software/design/procedure to meet requirements

- The ability to be cost-effective over the life of the system

- The ability to provide required safety, security and privacy

- The reliability/maturity of the reusable product

- The testability of the reusable product

- The interoperability with other systems and system external elements

- Fielding issues such as restrictions on distributions, licensing and fees

- Maintainability issues, including likelihood of changes, feasibility of change, availability of documentation and quality of documentation, impact on system if current version is not supported, acquirer's data rights and warranties.

- Technical, cost, and schedule risks and tradeoffs in using the software product.

The GBTS PMO subscribes to the computer suppliers update program.  Tradeoff studies will assesses and make recommendations as to when revisions to hardware and software should be incorporated.

The Government has unlimited rights to all newly developed deliverable software developed under GBTS JPATS program.  However, all COTS items are furnished to the Government by vendors with Restricted Rights to both the documentation and software per DFARS 152.227-7013, with the justification in each case being that the software and documentation items are proprietary commercial products developed at considerable vendor expense.  The FlightSafety team will procure and deliver to the Government all COTS software licenses.

#### 4.2.3.1  Incorporating Reusable Software Products

A list of COTS third party software to be used in the FTDs is provided in Table 4.2.3.1-1.  A list of reused FSI-SSD simulation products to be reused in the FTDs is provided in Table 4.2.3.1-2.

A preliminary list of COTS tools proposed for TIMS use and deployment is shown in Table 4.2.3.1-3.

#### 4.2.3.2  Developing Reusable Software Products

During the system requirements phase, the system engineers and software engineers in each  IPT coordinate with the PST System and Software Engineering  Process Managers to identify and allocate development of reusable software products which can be used by all the GBTS IPTs.

#### 4.2.3.3  Feedback From Reuse of FTD Software in Follow-on Programs

Software products developed for use on the JPATS FTDs will be reused by FlightSafety’s manufacturing division in follow-on programs.  The FTD IPT establishes a program to monitor changes to those products and evaluate the incorporation of those changes into JPATS FTDs.

When JPATS compatible software is employed on a follow on project, the software group leader notifies the

FSI-SSD configuration manager, who maintains a log of software versions used on various projects.

Compatible software is defined as software serving the same executive function or simulating the same aircraft component and running under the same host/operating system platform.

| COTS/Reuse Item | Vendor/Function |
| --- | --- |
| Windows/NT | Microsoft, Inc. / Operating system for underlying platform |
| RTX 4.1 | VenturCom - MicroSoft / Real Time Extension for Windows NT |
| Object Ada Enterprise NT | Aionix / Ada95 Compiler for Windows NT |
| Ada for Intel Windows NT | ActivAda / Runtime |
| ClearCase/PureDDTS | PureAtria / CM Tools |
| Microsoft Visual C++ | Microsoft / C++ Compiler and Text Editor |
| Microsoft Word for Windows | Microsoft / Word Processor |
| Microsoft NT Toolkit | Microsoft / IOS GUI builder |
| Rational Rose | Rational, Inc./ CASE Design Tool |
| AVIDS | Evans & Sutherland, Inc. / Instrument graphics development tool for LCD based panel displays |
| Model Builder | ASTI / Aural Cues Syst S/W Toolkit |

TABLE 4.2.3.1-1  FTD Deployment COTS and Reuse Products

| Functional Software Group | Fsi-Ssd Projects | Fsi-Ssd Software | Reuse Product D=Design, C=Code |
| --- | --- | --- | --- |
| D61 FLT-Init | Beech 1900, Cessna Caravan, de Havilland Dash 8, and Saab 340 | Aero initialization | D |
| D61 FLT-Auto T A | Beech 1900, Cessna Caravan, de Havilland Dash 8, and Saab 340 | Autotest initial conditions and drivers. | D |
| D61 FLT-Auto T B | Beech 1900, Cessna Caravan, de Havilland Dash 8, and Saab 340 | Autotest control, recording and plotting. | D |
| D61 FLT-Aero | Beech 1900, Cessna Caravan, de Havilland Dash 8, and Saab 340 | Atmospheric properties, wind, windshear, aerodynamics, mass properties, flight controls, ground handling and equations of motion. | D |
| D61 FLT-Instruments |  | AOA, accelerometer, altimeter, airspeed, pitot-static, and ADC. | D |
| D62 Engines | Beech 1900 (PT6A - 67B) | E-200 Inlet Parameters, E-210 Start & ignition, E-217 Power & Speed Ctrl, E-227 Engine Performance, E-230 Fuel Flow, E-235 ITT, E-245 Prop Speed & Pitch, E-252 Prop Performance, E-270 Bleed & Oil Temp/Pres, E-290 Instrument Driver. | D |

TABLE 4.2.3.1-2  FTD Simulation Applications Reuse Products and Sources

| Functional Software Group | Fsi-Ssd Projects | Fsi-Ssd Software | Reuse Product D=Design, C=Code |
| --- | --- | --- | --- |
| D63 Aircraft Systems | Caravan | S-400 Electrical, S-410 Fuel, S-420 Hydraulics, S-430 SEC Flt Controls, S-440 Landing Gear, S-450 Pneumatics, S-460 Pressurization, S-470 Anti-Ice, S-480 Fire Protection, S-483 Lighting, S-484 Master Warning Sys, S-490 Instrument Driver. | D |
| D64 Instructor Station | LearJet 31, MAS 777, C-17 | LJ and C-17 used for SLoC GUI screen count based on B777 | D, C |
| D65 Navigation | Cessna Caravan, Bell 212/412, and OH-58D. | Avionics CSC and constituent CSUs. Navigation CSC and constituent CSUs. | D, C |
| D65 Nav DB Acc | Cessna Caravan, Beach 1900 | Nav_Main related software. | D |
| D65 Nav DB PPI | Cessna Caravan, Beech 1900 | Nav_Main related software. | D |
| D65 Nav DB PPO | Cessna Caravan, Beech 1900 | Nav_Main related software. | D |
| D65 Nav DB CPI | Cessna Caravan, Beech 1900 | Nav_Main related software. | D |
| D65 Nav DB CPP | Cessna Caravan, Beech 1900 | Nav_Main related software. | D |
| D65 Nav DB CPO | Cessna Caravan, Beech 1900 | Nav_Main related software. | D |
| D65 Visual IG IF | OH-58D | IGIO CSCs | D, C |
| D65 Visual RT IF | OH-58D | VISUAL IO CSCs | D, C |
| D68 CSG-Math UTL | OH-58D | PRIM (primitives) CSCs | D, C |
| D68 CSG-IO SW | OH-58D | PRIM (primitives) CSCs | D, C |
| D68 CSG-Schdlr | OH-58D | SCHED (scheduler) CSC | D, C |
| D68 CSG-Task Utl | OH-58D | PRIM (primitives) CSCs | D, C |
| D68 CSG-Sym Tbl | OH-58D | PRIM (primitives) CSCs | D, C |
| D68 CSG-Timing | OH-58D | PRIM (primitives) CSCs | D, C |
| D68 CSG-Rcd Pba | LearJet 31 | Record-playback software. | D |

TABLE 4.2.3.1-2  FTD Simulation Applications Reuse Products and Sources (Continued)

| Functional Software Group | Fsi-Ssd Projects | Fsi-Ssd Software | Reuse Product D=Design, C=Code |
| --- | --- | --- | --- |
| D68 CSG-Rcd Pbb | LearJet31 | Record-playback software. | D |
| D68 CSG-Rcd Pbc | LearJet31 | Record-playback software. | D |
| D68 CSG-IO Dlag | OH-58D | PRIM (primitives) CSCs. | D, C |
| D68 CSG-Simmon | OH-58D | SIMMON CSC | D, C |
| D68 CSG-IOS Intf | OH-58D | XIOS CSCs | D, C |
| D68 CSG-RT Dbga | KC135 & OH-58D | Real-Time debugger CSC | D, C |
| D68 CSG-RT Dbgb | KC135 & OH-58D | Real-Time debugger CSC | D, C |
| D68 CSG-RT Dbgc | KC135 & OH-58D | Real-Time debugger CSC | D, C |
| D68 I/O Controller Exec | MAS 777 | I/O Controller Executive | D |
| D68 ECLS Exec | MAS 777 | ECLS Executive | D |
| D68 CSG-CM (interface to ClearCase) | OH-58D | Ada Configuration Mgmnt Environment (ACME) software | D, C |
| D-69-Airdata | LearJet31 | A-500 Airdata | D |

TABLE 4.2.3.1-2  FTD Simulation Applications Reuse Products and Sources (Continued)

| COTS Tool | Product(s) | Vendor |
| --- | --- | --- |
| CASE, Code Generation | PowerBuilder Enterprise | Sybase |
| Compiler(s) | Thompson Ada Visual C++ | Thompson |
| Network Operating System | Windows NT | Microsoft |
| RDBMS | Microsoft SQL Server | Microsoft |
| Graphics User Interface Builder | PowerBuilder Enterprise | Sybase |
| Configuration Management Tool | ClearCase DDTS DocExpress Word Visio PowerPoint | PureAtria PureAtria ATA Microsoft Shapeware Microsoft |
| System/Network Modeling | Paradigm Plus ERWin COMNET | Platinum Technologies Logic Works CACI |
| Reports Generation | Powersoft InfoMaker | Sybase |
| Requirements Management | Dynamic Object Oriented Requirements System (DOORS) | QSS |
| GUI Testing Tool | SQA Suite 5 | SQA |
| Program Management | Open Plan Professional MP*M MS Project MS Office Pro | Welcom Technologies MicroFrame Microsoft Microsoft |
| Core scheduling engine | ROSE | COSMIC |
| Anti-Virus | Dr. Solomon’s Anti-Virus Toolkit for Windows NT | S&S Software International |
| Email | MS Exchange | Microsoft, Inc. |

TABLE 4.2.3.1-3  TIMS Deployment Reuse Products

Prior to JPATS Product Baseline - The JPATS IPT’s responsible software CM person will maintain periodic contact with the appropriate projects as noted by the software reuse log.  JPATS IPT CM obtains change records of problems detected and modifications or improvements implemented in the reused products.  JPATS CM passes this information to the appropriate JPATS simulation engineers, who will evaluate the changes for correctness, applicability and recommend rejection or incorporation IAW the baseline control level in effect at the time of evaluation.

After Product Baseline Established - After the JPATS FTD product baseline control passes to the MUSS, The JPATS ATDSS group will participate in FlightSafety’s Maintainability and Corrective Action Report (MCAR) program, wherein fielded equipment problems and change requests are reported through FlightSafety’s Integrated Logistics Support department to the simulation engineering departments for corrective or other actions.

### 4.2.4  HANDLING OF CRITICAL REQUIREMENTS

Critical requirements will be tracked via technical performance indicators and addressed during all major reviews.  Those items with a critical nature will be monitored by Quality Assurance to insure appropriate safe guards and precautions have been established and are being maintained by program management.

#### 4.2.4.1  Safety Assurance

System Safety Engineering is addressed in the SEMP, Section 4.4.

#### 4.2.4.2  Security Assurance (SOW 7010.4.1)

Information which is designated as secure during the CDR will have password protection and limited accessibility.  Facility access will be controlled during the development phases to insure test data security.  Any additional security measures will be outlined within the appropriate development specifications PUSD.  The GBTS development complies with Government security procedures for all areas and safeguards Government equipment and property.

#### 4.2.4.3  Privacy Assurance

Systems data which contains information covered under the privacy statutes will be safeguarded against unauthorized access.  Specific data requirements are address in the appropriate PUSD.

#### 4.2.4.4  Assurance of Other Critical Requirements

Non-applicable.

### 4.2.5  COMPUTER HARDWARE RESOURCE UTILIZATION

Critical resources include processor execution speed, interface speeds, processor main memory, size of the recording medium for recording without manual intervention, the total recording capacity of the system, any documented System Specification or PUSD critical resource items, and any other computer resource that is expected to exceed more than 50 percent utilization.  The project follows Software Engineering Procedure for Estimating Critical Computer Resources LEIB SEP-10 (OSS IPT) and SEPP1000 procedure 6.02 (FTD IPT).  The processing performance measurements for the program will be defined during the system and software requirements analysis phase and documented within the PUSD.

Budgets for capacity, timing, and sizing will be allocated across the system, according to the normal

processing architecture.  A specified reserve will be established when making initial estimates, based on the

fidelity of the estimates.  Processing performance measurements will be obtained by using the following techniques:

- Defining baseline stress scenario

- Defining hardware and software configuration and using existing performance characteristics documented for this configuration

- Developing bottom up estimate by analyzing each component

- Developing estimate using an existing baseline and estimating changes

- Developing an estimate by comparison to a similar system

- Developing benchmark prototypes, models and simulations to support estimates.

Thresholds will be established for each critical resource.  Exceeding these thresholds will trigger corrective actions which may include performing additional trade-studies, identifying additional resources, reallocating budgets within the system, or allocating a portion of the reserve.  Performance metrics will be regularly monitored, measured, and documented.  Performance metrics will also be discussed at all major reviews.  Section B.2, Appendix B contains preliminary estimates of TIMS resources utilization.

For the FTDs, spare-measurement programs  developed on FSI SSD’s commercial programs will be used to monitor the processing time and memory usage.  “Spare time” will be defined as the percentage of processor time in a frame not used by the simulation program.  Spare time for a simulation frame will be measured by measuring the amount of processor time used by each module in a frame.  “Available memory” will be defined as the amount of free memory on the host computer just prior to starting the simulation software.  “Free memory” is the amount of unused local and global random-access memory on the host computer at a given point in time.  Swap space on a hard disk, used for memory management, is not counted as memory for the purposes of this calculation.  Spare memory will be calculated by dividing free memory while the simulation host CSCI is running by free memory when the simulation host CSCI is not running (thus excluding operating system overhead from the calculation).

### 4.2.6  RECORDING RATIONALE

A list of key decisions for which rationale must be recorded will be developed by the software group leaders prior to System Requirements Review (SRR).  The list of key decisions may include the following:

- Identification of software hazards and strategies for mitigating hazards.

- Identification of risks and risk-abatement strategies.

- Selection of software for reuse.

- Deviation from design or coding standards.

- Deviation from this Software Development Plan.

Rationale for key decisions affecting more than one software unit will be recorded in the form of electronic mail messages sent to the project account.  Electronic mail messages will be compliant with Internet Standard 11, also known as Request for Comments (RFC) 822.  Electronic mail sent to this account will be archived; the archive will be provided to the support organization.  The use of RFC 822-compliant electronic mail will provide the support organization with a collection of data which can easily be searched using standard tools.  Rationale data which cannot be represented as simple ASCII text (such as drawings, spreadsheets, word processing documents) may be provided in the most appropriate file format and sent as a binary attachment to an electronic mail message; the main body of such a message will contain an abstract of the attachment’s contents and instructions for accessing the data.  Electronic mail messages containing attachments will

conform to RFC 1521 and RFC 1522, which define the Multipurpose Internet Mail Extensions (MIME).  Rationale for key decisions affecting only one software unit will be recorded in the header section of the relevant source file.

### 4.2.7  ACCESS FOR ACQUIRER REVIEW. (SOW 5020.2.1.1)

Raytheon and the Government are integral members of the IPTs which will allow Raytheon first hand knowledge of the programming status and early review of the product.  The FlightSafety team will provide electronic access to software products under development by sending /receiving data to/from the Raytheon JPATS Management Information System (MIS) and by using a Secure Socket Layer (SSL) capable Internet Web Browser (Netscape Enterprise).  All new documents are generated using the Microsoft MS Office software suite.  All engineering drawing images will be in two-dimensional format compatible with viewing via the Internet.  This process will permit ongoing review of requirements, design, coding, and test information throughout the software development period.  Access to FSI SSD facilities will be coordinated through the FTD IPT Leader.  Access to the Logicon TIMS facilities will be coordinated through the TIMS IPT Leader.

# 5.0  DETAILED SOFTWARE DEVELOPMENT ACTIVITIES

## 5.1  PROJECT PLANNING AND OVERSIGHT (SOW 5020.1.9, 5020.1.1.7)

Software project planning begins during the pre-contractual phases and continues throughout the life of the resulting software project.  Pre-contractual planning includes overall contract planning, CSCI scheduling, quality assurance analysis and review , configuration management verification  and manpower analysis.  The FlightSafety Team develops, implements and maintains the following integrated plans:

- System Engineering Management Plan

- Courseware Development Plan

- Software Development Plan

- Integrated Master Plan

- Master Integrated Program Schedule (MIPS)

- Integrated Support Plan

- Software Quality Program Plan

- Configuration Management Plan

The System Engineering  Management Plan outlines both hardware and software management practices and procedures.  Detailed  PUSD are written and form the basis for flow down to software requirements, scheduling, and manpower.  Figure 5.1-1 gives an overview of how the software activities map to the overall program.

Technical progress is tracked against IMP criteria, technical performance indicators, and approved schedules.  Overall progress is captured via our Earned Value Management System.  Monthly status reports will be given to the GBTS program manager and reported to Raytheon  as part of monthly program progress/status reports (SDRL G034).  The GBTS software process manager also will monitor software development activities, working through the IPTs, and monitor software design maturity at the system level.  Software development status and indicators of technical performance  will  be reviewed at quarterly program management reviews (SOW  5020.1.1.7).

### 5.1.1  Software Development Planning. (SOW 5020.1.3)

Software development plan activities are included in the JPATS GBTS Integrated Management Plan (IMP).  The IMP is the controlling document for all program events and event accomplishment criteria.  This SDP is a comprehensive plan that documents the JPATS GBTS software development activities and schedule.  The SDP is updated as the contract or software commitments are refined or changed.  The SDP is maintained under project configuration control and is the baseline document for measuring software compliance.  The SDP is prepared and maintained in accordance with FlightSafety's Quality Assurance Manual QAM-1000 and Logicon's Quality Assurance Program LSIS890297.  Modifications to this plan may result from overall program changes or as a result of a standard Discrepancy Report form generated by any member of the program team who notes a discrepancy.  The program manager will determine whether the change is to be implemented, in consultation with the software process manager, IPT Leaders, and with the approval of the Raytheon JPATS program office.

FIGURE 5.1-1  GBTS Timeline

The FlightSafety GBTS Program Manager is responsible for measuring completion of the planning milestones, work completed and measuring the resources expended against the planned resources.  He is supported by each of the IPT leaders and the software process manager.  He will be responsible for reviewing software project planning activities on a monthly basis, or more often if events require it.

QA reviews the contract and coordinates quality program planning,  The review ensures that all contractual requirements for software, including software quality are properly flowed down to the appropriate plans.  These reviews also enable QA to plan for the necessary resources and skills required to support the contract.  This planning ensures adequate budgets, personnel and controls for software quality assurance activities.

CM reviews the contract and coordinates configuration management planning.  These reviews enable planning for necessary resources and skills required to support the contract.  This planning ensures adequate budgets, personnel, and controls for configuration management activities.

### 5.1.2  CSCI test planning (SOW 5020.1.3.1, 5030.5.1)

IPTs will plan and conduct a comprehensive software test program, which is compatible with the program-level Integrated Test Plan (ITP), for newly developed, reused, and modified software.  CSCI test  planning includes the planning for informal development tests, formal qualification tests, and acceptance test (see Section 5.1.3, Figure 5.1.3-1).  Raytheon and the Government will be given access to all testing.  An individual Software Test Plan (STP) will be produced for the FTD and TIMS development efforts.  These test plans will become part of the overall GBTS ITP.  Other components will be tested as part of the overall Development Test Procedures (DTPs) for the GBTS.  Software Test Descriptions (STDs) and Software Test Reports (STRs) will be developed for the TIMS CSCI.

#### 5.1.2.1 FTD Test Planning (SOW 5030.2-2.2.2)

Development Test Procedures (DTPs) will be developed for use during in-plant first article testing.  The DTPs will encompass all demonstration and test items required in PUSD Section 4.  Raytheon’s approval will be received on all DTPs prior to testing and Raytheon will be invited to participate in the testing activities.  QA or test and evaluation personnel plan and conduct in-plant first article testing utilizing the DTPs.  The test plan specifies the criteria for beginning and completion.  All discrepancies and deficiencies are documented within the test folders.  An activity log is maintained from verification testing on for each configuration item (CI) which contains equipment adjustments, modifications, failures, removals, replacements, and scheduled and unscheduled maintenance.

As part of the FTD test planning activities, the FTD IPT will plan for and conduct a Test Readiness Review (TRR) before each of the above mentioned test activities.  The criteria for successful completion of the TRR for in-plant Raytheon/Government test will be defined in the system test plan and in the IMP.  At least 28 calendar days prior to each Raytheon/Government test written notification will be sent to the Raytheon Subcontractor Manager.  The statement of readiness will schedule a TRR at least 2 calendar days prior to the proposed start of test.  The statement of readiness will also certify that the start test criteria will be met by the TRR and will specifically identify the current status of the work remaining.  As part of the TRR, the training devices will be available to Raytheon and the Government test team for a minimum period of five operational hours to accomplish a Functional Mission Assessment (FMA).  FMA will consist of Government defined procedures being used to verify that the training device is ready for test.  (DI-ADMN-81250, DI-NDTI-80808/T)

Verification that each ATD is installed, operates, and interfaces with the Government provided facilities and safety systems will be demonstrated through test procedures.  Prior to the start of testing, All discrepancies and deficiencies identified during in-plant testing will be corrected and identified during installation.  The on-site acceptance test will consist of Raytheon and Government conducted Acceptance Test Procedures (ATPs).  At the start of testing the FTD IPT will supply a Computer Program System (CPS) consisting of executable code (DI-NDTI-80603/T, DI-NDTI-80808/T).

#### 5.1.2.2  TIMS Test Planning (SOW 5030.5-5.1.1)

The TIMS IPT test team develops and records plans for conducting CSCI qualification testing in a Software Test Plan (STP) (DI-IPSC-81438, SDRL G035).  TIMS CSCI test planning starts in the earliest phases of software development.  During system requirements analysis, system design, and software requirements analysis, the TIMS IPT test members analyze each requirement for clarity and testability and produce the STP.  The preliminary STP is reviewed at SSR; the final STP is updated, reviewed and baselined at PDR.  As design and coding proceed for each increment, the STP is maintained and updated and detailed test descriptions are developed and recorded in a Software Test Description (STD)(DI-IPSC-81439, SDRL G036).  Preliminary versions of the software test descriptions are reviewed at CDR.  As each increment is coded, detailed test procedures are developed and reviewed.  Before each increment undergoes increment CSCI testing, the detailed test procedures for that increment are baselined.  After all increments are completed, the test team conducts a formal CSCI Test Readiness Review (TRR), baselines all the detailed test procedures, and performs formal CSCI testing for the completed TIMS software.  The TIMS IPT will plan for and support an in-plant test consisting of selected portions of the STD, a Raytheon/Government hands-on period of free-play usage, and other tests deemed necessary.  The ATP will be development from a Raytheon selected portion of the STD to be used during on-site test of the TIMS.  (DI-IPSC-81438/T, DI-IPSC-81439/T)

#### 5.1.2.3  Other CSCI Test Planning (SOW 5030.5.2, 5030.5.3, 5030.6)

All GBTS components will be tested, including Student Workstations, Mediated Interactive Lecture Classroom, UTD Adjunct Station, ATDSS, CSS, and the TIMSSS.  FlightSafety International (FSI) will provide for and participate (as required by Raytheon) in a Multi-Service Operational Test and Evaluation which will exercise the OFT with a series of typical training scenarios.

### 5.1.3  System Test Planning (SOW 5030, 5030.1.5-1.7, 5030.7)

As part of the system test planning activities set forth in the ITP, a GBTS Test And Evaluation (T&E) Program will be developed to: 1) plan, conduct, support and report on test activities; 2) verify compliance with the requirements of the GBTS SS, PUSD, and the SOW;  and 3)obtain acceptance of test reports.  Existing data (e.g., analyses or test results) will be provided to Raytheon and the Government to support acceptance or to address any questions about GBTS components.

Each IPT supports definition and integration of the T&E activities for the GBTS.  The IPT will address all test and demonstrations required by the GBTS SS and applicable product specifications and the additional testing required by the SOW.  The ITP will be written as an appendix to Raytheon ITP (133E662) and conform in style and format.  Integrated tests will verify the interfaces between the components and simulate loads to verify response times for all components of the GBTS, including FTDs, TIMS, MUSS, CBTS, and courseware.  (DI-NDTI-80603/T, DI-NDTI-80808/T)

Individual test reports for each test and demonstration required by the GBTS SS, applicable product specifications, and the SOW will be made available for Raytheon and the Government to review.  FlightSafety will implement an automated test tracking and reporting system that will interface seamlessly with the Raytheon system.  Data will be transmitted in an MS Excel readable format.  The following data will be provided:  Test Event, Duration, RFP Paragraph, Schedule Event, Test Plan Number, Test Plan Due Date, Test Date, Test Report Due Date, and Status.

Figure3.0-5 shows how the various test plans and procedures will work together to produce a total system test plan.

#### 5.1.3.1  TIMS System Test Planning (SOW 5030.5.1.1)

The TIMS IPT test team members participate in developing and recording plans for conducting TIMS component-level on-site acceptance testing.  TIMS component-level on-site acceptance testing is performed at Randolph AFB by Raytheon and the Government testers with support from the TIMS IPT test members.  System test planning is documented in the TIMS STP (SDRL G035) and the Integrated Test Plan.  The TIMS STP is reviewed and baselined at the TIMS CDR.  The TIMS on-site acceptance testing includes a mutually agreed to subset of the STDs, which have been designated as ATPs.  Sections 5.10 and 5.11 of this SDP contain further details about TIMS CSCI/HWCI integration testing and TIMS system testing.

### 5.1.4  Software Installation Planning (SOW 5080-1.1, 5080.2.1-2.2, 5080.3 )

IPTs will prepare and maintain a site activation plan for support of the Government's site activation and transition planning activities (DI-FACR-81047/T).  This plan will address: all the components of the GBTS;  the transportation, assembly, installation and checkout of each GBTS component on site; the total maintenance support of the GBTS including all materials, spares, equipment and personnel needs to support this effort; additionally the plan will address activation activities for those operational sites are not addressed in the JPATS Site Activation Plan.  Support system installation planning will include a list of all equipment and fixtures required to supply support and maintenance of the GBTS.

IPTs will provide consulting and engineering services to the Government System Program Office’s (SPMO's) Site Activation Task Force team through assisting in the development of procedures, drawings and equipment installation and checkout procedures.

As part of the installation planning, a facilities requirements document (DI-FACR-81045/T) will be prepared to assess the current impact on the facilities and identify new capabilities required for installation of the GBTS.  Site Evaluations Reports (DI-FACR-81046) will establish facility requirements for each GBTS component, to include the layout for all training system equipment in the facility.

The comprehensive transition plan will detail how GBTS components will be activated in a way which minimizes the impacts to primary training operations and will be part of the status reporting at program reviews.  If necessary Appendices will be generated for the Support Site Activation Plans to address any and all software requirements.

The Support Site Activation Plan contains the following information:

- Site Activation Management Organization  (government and contractor)

- List of government and contractor responsibilities during planning, requirements preparation, facility modification, support equipment installation and acceptance check-out.

- Description of personnel (number, type and skill level) needed for installation

- Activation milestone schedules (2 levels of detail)

- (For each site) Delivery dates for support equipment and spares.  Identification, quantity, and delivery dates for  technical manuals, training requirements, and facility construction.

- Identification of required government support services.

- List of support equipment checkout contracts, plans, sell-off procedures, and forms for each site and unit.

- Installation team, installation procedures, and data update procedures.

- Plans for statusing, tracking and reporting site activation activities.

### 5.1.5  Software Transition Planning (SOW 5080.2.3, 6040-1.5 )

As part of the software transition planning, a Support Site Activation Plan is developed and a Facilities Engineer is assigned to oversee facilities management and design requirements.  The Facilities Engineer  will provide facility engineering design planning, analysis, and consulting services to the Government as outlined in the SOW.  Facilities Engineer  duties also include pre-planning activities which assist in the transition of operations to the proposed GBTS site.  Planning is documented in the Support Site Activation Plan.

Initial GBTS training will be provided in accordance with the SOW 6040.  IPTs will prepare training outlines for Raytheon approval.  Randolph AFB will be supported by a temporary MUSS (on-site or at the development facility) until the USAF MUSS becomes operational.

### 5.1.6  Following and Updating Plans

Following approval of the plans by Raytheon and the Government, the GBTS PMO places the above described planning documents under configuration control and implements the various software development, testing, transition and site activation activities according to the plans.  The IPT leaders are responsible for ensuring compliance with the various plans.  IPT leaders and Software Quality Assurance (SQA) perform periodic reviews and audits of the plans and processes to ensure compliance.  Except for internal schedules and related staffing information, updates to the plans go through the change control process and require Raytheon approval.

SQA uses procedures listed in Section 5.16 to evaluate compliance with plans, especially the SDP.  CM is responsible for all documentation deliveries in accordance with the procedures listed in  Section 5.14.  In addition, the IPTs use the  following directives, procedures, and guidelines for additional information on updating and following plans.

- Logicon Engineering Instruction Binder (LEIB)

- FSI Software Engineering Practices & Procedures manual

- FSSC QAM-1000 Quality Assurance Manual

## 5.2  Establishing a Software Development Environment

The following sections describe the approach for establishing, controlling, and maintaining the software development environment.

### 5.2.1  Software Engineering Environment (SEE)

#### 5.2.1.1  FTD Software Engineering Environment

The Software Engineering Environment (SEE)  includes the tools listed in Table 5.2.1.1-1 for development of FTD software.

| Software Tool | Vendor | Purpose |
| --- | --- | --- |
| Windows NT | Microsoft, Inc | Operating System |
| RTX 4.1 | VenturCom/Microsoft | NT Real Time Extension |
| ObjectAda Enterprise NT | Aionix | Ada95 Compiler for Windows NT |
| Visual C++ | Microsoft, Inc. | Text Editor and C++ Compiler |
| MS Office 97 | Microsoft, Inc. | Word Processor & Desktop Applications |
| Rational Rose | Rational, Inc. | CASE Design Tool |
| AVIDS Development Software | Evans & Sutherland | LCD Graphics and drivers development tool |
| Radio-Nav Database Utilities | FlightSafety International | Down loading & managing ARINC 424 RNAV data |
| DOORS | QSS Corporation | Requirements management & traceability tool |
| ClearCase | PureAtria | CM Tool |
| PureDDTS | PureAtria | Change Request Manager |
| Microsoft NT Toolkit | Microsoft, In. | IOS GUI Toolkit |
| Model Builder | ASTI | Aural Cue CASE toolkit |

TABLE 5.2.1.1-1a  FTD SEE Software Tools

The SEE will include a project directory structure which will be resident on the GBTS development computer.  The project directory will include the subdirectories listed in Table 5.2.1.1-2.

FSI’s Computer Systems department will set up the SEE, Software Development Library (SDL), and project directory structure as needed for software development activities.  Included in this is set up and configuration of the GBTS development computer, which will be delivered as the FTDs support site computer.  The SDL and project directory structure will be set up on the FSI SSD computer network, and transferred to the GBTS development computer when it is delivered.  The Ada compiler will be set up on the GBTS development computer prior to the start of the software design phase.

| SDL | The software development library (SDL), containing ClearCase controlled version data on all source code, documentation, and configuration files in the simulation host CSCI. Data on each release to the Developmental Configuration (DC) is also contained in the SDL. Changes to the contents of this directory will be permitted only by means of ClearCase utilities. |
| --- | --- |
| USERS | Will contain a subdirectory for each engineer. This subdirectory will be used to create test executables. Each user subdirectory will contain a symbolic link to the SDL directory, allowing all users to work from the same ClearCase archive. |
| DC | Contains the Development Configuration, including a copy of the released version of each source code and documentation file and an executable load built from released software. |
| TRAIN | Contains the current Training Configuration (TC) and some previous TCs in separate subdirectories. The current TC is used for system checkout, Acceptance, and, following approval, for training. |

TABLE 5.2.1.1-2  FTD Subdirectories of the Project Directory

#### 5.2.1.2  TIMS Software Engineering Environment

The TIMS development network is a Personal Computer (PC) workgroup based, peer-to-peer Local Area Network (LAN), designed to mirror the deployed network.  This network contains dedicated server(s) and can be easily reconfigured for prototyping, demonstrations, and testing.  Table 5.2.1.2-1 lists the SEE software items, including CASE tools.

TIMS will selectively replace/upgrade about half of the development machines to the machines picked for deployment at about the three year point.  TIMS intends to delay selection of the specific deployed PC machines until that time, in order to take advantages of technology changes and cost changes.  The same philosophy is used for notebook devices and other computer equipment.  The TIMS IPT is delaying the exact choice of these devices until year two and three in the program.  Table 5.2.1.2-2 lists the current SEE hardware items.

| Software Tool | Vendor | Purpose |
| --- | --- | --- |
| Basic Software |  |  |
| MS Office Pro & MS Office Standard | Microsoft, Inc. | General Word processing, diagrams, briefing charts, documents |
| Windows NT | Microsoft, Inc. | Windows operating system |
| Dr. Solomon’s AntiVirus Server for Windows NT & AntiVirus Software Workstation (WinGuard only) | S&S Software International | Anti-virus software |
| Visio 4.0 | Shapeware Corporation | Graphics tool |
| MS Project | Microsoft, Inc. | Project Management |
| DocEXPRESS | ATA, Inc. | Integrated Document Generation & MIL-STD-498 Templates |
| Open Plan Professional | Welcom Technologies | EVMS; Scheduling interface with Raytheon |
| Open Plan for DOS 5.2 | Welcom Technologies | Interim tool to support risk analysis (required by SOW) |

TABLE 5.2.1.2-1  TIMS SEE Software Tools

| Software Tool | Vendor | Purpose |
| --- | --- | --- |
| Basic Software (Continued) |  |  |
| OPERA 1.5 | Welcom Technologies | Interim risk analysis tool that works with Open Plan for DOS (required by SOW) |
| FoxPro | Microsoft, Inc | Needed to support Open Plan for DOS |
| Lotus Notes Desktop 4.0 | Lotus Development Corporation subsidiary of IBM | Interface with Raytheon MIS |
| MS Exchange | Microsoft, Inc. | Mail for connections to JPATS community (Government, Raytheon, FlightSafety, etc) |
| Network Support |  |  |
| MS BackOffice plus client packages | Microsoft, Inc. | Includes NT Server, MS Exchange, SQL Server, System Management Server |
| BackOffice Tech support (10 incident packs) | Microsoft, Inc. | Technical support |
| Open View Workgroup Node Manager for Windows NT | Hewlett Packard | Network support tool |
| Software Development Tools |  |  |
| Paradigm Plus for Windows NT plus OOD module | Platinum Technologies | CASE design modeling tool |
| Visual Workflow | File Net Corp. |  |
| DOORS | QSS, Inc. | Allocate, categorize and trace requirements between system reqs, software reqs., test cases, design, code, increments, etc. |
| ObjectAda | Aionix | Ada95 Development Environment, Ada 95 Compiler and Windows GUI Builder |
| Microsoft Visual C++ | Microsoft, Inc. | C++ Development Environment, Compiler, and Windows GUI Builder |
| Microsoft Developer’s Network (MSDN) CD Level 1 subscription (Library Subscription) | Microsoft, Inc. | Up-to-the minute documentation and knowledge base for Windows problems, utilities, and debug information. |

TABLE 5.2.1.2-1  TIMS SEE Software Tools (Continued)

| Software Tool | Vendor | Purpose |
| --- | --- | --- |
| SoftwareDevelopment Tools (Continued) |  |  |
| MSDN CD Level 2 subscription (Professional Subscription) | Microsoft, Inc. | Same as Level 1, with additional access to debug kernels, code examples, bug fixes. This level includes technical support and is designed to support development of individual workstation set-ups. |
| MSDN CD Level 3 Subscription (Enterprise Subscription) | Microsoft, Inc. | Same as Level 2, with additional access to debug kernels, code examples, and bug fixes. This level includes technical support and is designed to support development of network client/server applications and enterprise integrated systems... |
| MSDN CD Level 4 Subscription (Visual Tools Subscription) | Microsoft, Inc. | Visual Basic Enterprise, SourceSafe, Visual C++ Enterprise, FoxPro Professional, Visual J++, Access Developer's Toolkit, the Office products (including dev. & test licenses) Word, Excel, Access, and Project. |
| ClearCase/PureDDTS for Windows NT | PureAtria, Inc | Configuration Management and change processing tool for files (binary and ASCII) |
| SQA Suite 5 | Software Quality Automation Inc. | Automated testing tool |
| PowerBuilder 5.0 Professional & Enterprise | PowerSoft | GUI Tool. Used for prototyping database forms. |
| PowerSoft Technical Support (10 incident packs) | PowerSoft | Technical support for PowerBuilder and InfoMaker |
| InfoMaker | PowerSoft | Provides end-user database report generation capability |
| Authorware | MacroMedia | CAI authoring package (interface with Courseware) |
| PHDEnterprise | Professional Help Desk subsidiary of Data Systems & Software | Help desk systems |
| Doc-To-Help | WexTech | Hypertext help authoring system utilities |

TABLE 5.2.1.2-1  TIMS SEE Software Tools (Continued)

| Hardware Item | Quantity | Purpose |
| --- | --- | --- |
| Main development network server Pentium 200, 128MB RAM, 3 Ultra SCSI fast 3.1G hard drives, 7 GB Tape drive (XOByte), 17" monitor, 512K L2 cache, keyboard, mouse, ethernet card, internal 33.3 modem | 3 | Server |
| Proxy server Pentium 200, 128MB RAM, 3 Ultra SCSI fast 3.1G hard drives, 7 GB Tape drive (XOByte), 17" monitor, 512K L2 cache, keyboard, mouse, ethernet card, internal 33.3 modem | 1 | Exchange Server (Email) |
| Developer Workstation 1 Pentium 200, 32MB RAM, 2.4G hard drive, 8x or better CD-ROM, 17" monitor, ethernet card, Matrox Millenia video card, 512K L2 cache, keyboard, mouse, ZIP drive (parallel) | 39 | Most developers, plus IPT lLeader, System Engineer, Lead Software Engineer, |
| Developer Workstation 2 Pentium 200, 48MB RAM, 3.1G hard drive, 12x or better CD-ROM, 21" monitor, ethernet card, Matrox Millenia video card, 512K L2 cache, keyboard, mouse, ZIP drive (parallel) | 10 | 3 developers each of GUI, database, and applications |
| Developer Workstation 3 Pentium 200, 64MB RAM, , 2 Ultra SCSI fast 3.1G hard drives, 800MB CD-R burner, 21" monitor, 512K L2 cache, keyboard, mouse, ethernet card, Matrox Millenia video card, ZIP drive (parallel) | 2 | CM/Integration/Sys Ops |
| Business Workstation Pentium 166, 32MB RAM, 1.6G hard drive, 8x or better CD-ROM, 17" monitor, ethernet card, Matrox Millenia video card, 256K L2 cache, keyboard, mouse, ZIP drive (parallel) | 7 | PCA, secretary, 3 tech writers |
| Low End Laptop P133 with 16MB RAM, 1.08MB hard drive, 28.8 PCMCIA modem, ZIP drive (parallel), ethernet PCMCIA, dual scan | 2 | Used by technical staff when traveling |
| High End Laptop P133 with 48MB RAM, 1.08GB hard drive, 33.6 PCMCIA modem, high quality display, ZIP (parallel), 4x CD-ROM, ethernet PCMCIA | 1 | Used for “road show”, demonstrations of prototypes, etc. |
| Developmental PDAs | 6 | Devices don’t exist yet. Will be bought at later date based on results of system design and software requirements analysis |
| HP Laserjet 5 with cable and network card | 3 | Shared laser printer |
| HP 1600M with cable and network card | 3 | Shared color printer to support briefings and road shows |
| UPS 4kva UPS, 15 connect | 1 | Workgroup experiments uninterruptible power supply |
| UPS 900va , 2 connect | 1 | Hub uninterruptible power supply |
| UPS per workstation | 58 | Individual uninterruptible power supply |
| UPS per server | 4 | Server uninterruptible power supply |
| 100-base-T Network cabling, hub, and installation labor to support 56 users and 4 servers in a "typical" office building; rack | 1 | Interconnect workstations |
| Epson LCD data/video projector (1024x768) with hard travel case and replacement lamp | 2 | Support item for reviews, meetings, and briefings |
| Kodak DC-50 digital camera, A/C adapter, and software | 1 | Supports site visits |
| Desktop Video Conferencing System, 32" TV, and VCR | 1 | Supports video conferencing and high speed data transfers |
| ISDN Modem (128KB) (Motorola BitSurfer Pro) | 3 | Supports video conferencing and high speed data transfers |

TABLE 5.2.1.2-1  SEE Hardware Items

| Hardware Item | Quantity | Purpose |
| --- | --- | --- |
| ISDN Digital Phone System | 2 | Supports video conferencing and high speed data transfers |
| Automated ID Technology External Reader and associated card | TBD | For secure use of Lotus Notes, required for RAC’s secure MIS system |
| 33.6 Modem (Internal) | 10 | For initial connectivity and as needed dialups |
| ISP | 1 | For email and internet connectivity |
| Overhead projectors (3000+ lumens) | 1 | Support item for reviews, meetings, and briefings |
| ZIP Blanks | 300 | Blanks; used for developer backups |
| CD-R Blanks | 190 | Blanks; used to produce documentation and software CD-ROMs |

TABLE 5.2.1.2-1  SEE Hardware Items (Continued)

The configuration management organizations support installation, control, and maintenance of the commercial portions of the SEE.  The TIMS IPT may use vendor technical support in installing and maintaining each item.  CM places all hardware and COTS software items under configuration management.  When upgrades or new versions become available, the TIMS IPT evaluates and recommends whether the update should be incorporated.  Upgrades are installed as soon as is reasonable for the development activities if the update is agreed to by all affected organizations.  Criteria for evaluating an update include considering problems detected with an update, problems solved by an update, and the impact on the software development effort.

### 5.2.2  Software Test Environment

FTD and TIMS software test environment specifics are described in detail in the Section 3.0 of the Software Test Plan.  The TIMS software test facility is a subnet of the development network (Figure 5.2.2-1).  The IPTs verify that system configurations meet the details of the Test Plan prior to the start of testing.  Preliminary TIMS-FTD integration testing is conducted at the FSI-SSD facility in Broken Arrow, OK.  Final on-site integration and qualification testing is performed at Randolph AFB, TX.  The in-plant integration test environment is a subset of the actual equipment to be delivered to Randolph AFB.  The on-site integration test environment is on the complete set of operational delivered equipment.  The on-site testing uses the base external system interfaces.

System test is performed at Randolph AFB, TX by Raytheon/Government personnel.  The system test equipment is the operational delivered equipment as described above.

#### 5.2.2.1  FTD Software Test Environment

FSI SSD’s OLIVE (Off-Line Integration and Validation Environment) station will be used for off-line testing of flight and engine models.  (The OLIVE is part of FSI SSD’s in-house software engineering environment and is used for development and testing prior to the availability of simulator hardware.  Its use is not required for operation or support of the trainer and it will not be part of the MUSS.)

FIGURE 5.2.2-1  TIMS Development Environment

An off-line development environment (Figure 5.2.2-2) will be set up for initial design and unit code/test and integration work.  This environment serves as the prototype for the Aircrew Training Device Support System (ATDSS), which will be delivered to the customer at the end of the development phase.  The first-unit computer equipment will also be employed for development and for advanced testing prior to integration with the FTD hardware (Figure 5.2.2-3).  Following hardware test, the FTD components will be used for hardware/software integration and testing.  Testing time on the OLIVE station and the simulators will be assigned by the Software Configuration Manager (SCM), as a part of the standard FSI SSD simulation time scheduling procedure.  Requests for simulator or OLIVE time are submitted each week by noon Wednesday.  The SCM assigns time to individual software engineers and to the hardware test group and publishes the next week’s schedule on Friday morning.  In periods of high demand, a simulator may be scheduled around the clock.

#### 5.2.2.2  TIMS Software Test Environment

The TIMS in-plant software test network is the same as the software development network.  It is a PC workgroup based, peer-to-peer LAN, designed to mirror the deployed network, except for being a smaller size.  Software development, unit integration testing, and CSCI testing  all occur on the same network.  The network is easily configured to a test environment.  During development, unit integration, and incremental CSCI testing, the network can be configured to isolate the development and integration testing.

FIGURE 5.2.2-2  FTD Development & Initial Test Environment

FIGURE 5.2.2-3  FTD Advanced Test Environment

During the formal TIMS CSCI testing, the network is fully configured for testing.  During TIMS CSCI testing, TIMS will be tested with GBTS external interface elements, though some data transfers with ATDs may be simulated with a simulator (playback files and lesson sortie files).  When external systems cannot be hosted at the development site or accessed remotely, stubs or drivers will be used for the external AF system interfaces.  The Raytheon/Government in-plant testing occurs on this same network.

### 5.2.3  Software Development Library

The GBTS SDLs are controlled collections of software, documentation, other intermediate and final software products, and associated tools and procedures used to facilitate the orderly development and subsequent support of software.  The SDL serves as the official source of project data and all materials entered into the SDL are catalogued, indexed, and numbered in a manner which facilitates retrieval by users.

The material in the SDL may be stored in human-readable form, machine-readable form, or both.  The SDL contains two logical parts: the documentation library and the code library.  The CASE tool ClearCase is the program level configuration management tool used to manage the library.  ClearCase provides control for both binary and ASCII files.

CM establishes the SDL shortly after the contract starts and maintains the SDL for the duration of the contract.  Prior to contract end, CM and the IPT Leader review the contents of the SDL to determine the items which need to be archived.  CM is also responsible for developing SDL procedures, which include:

- Procedures for cataloging and configuration identification of  baselined software products

- Procedures for the control of changes, including administration of the processing of Software Change Requests (SCRs)

- Procedures for initiating, recording, reviewing, approving, and tracking SCRs for software configuration items

- Procedures for creating software baseline integrated products and for the protection and release of software baseline products

- Procedures for recording and reporting the status of software products and SCRs

- Procedures for non-developmental software controls, including as applicable, commercially available software, Government furnished software, licensed software tools, and other plans, directives and guidance documents.

#### 5.2.3.1  FTD SDL

The SDL includes a directory on the software engineering environment computer.  The directory contains source and documentation files with change history, a list of source file versions in the current developmental configuration, and a Software Problem Report (SPR) for each software change released to the SDL.  The SDL directory will be configuration controlled; access will be provided only by means of ClearCase utilities.  (See SDP, Section 5.14)  The on-line portion of the SDL will be backed up to mass storage media each night, along with the rest of the project directory.  The FTD SDL operations and maintenance is described in SEPP-1000 procedure 2.02.  The SDL will be delivered as part of the MUSS support center.

#### 5.2.3.2  TIMS SDL

During the software development, CM maintains a directory structure for all code library items with at least the following directories:

- A NEXT BASELINE directory.  This directory contains the code towards the next developmental configuration.

- A CURRENT BASELINE directory.  This directory contains the current released developmental configuration.

- A DEVELOPMENT directory.  This directory contains the CSUs being coded, tested, or changed from the current developmental configuration.

Each baseline directory contains all Computer Software Units (CSUs), integrated Computer Software Components (CSCs), and the procedure files (i.e., the build or baseline procedures and compilation files) used to create the developmental configuration version.  Naming conventions for files are documented in the CSCI SDF.  To facilitate code release to SQA (for certification), independent testing group, or other organizations, the directory construction will be as “generic” as possible (i.e., the directory should not be constructed using parameters and structures that are unique to the development environment).

The TIMS SDL operation and maintenance is described in further detail in LSIS900213A CMP 3-4, Configuration Management Procedure for Software Development Library (SDL).  TIMS SQA has the responsibility for periodically evaluating and monitoring the procedures and operations of the SDL using LSIS890297 procedure QAP 2-1.

### 5.2.4  Software Development Files (SDFs)

SDFs serve as the repository for a collection of material pertinent to the development or support software.  SDFs are established and maintained at the system, CSCI, CSC and unit level.  A project system level SDF is established at the start of the contract in accordance with LSIS890297 QAP 2-7-1 and SEPP-1000 procedure 3.08.  The CSCI SDF is established during requirements analysis.  The CSC SDFs are established during the architectural design process.  The unit SDFs are established in the detailed design and coding processes.  SDFs will be maintained in electronic form.  The SDFs consist of files, checklists, notes or references to files or documents.  Occasionally, valuable technical data is not available electronically; in this case, the material is collected within a notebook or folder and the electronic SDF will reference this data.  SQA periodically audits the SDFs using LSIS890297 procedure QAP 2-7-2 and QAM-1000 procedure S-4010.

The unit level SDF includes (directly or by reference) the following minimum contents:

- The development record which provides the unit development schedule and current status

- A mapping of the applicable requirements and design constraints to the unit

- Detailed design documentation for each unit

- SCR change log, referencing by number, problems or changes which have been implemented after the initial baseline is established

- Unit listing which references the unit program listing

- Unit test which describes the unit test cases and the unit test results including applicable integration tests

- Notes, analysis, design considerations and constraints (including alternate designs which were considered and why they were not used), prototyping results, trade studies results, performance issues, etc.  which would be useful in the future maintenance of the unit.

### 5.2.5  Non-Deliverable Software

CM is responsible for maintaining and controlling any non-deliverable software used during software development.  The IPTs have the responsibility to ensure the operation and support of the deliverable software does not depend on any non-deliverable software used in the program, unless the Government has or can obtain the same software.  SQA is responsible for monitoring the non-deliverable and test support software for contractual requirements using LSIS890297 procedures QAP 5-1 and QAP 10-1 and QAM-1000 procedure S-3000.  Software necessary to the operation and support of deliverable software is maintained in the SDL and provided as part of the MUSS.

The only item of non-deliverable software foreseen for the JPATS project is the OLIVE system employed to perform early testing of integrated FTD software.  This system is not required (or used) after a real FTD environment comes into existence at the FTD manufacturer’s facility.  After delivery of the product baseline to the MUSS, software change testing will be accomplished on a co-located designated prototype FTD, thus OLIVE is not required.

## 5.3  System Requirements Analysis  (SOW 5020.1.1.11, 5020.1.7.1, 5020.1.7.2)

During system requirements analysis, the IPTs define and refine the system level requirements following the process depicted in Figure 5.3-1.  As part or the proposal effort, the FlightSafety team submitted a draft System Specification (SS) and draft component Prime Item Development Specifications.  During the analysis phase, all requirements are entered into the DOORS requirements traceability database.  The DOORS database tracks all allocated and derived requirements to customer requirements in the Raytheon JPATS GBTS Statement of Work (SOW) and to the System Specification.  Derived requirements may also reference a trade study that justifies the requirement.  As the software development process proceeds through system design and software requirements analysis, the requirements traceability database is expanded and updated.  If changes are necessary for any requirement, DOORS helps identify all linked higher and lower requirements.  System and software analysts use the DOORS database to more accurately predict the impact of changes.  The system requirements (documented in the SS) are reviewed and baselined at a GBTS System Requirements Review (SRR).

FTD SRA - During the system requirements analysis phase, the FTD IPT Leader and Project Engineer review the information contained in the JPATS - GBTS Data Package for input into the SSDD and SRS.  The data package contains aircraft data and assists in providing the necessary information to identify modules which might be candidates for simulated versus stimulated equipment.  Trade studies are performed as part of this phase to evaluate cost parameters and assist in the determination of simulate or stimulate.

TIMS SRA - The TIMS system requirements are documented in the updated SS and in updated TIMS PUSD.  The system and software interface requirements are documented in a TIMS Interface Requirements Specification (IRS).  The software requirements are documented in a TIMS Software Requirements Specification (SRS).

TIMS is designed to provide the functions of and gradually replace the following existing software systems.

- Time Related Instructional Management  (TRIM) System

- Navigator Training Student Accounting System (NTSAS)

- T-1A Training Management System (TMS)

- T-45 Training Integration System (TIS)

- AETC  Command Management System (CMS) (Form 7101)

- AETC Flying Training History Analysis System (FTHAS) (Form 7601)

- AETC Command Level (Honeywell DPS8) computer system

- Navigator Training Scheduling System (NTSS)

- Flying Training Programming and Accounting System (FTPAS)

- Flying Training Resource Allocation Program (FTRAP)

- Standard Training Activity Support System Flight (STASS-FLT)

During system requirements analysis, the TIMS IPT will work with existing documentation, the UFT community and SMEs to derive the appropriate system and software requirements for TIMS from these existing systems.  After contract award and analysis of existing software systems, the TIMS IPT intends to

conduct numerous site surveys and to conduct prototyping to thoroughly understand the user needs.  The TIMS IPT also performs risk analysis for volatile requirements to identify potential effects of changes in cost, schedule, support, or system performance.  Requirements whose volatility poses significant risks are entered into our risk management system so that the potential effects of changes can be monitored and detected early.

Also during the system requirements analysis, the TIMS IPT focuses on defining the interface requirements for TIMS external interfaces.  These interface requirements are documented in TIMS IRS.  The following are currently known TIMS interfaces to external systems:

- Core Automated Management System (CAMS) maintenance supply computer

- Military Airspace Management System (MAMS)

- Air Force Operations Resources Management System (AFORMS)

- Airspace Data to HQ AETC/XO

- Annual History Files to AL/HRMP (Armstrong Labs/Human Resources Laboratory) at Brooks AFB

- Reports 7101 & 7601 data to HQ AETC/ XOPR Personal Computers

- Air Force Training Management System (AFTMS)

- AETC Advanced Training System (ATS)

- Base bookstores (lists of training materials such as charts, manuals, or workbooks)

- Standard Training Activity Support System (STASS)

- Aviation 3M (AV3M)

- Navy Integrated Training Resources Administration System (NITRAS)

- Systems being replaced by the TIMS as necessary and external interfaces of the replaced systems.

- Automated Weather Distribution System (AWDS)

- Defense Data Network (DDN) for network E-Mail and file transfer.

- AETC base computer management information system network.

- Standard Accounting and Reporting System - Field Level

- Uniform Automated Data Processing for stock parts

- Automated Travel Order System

- AETC Management System

- Global Combat Support System

- Personnel Data System

- Navy Meteorological Integrated Distribution and Display (MIDAS) system for current weather

- Advanced Decision Support System (ADSS) to support flying hours tracking in support of 19th AF briefings

- Navy Smart Phone system to make daily event schedule information available via voice mail dial-up

At the end of the initial system requirements analysis process, the TIMS IPT participates in the GBTS System Requirements Review (SRR) to review the system requirements.  After SRR, the system requirements are placed under formal configuration control and used as the basis for developing the system design and system qualification tests.  During subsequent iterations through the system requirements analysis process for each addition increment, the TIMS IPT concentrates on analyzing changes or problem reports to assess whether the system requirements need updating.  TIMS IPT system engineering members provide technical expertise and continuity throughout the life-cycle.  TIMS IPT system engineering and PST T&E are also responsible for developing the system tests and system test procedures.

### 5.3.1  Analysis of User Input

The FTD IPT works with users and SMEs to refine the simulation operational concepts.  The GBTS PMO will include FlightSafety SMEs who have received Raytheon training, and have been qualified in the aircraft IAW SOW 5040.1.2, as well as Raytheon and Government personnel who are (or have access to) aircraft and instructional delivery SMEs.

Throughout the TIMS software development process, but with extra emphasis during system requirements analysis and system design,  the TIMS IPT works with Raytheon, the UFT community  and SMEs to gain an understanding of user needs and to promote consensus on expectations for the TIMS software.  The TIMS IPT plans to do extensive prototyping, including display models and demonstrations of COTS tools to involve all interested participants, obtain feedback, and derive complete and accurate requirements.  Section 5.3.3 contains further details about prototyping activities.  The TIMS IPT uses need statements, surveys, interviews, storyboards, prototyping, and demonstrations to obtain feedback.  Software engineers work closely with users to identify and refine the human interface.  The TIMS IPT prototypes and reviews displays and human interfaces with the UFT community.  The TIMS IPT discusses results from trade studies at regular technical interchange meetings.  The UFT community and users may also provide inputs to the TIMS IPT through problem reports.  The IPTs greatly facilitate attempts to involve all interested parties.  Obtaining user feedback is a continuous process that reduces risk by resolving problems and building consensus early in the development cycle.

FIGURE 5.3-1  Process Flow Diagram for System Requirements Analysis

### 5.3.2  Operational Concept

The goal of operational concept development is to describe the operational environment and objectives of the user.  The IPTs perform operational concept development as early as possible during the system requirements analysis process.  The operational concept definition then feeds into the refinement/development of the system requirements.   An overview of the operational concept definition process flow is shown Figure 5.3.2-1.  Training objectives are evaluated in addition to data obtained from the SMEs to determine implied hardware and software requirements.  Training scenarios are reviewed to outline software parameters and training station requirements.  JPATS training procedures are reviewed to ensure proper simulation.  Visual databases analyses and selection are based on the targeted training scenarios.

The TIMS IPT uses site visits, storyboards, and rapid prototyping methods to evaluate and refine user needs, define and quantify software scenarios, and develop user interface standards.

During operational concept development, the TIMS IPT analyzes and reviews the following:

- the current system and the proposed  new and modified system,

- the current users (types, organizational structures, training/skills, responsibilities, activities, and interactions with each other)

- the users for the new or modified system (types, organizational structures, training/skills, responsibilities, activities, and interactions with each other)

- the support concept for the current and new/modified system

- justification for the change

- one or more operational scenarios for the new/modified system

- summary of operational impacts including advantages, disadvantages, and alternatives and trade-offs which were considered.

| Description of Prototype | Output/Purpose |
| --- | --- |
| Prototype user interface for flight scheduler, electronic gradebook, squadron scheduler, and SOF/SUP assistant, and additional components as required | Active prototypes, GUI displays feed into design |
| Model network performance | Formal baseline computer simulation and prediction of net performance (normal and max loading). Used for measuring predicted/actual performance |
| Database Prototyping | Documented results of small-scale experiments feed into design. |
| Net Management Prototyping | Documented results of small-scale experiments feed into design. |

TABLE 5.3.3-1  Sample of TIMS-Specific Prototyping Activities

### 5.3.3  System Requirements

The IPTs use the system requirements analysis process is to describe the complete functional and performance needs of the GBTS system in sufficient detail so that system requirements can be completed and accurately stated.  Specialty engineering requirements, such as human-machine interfaces, reliability, maintainability, safety, and security are incorporated into the analysis process.  The IPTs identify, perform and document trade studies.  The teams also perform demonstrations and rapid prototyping to solicit feedback and to evaluate alternatives.  Table 5.3.3-1 describes a sample of specific TIMS IPT prototyping tasks.  Table 5.3.3-2 provides an overview of prototyping activities.  The IPTs record system requirements and traceability of each system requirement to higher level SOW using the  DOORS requirements traceability database.

Develop Operational Concept

FIGURE 5.3.2-1  Operational Concept Definition Cycle - Detailed Steps

| Technique | Description | Uses |
| --- | --- | --- |
| Storyboards | bullet charts, graphs, diagrams | System engineering practice . Used to model the business process in a way meaningful to the user. Diagrams can be used to show control and data flow. Storyboards help us understand the user needs. Used in early analysis phases. |
| Rapid Prototyping | quick development with no intention to reuse any actual code in the system | System engineering practice. Used to conduct feasibility studies. Used in early analysis and design phases. Also for developing initial GUI interfaces and displays. Used to solicit feedback from the users on their needs. An example is the development of screen navigation prototypes, which are produced to simulate the flow of one screen to another, allowing the user to get the look and feel of the system. Used by system engineering and developers to demonstrate a “proof-of-concept”. |
| Existing Systems | demonstration of existing products (e.g., SORTIM scheduler, COTS tools) | System engineering and software development practice. Used in early analysis and design phases to determine capabilities (COTS) and interfaces. Results of demonstration factor into the overall design allocation decisions |
| Evolutionary Prototyping | develop small, non-throwaway piece of the proposed system that tests the development and operational environment | Builds the software or a piece of the software in stages, in a quality manner with all the supporting documentation. Used in design and implementation phases. The software product evolves to be the operational system over several iterations. The user evaluates each iteration and provides feedback which is incorporated into the next iteration. This type of prototyping may be used for development of GUI displays. Another example is development of conversion software needed for a single legacy file. |

TABLE 5.3.3-2  Overview of Prototyping Activities

All IPTs participate in the review of the system requirements included in the SS prior to contract award.  The SS is baselined at and controlled after contract award.  TIMS component level system requirements are documented in the TIMS PUSD: Development Specification.  In the TIMS IPT RDM model, TIMS component system requirements analysis is an on-going process that is revisited for each subsequent TIMS increment/build.  Results from testing the first TIMS increment, action items, SCRs, additional trade studies, additional prototyping, and additional UFT community feedback may be incorporated into the system requirements analysis process for subsequent TIMS increments.  The TIMS IPT reviews any changes for impacts to the system requirements, and updates those requirement through the change control process as required by the baseline status of affect documents.

## 5.4  System Design (SOW 5020.1.1.13, 5020.1.7.2)

During the system design process, the IPTs develop a system architecture (system engineering synthesis).  The GBTS teams conduct trade studies, demonstrations, and prototyping to solidify and provide “proof-of-concept” for proposed architectures.  The IPTs develop the system processes and subprocesses interactively, all the while defining and refining the system and subsystems components and objects.  The IPTs examine existing designs and code to determine the feasibility of reusing them for the application.  The IPTs thoroughly consider COTS tools and other reuse elements during system design and maintains awareness of the long-term life-cycle strategy.  The TIMS system design is documented in a System/Subsystem Design Description (SSDD).  The FTD system design is documented in the PUSD.  The FTD IPT presents and discusses the preferred system design solution at the JPATS GBTS System Design Review (SDR).  The IPTs use the DOORS tool to update traceability between the system requirements and the system design.  An overview of the system design process flow is shown in  Figure 5.4-1 and Figure 5.4-2 below.

In the TIMS IPT RDM model, system design is an on-going process.  Results from testing the first TIMS increment, action items, SCRs, additional trade studies, additional prototyping, and additional UFT community feedback are incorporated into the system design process for subsequent TIMS increments.  The TIMS IPT reviews any changes for impacts to the system design, and updates the design through the change control process as required.

### 5.4.1  System-Wide Design Decisions

During the initial phase of system design, various system architectures are proposed and examined.  The IPTs conduct trade studies to consider risk, cost, viability, constraints, advantages and disadvantages of each proposed architecture or portion of the architecture.  The TIMS IPT team conducts extensive prototyping and demonstrations to obtain feedback from the UFT community.

The IPTs document IPT-applicable system-wide design decisions in the CSCI SDFs; the TIMS IPT also documents these decisions in the TIMS SSDD.  System-wide design decisions are also reviewed during peer reviews of the system architectural design.

### 5.4.2  System Architectural Design

The output of the system design process is an allocated baseline which describes:

- All component functional and performance characteristics

- Tests required to demonstrate functional and performance characteristics

- External system interfaces and interfaces between configuration items

- Performance and capacity characteristics

- Loading scenarios

- Components (configuration items) and their functional characteristics

FIGURE 5.4-1  Process Flow for System Design

FIGURE 5.4-2  Develop/Refine System Design - Detailed Steps

The FTD architectural design is predicated on the legacy architecture, system requirements analysis and the decision to simulate or stimulate aircraft components.  Trade studies are utilized and final decisions are documented in the FTD System/Subsystem Design Description SSDD.

During the system architectural design process, the TIMS IPT team defines and evaluates various system architecture alternatives; then a preferred solution is selected.  The TIMS IPT uses trade studies, prototyping and demonstrations throughout system design to define, refine and document the reasoning and rationale utilized to arrive at the allocated baseline for each of the components in the selected system architecture.  System requirements are allocated to hardware and software components.  Interfaces between hardware and software components are defined.  The TIMS IPT iterates through analysis and synthesis to assess feasibility and to structure the requirements in the most cost-effective manner.  The team identifies and examines reuse and COTS elements.  The TIMS IPT records the results of the initial design in the SSDD, which is subjected to internal TIMS IPT peer reviews as well as being  presented and reviewed at the GBTS SDR.  SQA is also responsible for performing an independent product evaluation of the SSDD using the LSIS890297 QAP2-13.27 checklist.  The SSDD is put under configuration control after the SDR.  During subsequent iterations, for the other increments, the TIMS IPT examines changes for impacts to the SSDD and updates the document as required.

## 5.5  Software Requirements Analysis  (SOW 5020.1.7.2)

The software requirements analysis process includes extracting and refining software requirements from the preliminary allocated functional baseline.  Software requirements analysis involves defining and recording the requirements (e.g., modes, functions, behavior, interfaces, security) for the GBTS CSCIs and their associated databases and adaptation procedures.  Figure 5.5-1 presents an overview of the process flow diagram for software requirements analysis.

FIGURE 5.5-1  Process Flow Diagram for Software Requirements Analysis

The IPTs document all of the software requirements in the DOORS requirements traceability database.  DOORS  allows full two-way analysis of all requirements relationships.  This capability enables engineers to quickly and reliably identify all  products (e.g., system specifications, requirements specifications, design, code, and test procedures) that are potentially affected by a change in requirements.

FlightSafety SEPP-2.01 contains additional details about the FTD activities to be performed during the  software requirements analysis phase.  The FTD IPT document the software requirements in Software Requirements Specifications (SRSs).  The software requirements are reviewed internally by the FTD IPT members.  Software requirements analysis for the FTD’s initially consists of isolating the software related requirements contained in the FTD PUSD Development Specification and identifying the FTD characteristics required to support the maneuver items contained in the JPPT syllabus.  These general requirements are combined with other component interface requirements, aircraft design criteria, courseware derived media requirements, trade study results, and other design concept related requirements and documented in the FTD SRS.  FTD interface requirements will be documented within the SRS.

The TIMS IPT analyzes system requirements, identifies software requirements, and analyzes the software requirements using the Object Modeling Technique (OMT) developed by James Rumbaugh.  This object oriented requirements engineering methodology (summarized in Figure 5.5-2 and Table 5.5-1) is an iterative process, which develops models of software functions and performance requirements.  The models are expressed in terms of objects and relationships (object models), dynamic control flow (dynamic models), and functional transformations (functional model).  The object model describes the static data structure of objects, classes, and their relationships between one another.  The dynamic model represents control information such as the sequence of events, states, and operations that occur within a group of objects.  The functional model shows the transformation of input value to output values by processes which become operations in the object model.  The TIMS IPT plans to use the CASE tool Paradigm Plus to describe the OMT models during the software requirements and software design phases.

During the software requirements analysis process, the TIMS IPT team uses prototyping and demonstrations to solicit user feedback, analyze functional and performance requirements and risks, analyze user functionality and interface requirements, and analyze non-developmental software items such as GFE or COTS products.  The TIMS software developers actively solicit feedback from the UFT community to derive complete requirements and build consensus.  The TIMS IPT also identifies opportunities for reusing software requirements material from other projects.  Logicon’s Software Engineering Directive for Requirements Management (LEIB SED-005) establishes standard instructions for allocating system requirements to software, controlling the baseline for software engineering and management use, and keeping the software plans, products and activities consistent with the software requirements.

The TIMS IPT documents the TIMS software requirements and interface requirements in the TIMS Software Requirements Specification (SRS) and TIMS Interface Requirements Specification (IRS) (DI-IPSC-81434, SDRL G037).  The TIMS IPT conducts internal peer reviews and a TIMS Software Specification Review (SSR).  After the TIMS SSR, the SRS and IRS become the baseline used during software design activities.  The SRS/IRS documents are placed under configuration control using ClearCase.  During the software requirements analysis process, the TIMS IPT team, working with the UFT community, prioritizes and categorizes the software requirements.  Then the TIMS IPT team coordinates to reach a consensus on the allocation of the software requirements into three incremental builds.  The allocation of requirements to increments is entered into the DOORS database.

During internal peer reviews, TIMS IPT reviewers evaluate each requirements for feasibility, risk, anticipated areas of volatility, correctness, completeness, testability, missing information, wrong information, and extraneous information.  SQA provides an independent product assessment of the SRS and IRS using the LSIS890297 product evaluation checklists QAP 2-13.28 and QAP 2-13.29.

In the TIMS RDM model, software requirements analysis is an on-going process that is revisited for each subsequent increment/build.  Results from testing the first increment, action items, SCRs, additional trade studies, additional prototyping, and additional UFT community feedback from previous increments are incorporated into the software requirements analysis process for subsequent increments.  During subsequent increments, the TIMS IPT software engineers review any requirement changes for impacts to the software requirements document and the incremental build allocations.  If new requirements arise or if a software requirement undergoes a significant change, the TIMS IPT coordinates with the UFT community and may re-map increment allocations.  The incremental build approach  and mini-life cycle for each increment provides flexibility to adapt to changes (i.e., changes as a result of feedback from testing an increment, technology changes, etc.).

FIGURE 5.5-2  TIMS Object Oriented Requirements Engineering

| Activity | Product | Steps |
| --- | --- | --- |
| Develop object model | - Object diagrams - Data dictionary | - Identify candidate object classes - Critically review candidate classes - Make a data dictionary - Identify candidate associations - Construct initial object model - Critically review candidate associations - Identify significant attributes - Refine object model (Iterate the steps above.) - Group classes into modules |
| Develop dynamic model | - Scenarios - Event trace diagrams - Event flow diagrams - State diagrams | - Develop scenarios of typical interaction sequences by identifying events between objects - Prepare event trace or event flow diagram for each scenario - Develop state diagram for each class that has important dynamic behavior - Check for consistency and completeness of events shared among state diagrams - Identify concurrence |
| Develop functional model | - Data flow diagrams | - Describe the important functions (input/output transformations) within the system - Show functional dependencies with data flow diagrams - Identify constraints. A constraint may be a function expressing one value directly in terms of others, or may be a constraint on the value of a function or several arguments. |
| Refine requirements | - Requirements database | - Remove non-requirements; restate to improve testability - Update requirements with understanding gained from the different models - Rephrase to clarify and reduce ambiguities - Incorporate information from user surveys, simulations, and trade studies |
| Build simulation | - Refined dynamic model - Refined requirements | - Define performance objectives and input to performance model - Use results to feed back into the dynamic model - Update requirements with understanding gained from performance model |
| Conduct trade studies | - Refined requirements | - Identify and conduct trade studies - Update requirements with information gained from trade studies - Identify and conduct prototyping - Update requirements with information gained from prototyping |

TABLE 5.5-1  TIMS Object Oriented Software Requirements Analysis Methodology

## 5.6  Software Design (SOW 5020.1.1.14, 5020.1.1.15)

Software design is composed of two phases: architectural design (preliminary design) and detailed design.  During the software design process, the IPTs software engineers decompose the software design into distinct software components.  The IPTs use these components to monitor the software development and provide for more accurate status reporting.  Specific definitions used within this SDP are as follows:

- Computer Software Configuration Item (CSCI):  An aggregation of software components that satisfies an end use function and is designated for separate end item documentation and configuration management.  TIMS software is a CSCI.

- Computer Software Component (CSC):  A functionally distinct part of a CSCI.  CSCs may be further decomposed into CSUs (see below).  The TIMS flight scheduler and the TIMS electronic gradebook are examples of CSCs.

- Computer Software Unit (CSU):  A logically distinct software component (module, Ada library unit, procedure, object, etc.) that is an actual physical entity, implemented in code, and that is separately testable.  The core scheduling algorithm is an example of a CSU.

During the initial software architectural design and detailed design process, the IPTs software engineers prepare the design at increasing levels of detail.  The preliminary design  and interface design information is documented in an appendix of the Software Product Specification (SPS) and reviewed at GBTS component PDRs.  The detailed design activity then proceeds with further refinements.  The detailed design is documented in updates to the SPS design appendix and reviewed at GBTS component CDRs.  After CDRs are complete, the GBTS design is baselined and put under CM control.

The software design for the FTDs follows the established simulator architecture for FSI-SSD produced simulators.  Figure 2 of SEPP-1000 procedure 4.03 shows the established Ada CSC architecture.  Design efforts are centered around specific aircraft data, visual systems, and training objectives.  Export and command package details are addressed during the design process.

In the TIMS IPT RDM model, the first iteration through the life cycle defines the design.  However, the TIMS software design process is on-going and is revisited for each subsequent increment/build.  Results from testing the first increment, action items, SCRs, additional trade studies, additional prototyping, and additional UFT community feedback are incorporated into the software design process for subsequent increments.  The TIMS software engineers evaluate any suggested changes for impacts to the software design and update the SPS design information as required.  In addition to design information in the SPS, the TIMS software engineers also record design information in CSCI, CSC, and CSU SDFs are appropriate.

In addition to the formal PDR and CDR, the TIMS team subjects both the architectural and detailed design to internal TIMS IPT peer reviews using the inspection checklists from the LEIB SER-20, Attachment 2.  SQA is responsible for independent product assessments of the design information.  During subsequent increments, changes to the SPS design information are controlled with the internal TIMS change control process and reviewed as necessary at technical interchange meetings.

### 5.6.1  CSCI-Wide Design Decisions

GBTS CSCI-wide design decisions are documented in the appropriate SPS design appendix and the CSCI SDF.  CSCI-wide decisions are decisions about the CSCI’s behavioral design (how it will behave, from a user’s point of view, in meeting its requirements, ignoring internal implementation) and other decisions affecting the selection and design of the software units that make up the CSCI.  Examples of CSCI-wide design decisions include:

- states and modes

- design conventions used to describe the design (e.g., Ada Design Language)

- inputs and outputs, including interfaces to other systems, both hardware and software

- responses to inputs and outputs

- approach for safety, security, and privacy requirements

- approach for providing flexibility, availability, and maintainability

- conventions for reentrant code

### 5.6.2  CSCI Architectural Design (SOW 5020.1.1.14)

Architectural design defines and records the behavioral design, interfaces, and architecture of each CSCI, associated databases, and adaptation procedures.  Figure 5.6.2-1 describes the process flow for architectural design.  Results from the architectural design process feed into the detailed design process.  The GBTS software engineers use object oriented design methods to develop the architectural design.  The software engineers map the functional and performance requirements to components (CSUs) or objects, databases, and procedures.

FIGURE 5.6.-1  Process Flow Diagram for Software Architectural Design

The partitioning of the CSCI into components or objects is based primarily on the principle of information hiding.  Using this method, requirements or design decisions that are likely to change are encapsulated to minimize the number of modules whose design will be sensitive to the potential change.  Typical areas of volatility are:

- target computer platform changes,

- format changes for external interfaces,

- structure of data stores,

- choice of algorithm.

The derived architecture is thus more robust and easier to extend during a subsequent build.  The database logical design is defined and documented.  The database is defined in terms of anticipated storage requirements, choice and rationale for schema, structure of the schema, database access keys, and database security and privacy considerations.  Interfaces are defined and documented.  Interfaces are defined in terms of purpose, the information to be exchanged, the interface communications protocol, and the purpose and format of any messages across the interface.

Each IPT’s software engineers are responsible for recording the traceability of the software components/objects, databases and adaptation procedures to software requirements in the DOORS database.  During the architectural design process, the GBTS software engineers document design results in the appropriate SPS design appendix.  The results of architectural design are also reviewed at component Preliminary Design Reviews (PDR).

The details for FTD architectural design are addressed in SEPP-1000 procedure 3.01 and 4.03.

The TIMS IPT detailed OMT process flow and methodology is shown in Figure 5.6.2-2 and Table 5.6.3-1.  The LEIB SER-004 and SER-004-2 contain additional details about activities to be performed during architectural design.  The TIMS architectural design is documented with the help of object models, dynamic models, and functional models.  The three models are combined to obtain class operations.

| Activity | Product | Steps |
| --- | --- | --- |
| Develop CSCI behavioral design | - External interfaces - Message formats - Communication protocols | - Refine external interface definitions - Identify interface messages and formats - Identify communication protocols - Identify reusable design elements from other systems |
| Develop CSCI architectural design | - Object diagrams - Data dictionary - Scenarios - Event trace diagrams - Event flow diagrams - State diagrams - Data flow diagrams | - Refine object model, allocate classes to subsystem - Develop solution object models, add implementation classes, and combine with dynamic model, and functional model to develop class operations - Develop solution dynamic model, adopt or finalize the strategy for control of the overall state for the subsystem - Develop solution functional model to show input transformations and output; operations from the object model are expressed as algorithms |
| Develop database logical design | - Database and bindings design - Database schema - Database administration capabilities - Database environment model | - Identify database environment - Develop database transaction analysis - Define database schema (items) - Define database binding design - Define database administration capabilities - Identify database conceptual model changes |
| Do Prototyping | - GUI products | - Identify user interfaces |

TABLE 5.6.2-1  TIMS Software Architecture Design Object Oriented Methodology

FIGURE 5.6.2-2  TIMS Object Oriented Design -- Detailed Steps

### 5.6.3  CSCI Detailed Design (SOW 5020.1.1.15)

During the detailed design process, the software development team further decomposes, refines and elaborates the architectural design to the lowest level of detail needed for a clear understanding of the capability requirements for each software unit.  Figure 5.6.3-1  presents an overview of the process flow for software detailed design.

The software developers record the behavior and relationships of each unit.  Each data element exchanged across each interface is identified and characterized with respect to units of measure, range of allowed values, accuracy and precision, timing and frequency of exchange, data type and data representation.  Communication protocols are elaborated, including message formatting, methods for decomposing and reassembling messages, error detection and recovery procedures, flow control, and routing and addressing conventions.  Reusable design elements are identified.  The database design is refined and related to data declarations.  The database logical design is transformed into a preliminary physical design expressed in the Data Definition Language (DDL) of the target database management system.  Supporting database information is developed including procedures for loading the database, detecting errors, recovering and reconstructing the database after a failure, and managing the database.

The software engineers are responsible for recording the traceability of the software units, databases and adaptation procedures to software requirements in the DOORS database.  During the detailed design process,

the software engineers document  the results of the software detailed design process in updates to the SPS design appendix.  The detail design is reviewed with the UFT community at component Critical Design Reviews (CDRs).  The design is then put under developmental configuration control.

FIGURE 5.6.3-1  Process Flow Diagram for Detailed Design

SEPP-1000 procedure 3.01 and 4.03 describe details for the FTD detailed design process.  The LEIB SER-005 describes additional details about activities to be performed during TIMS detailed design.  Table 5.6.3-1 describes the TIMS detailed design methodology.

| Activity | Product | Steps |
| --- | --- | --- |
| Develop CSCI detailed design | - Object diagrams - Data dictionary - Scenarios - Event trace diagrams - Event flow diagrams - State diagrams - Data flow diagrams - Ada packages - Change pages for modified software data packages | - Refine object model to software unit level - Refine dynamic model to software unit level - Refine functional model to software unit level - Update software and interface requirements trace to software units - Refine the performance model - Develop Ada packages |
| Develop CSCI interface design | - External interfaces - Internal interfaces | - Refine and complete external and internal interface definitions |
| Develop database physical design | - Database and bindings design - Database schema - Database administration capabilities - Database environment model | - Refine database environment model - Refine database schema - Refine database administration capabilities - Identify database conceptual model changes - Refine distribution, replication, and data synchronization approach - Refine directory structures |

TABLE 5.6.3-1  TIMS Software Detailed Design Object Oriented Methodology

## 5.7  Software Implementation and Unit Testing (SOW 5020.1.3.1)

Software implementation involves translating the detailed design into computer instructions for each software unit, database, data file, and adaptation procedure.  A consistent approach to program coding improves the quality, readability and maintainability of program source code.  It also increases the productivity, efficiency and mobility of software engineering resources.  The following factors are critical to effectively conducting the software coding activity:

- Develop and adhere to a well defined and structured software methodology.

- Use structured design and coding techniques.

- Control changes to software products with change and configuration management practices.

- Use incremental testing to improve the quality of deliverables.

Each section of code described in the specification is evaluated for compliance with the corresponding requirement, description, and applicable coding standards.  Basic rules in development include:

- Build hierarchical programs, group classes with similar functions

- Limit module size

- Use single entry and single exits from each module

- Isolate hardware and software dependencies

- Ensure data coupling by passing only data items between modules

- Prohibit self-modifying code

- Distinguish public and private operations

Table 5.7-1 describes the general methodology for the code (implementation) and unit test process.

| Activity | Product | Steps |
| --- | --- | --- |
| Develop unit code | - Software, databases, data files, and procedures | - Translate unit’s design into software code, database and data file declarations, and procedures |
| Develop unit test plan | - Unit test plans | - Develop unit test plans to verify the functionality, logic paths, interfaces, and error handling |
| Implement database | - Screens, reports, and views - Queries - Utilities and procedures | - Develop screens, reports, and views from the database design - Develop queries as needed to support screens, reports, and views - Develop utilities and procedures for maintaining and administering the database |
| Conduct unit test | - Unit tested software, databases, data files, and procedures - Unit test results | - Develop test data and test environment - Conduct test and capture results - Analyze and record test results |

TABLE 5.7-1  Code and Unit Test Methodology

For FTDs, the programmer is responsible for adhering to the given standards during the development of the assigned CSU.  The programmer will perform internal programming and testing prior to releasing the CSU to the build area.  Each software group will define tasks for implementation of the FTD and unit testing, under the direction of the PST Software Process Manager.  Prior to CDR each software group will develop a detail schedule covering software implementation, unit testing, and unit integration and testing.  FTD Software will be compiled against package specifications released during the architectural design phase to verify compliance with software interfaces.  Preparation steps and results of any unit tests performed will be recorded in the SDF for the software unit, along with analysis as appropriate.

The TIMS IPT plans to implement the TIMS software in three increments.  During the initial pass through the software requirements analysis activity, the TIMS IPT in coordination with the UFT community assigns requirements to specific increments.  For increment one, the TIMS software developers code the design portions needed to implement the requirements that have been assigned to increment one.  The process is repeated for increments two and three.  Unit testing is performed based on the current increment’s requirements and functionality; unit testing verifies the accuracy of the implementation for the current increment.

Figure 5.7-1 presents an overview of the process flow for code and unit test.  The unit software developer is responsibility for conducting and recording unit tests.  Internal IPT peer reviews are conducted to examine unit code, unit test cases, and unit test results.  Peer review members use the code and unit test inspection checklists from Logicon LEIB SER-20, Attachment 2 and FSI’s SEPP 5.00.  SQA participates in the peer reviews and provides an independent assessment of progress and the code and unit test process.

### 5.7.1  Software Implementation

During software implementation, the software developer codes the individual unit and populates databases and data files with real or realistic data.  The software developer is also responsible for recording traceability information between the software code units, databases and adaptation procedures to software requirements and the detailed design in the DOORS database and the unit SDFs.  The GBTS team uses internal IPT peer reviews of the code and unit test results to ensure the code correctly implements the design and requirements

and conforms to coding and documentation standards.  Normally, the IPT uses separate code and unit test peer reviews as shown in Figure 5.7-1.  However, for simple, non-critical units, the peer review process may be combined into a single code and unit testing peer review.  After the unit successfully completes the peer review process(s) and all action items have been resolved, the peer review moderator and the software developer notify CM that the code unit is ready for developmental CM control.

FIGURE 5.7-1  Processes Flow Diagram For Code and Unit Test

### 5.7.2  Preparing for Unit Testing

As the code for the current increment is being developed, the software developer also builds unit test case descriptions, procedures and test data.  The test cases and procedures should define inputs, expected results and evaluation criteria.  Unit test cases will cover each aspect of a unit’s detailed design including the following general requirements:

- Testing nominal, extreme and erroneous input values

- Testing all branches with the unit code

- Testing that all calling interfaces are correct

- Testing for proper error detection, error recovery, and generation of correct error messages

- Testing that allocated requirements are verified

- Testing executable statements for run-time errors

The software developer may use other previously tested, peer reviewed, and configuration controlled units in the process of conducting the current unit’s tests.  Test cases and  test descriptions are documented in the SDF.

### 5.7.3  Performing Unit Testing

The software developer performs unit testing after clean compilations of a unit, using the unit test cases and procedures described in Section 5.7.2.  Unit testing is done to assure proper execution of the unit.  Unit test results are recorded in the SDF.  After the software developer completes unit testing, the unit  undergoes a peer review of the unit testing results.

### 5.7.4  Revision and Retesting

Based on the results of the unit testing, the software developer makes all necessary revisions to the software, performs all necessary retesting, and updates the SDFs and other products as needed.  The software developer is also responsible for resolving action items which may come from a peer review or SQA review of the units.  SQA and the peer review moderator are responsible for monitoring that action items are resolved satisfactorily before action items are closed.  Once all action items are resolved, the unit is ready for developmental CM control and integration testing.

### 5.7.5  Analyzing and Recording Unit Test Results

The unit software developer is responsible for analyzing the results of unit testing and recording unit  test results in the SDF.  The IPT also uses the peer review process to examine test cases, test descriptions, and test results.  Peer review members are responsible for determining the adequacy, completeness, and accuracy of the testing.  SQA may participate in peer review,  performs independent audits of the SDF, and periodically evaluates the entire code and unit test process.  During iterations through the code and unit test process for subsequent increments, the software developer and the peer review members also place a focus on identifying and completing regression tests which may be needed as a result of the changing a CSU to add new capabilities (i.e.  not just focusing on testing and analyzing the new code).

## 5.8  Unit Integration and Testing (SOW 5020.1.3.1)

Unit integration and testing occurs in-house on the development configuration and is done throughout the coding phase.  Each IPT’s integration team plans to implement an integration and test approach called “frequent and public builds”.  This approach is described in detail in Dynamics of Software Development from Microsoft Press.  The following paragraphs summarize this process.

When coded units come available (i.e., a CSU is under developmental CM control and has completed code and unit test), each IPT’s integration team starts regular, scheduled builds of the current incremental product.  CM and SQA are major players on the integration team.  Each build includes the setup scripts, on-line help, etc.  Each IPT’s integration team (including SQA) then has a product that is available for status assessments by all IPT members, including testers, the software developers, the independent SQA, and the IPT Leader and technical leads.

The regular and frequent build process is a reliable indicator of the progress of the product.  The advantages of frequent builds are:

- The build exposes the real dependency tree.  Everyone can see what is causing the build to fail.

- The build exposes unanticipated weaknesses in design very early.  (Examples are performance or size problems.)

- The build gets everyone working in-sync.  This mechanism prevents the disconnect of every developer working to a different version.  Software developers can also use pieces already in the regular build to simplify their own unit testing.

- The build process forces the team to confront issues.  The current build is the real status indicator for the team.  This process promotes team solutions to problems.  This process also imposes discipline upon each developer, who must check for functionality and lack of regression before he or she presents new code to the integration team.

The key to the frequent build process is the idea of getting the product to a known state and staying there or progressing.  The software developers are constantly adding new features incrementally to the product including all documentation.  The IPT software developers address any regression in functionality immediately.  The IPT’s integration team is responsible for testing the multiple builds with automated and manual tests.  Each IPT’s integration team is also responsible for documenting the current known state.  The IPT integration team maintains:

- a comprehensive list of tested and missing functionality,

- a problem (bug) count sorted by severity, and

- other vital metrics.

### 5.8.1  Preparing for Unit Integration and Testing

Figure 5.8.1-1 presents an overview of the process flow for preparation for all types of testing, including unit integration and test, CSCI test,  CSCI/HWCI integration and test, and system test.  Table 5.8.1-1 summarizes the test preparation methodology for all types of testing.

Preparation for all testing starts at the beginning of the software development process and proceeds in parallel with the system requirements analysis, system design, and software development requirements analysis, design and coding activities.  Each IPT designates integration and formal test members who are responsible for developing test plans, test procedures and test cases (for unit integration and test level, CSCI test level, CSCI/HWCI test level, and System Test level.  These test plans contain the information about the test environment, the test tasks, and the test schedules.  Formal test planning is documented in the Test Plans/Procedures (SDRL G028) or Software Test Plans (SDRL G035).  The informal unit integration and test planning is documented in software test folders (STFs) or software development files (SDFs).

During early requirements analysis (system and software requirements analysis), the IPT test members examine dependencies between requirements and conduct planning for the test environment.  During the design phase, the IPT test member examine the dependencies between components and refine the number of planned integration and formal tests.

The TIMS IPT uses five Logicon procedures/guidelines documents to help guide TIMS integration and formal test teams in developing planning and test material.  These following items contains detailed steps, background information, and discussions of specific test methods.

- Software Engineering Procedure for Developing Integration and Test Plans (LEIB SEP-017)

- Software Engineering Procedure for Establishing Product Engineering Environments (LEIB SEP-018)

- Software Engineering Procedure for Developing Test Cases (LEIB SEP-019)

- Software Engineering Procedure for Developing Test Procedures (LEIB SEP-020)

- Software Engineering Guidelines for Integration and Test (LEIB SEG-009)

The FTD IPT uses FlightSafety’s SEPP 5.00, which provides objectives and guidelines to assist the FTD integration and formal test teams in developing planning and test material.

FIGURE 5.8.1-1  Process Flow Diagram for Preparation for Integration and Test

| Activity | Product | Steps |
| --- | --- | --- |
| Develop Integration and Test Plan | - Integration and Test Plan (informal integration plans for unit level and CSCI/HWCI level, formal test plans for CSCI and system test) | - Define scope of effort - Define the integration and test environments - Define the integration and test tasks - Define the integration and test schedules |
| Establish integration and test environments | - Configuration controlled integration and test environment (all test levels) | - Acquire and install environment hardware and software items - Maintain environment hardware and software items - Control the environment configuration |
| Develop test case descriptions | - Test case descriptions (all levels, informal documentation for integration levels, formal documentation for CSCI & system test level) | - Define functional test cases - Define performance test cases - Define interface test cases - Define regression test cases - Define benchmark test cases |
| Develop test procedure descriptions | - Test procedure descriptions (informal test procedures for unit integration and CSCI/HWCI levels, formal documentation for CSCI & system test) | - Define test procedures for each test case |

TABLE 5.8.1-1  Preparation for Integration and Test Methodology

### 5.8.2  Performing Unit Integration and Testing

During the unit integration and test process, each IPT’s integration team integrates the available software units, database, data files, and procedures in accordance with the integration and test plan.  Prior to the integration of a unit, the unit must have passed unit testing and peer reviews and be under CM control.  Integration testing emphasizes functional and performance aspects using integration threads.  During early testing, it may be necessary to represent unfinished portions of the software using stubs or drivers within the integration build.  Finished units gradually replace any stubs and drivers until the complete functionally for the CSCI is obtained.  Each IPT’s integration team is also responsible for tracing integration tests to the software requirements using the DOORS tool.

SQA is a key member of the integration team and is responsible for providing the IPTs Leaders and other management with an independent assessment of the current build.  SQA is also responsible for an independent assessment of the integration planning and is responsible for periodically evaluating unit integration and test activities using LSIS890297 procedure QAP 2-9 and QAM-1000 procedure S-8010.

Figure 5.8.2.1-1 presents a summary of the process flow for unit integration and test.  The following types of tests are conducted during unit integration and test:

- Functional -- Testing using nominal inputs to demonstrate functional capability and requirements satisfaction.

- Interface -- Testing to demonstrate consistent correct interfaces internally and externally.

- Regression -- Testing to verify the continued integrity of requirements implemented in prior development builds.

- Benchmark -- Testing to establish functional and performance characteristics of the current development build.

- Verification -- Testing to verify that specific software errors from previous development builds have been eliminated.

#### 5.8.2.1  Performing TIMS Unit Integration and Testing

TIMS unit integration and testing will be done in accordance with LEIB SER-011: Software Engineering Process Description for Unit Integration and Test.  Logicon experience has shown that incremental methods are effective tools for exposing and controlling risks.  The TIMS IPT plans on developing and testing the TIMS software in three increasingly formal increments.  To support this process, the TIMS integration testers generate frequent builds within each increment and perform unit integration and testing on the units needed for the current increment.  The last stage of the testing for each increment is informal testing of the CSCI test procedures and test cases, which are appropriate for the requirements of the current increment.  When all increments are complete, the final stage of the entire unit integration and testing process is informal testing of all the CSCI test procedures and test cases.

During the internal informal increment testing using the CSCI test procedures, outside participants such as Raytheon, the IV&V contractor, and Government representatives are encouraged, but not required to attend.  The approach of doing internal informal increment testing using CSCI test procedures minimizes risks by providing tangible progress milestones.  This approach also allows for incremental development and review of the detailed test procedures.  The TIMS IPT holds an internal test readiness meeting to review the detailed test procedures and verify that the test environment and the software for the current increment is ready for the internal informal increment testing using the CSCI test procedures.  The current CSCI test procedures, the increment’s software and test environment are placed under developmental CM control before the start of informal testing with the CSCI test procedures.

#### 5.8.2.2  Performing FTD Unit Integration and Testing

FTD unit integration and test activities will be conducted by each software department and will focus on integrating software units into groupings by department (Flight, Engines, Aircraft Systems, Nav & Avionics, Autoflight & Air Data, etc.).  Testing, corrective action and retesting are performed by the developers.  Departmental CSUs are integrated and tested using OLIVE (see 5.2.2 above), which includes the target operating system, simulator executive, but no simulator-unique hardware or computer to computer interfaces.  Code which interfaces with high-value hardware, control loading hardware or kinesthetic systems is tested completely for safety land robustness.  Other code is tested to ensure operation in the integrated environment.  This testing shall confirm that:

- CSU to CSU interfaces function properly.

- That integrated code runs and produces correct test results.

- That critical hardware interfacing code operates safely and without risk of damage to equipment.

Individual FTD components (IOS, Host, ECL, etc.) are independently integrated using the frequent public build method.  Informal testing is conducted by the developers and by Software QA, with results noted by Q/A in the appropriate SDFs.  Department 68 (computer systems) accumulates tested units into the component aggregate builds.

FIGURE 5.8.2-1  Process Flow Diagram for Integration and Test

### 5.8.3  Revision and Retesting

The IPT integration team documents problems encountered during unit integration and testing in problem reports and entered the problem reports into the corrective action system (see Section 5.17 for further details).  Software developers are responsible for fixing the problems, updating the design, recoding and unit retesting.  Changes to the previously CM controlled and test data or re-test data are reviewed as part of the change control system.  Major changes to design or code require another peer review of the unit and the unit test results.  Then the software developer resubmits changed the unit to CM control; the updated unit is then available for integration and test activities.  Both the software developer and the integration team use the DOORS database to identify all the existing test cases and procedures related to requirements in the changed units.  Analysis of the tests and procedures helps determine which test procedures are candidates for retest or regression testing.  Regression testing ensures that the changes in the software are fixed, do not degrade the resulting software and that the unit or function thread still performs its overall requirements.  SQA audits software changes and the integration testing as specified in the Section 5.8.2.

### 5.8.4  Analyzing and Recording Unit Integration and Test Results

Each IPT’s integration team analyzes the integration test results to verify that the software is performing properly.  Actual test results are compared to expected test results documented in the integration test plan.  Each IPT’s integration team stores integration test results in STFs or SDFs. The SDFs/STFs include a list of the current configuration controlled units which belong to the development build, integration (compile and link) instructions, integration results for the current development build, test cases, test data, test environment, test procedures, test results, and an up-to-date list of current known problems.  SQA has the responsibility to periodically audits the SDFs/STFs to verify that all items are properly recorded.  Integration test results are documented in an informal test report or briefing charts.  The FTD IPT produces an informal integration report at the end of the unit integration and test process.  The TIMS IPT produces an informal integration test report for each increment.  The TIMS integration report for the last increment summarizes the results of all the unit integration testing.

Each IPT holds an informal test readiness meeting to review the integration results and to verify that the software is ready to proceed to the formal CSCI qualification testing.  The code, test plans, test cases, integration test procedures, integration test results and integration test reports are all under placed under CM control.

## 5.9  CSCI Qualification Testing

CSCI testing is conducted in-plant at the IPT development sites.  Figure 5.9-1 presents an overview of the process flow for CSCI qualification test activities.

Note that the FTD software components are installed in separate computers, each with its associated hardware systems.  CSCI qualification consists of qualifying each software component for integration with its respective hardware component.  Subsequent to this component hardware/software integration,  the hardware/software components will be integrated to form the FTD system.

FIGURE 5.9-1  Process Flow Diagram for CSCI Qualification Test

### 5.9.1  Independence in CSCI Qualification Testing

#### 5.9.1.1  Independence in CSCI Qualification Testing (FTD)

FTD CSCI qualification testing is conducted only in order to verify that the software is ready for integration with hardware.  True qualification testing is conducted later in the process using the entire hardware/software system.  For this reason, CSCI qualification testing is performed by the Software Lead Engineer (SLE).

#### 5.9.1.2  Independence in CSCI Qualification Testing (TIMS).

Independence is a key component of the TIMS CSCI qualification test process.  The TIMS CSCI testing is planned by test personnel who are separate from the software developers involved in preparing the preliminary design, detailed design, or code.  The TIMS test personnel are  responsible for preparing the TIMS Software Test Plan (STP, SDRL G035) and TIMS Software Test Descriptions (STD, SDRL G036) and for providing the leadership and oversight for all testing.

Software developers support the CSCI test effort by contributing test cases and data or other technical information.  The software developers are also part of the peer review process for product evaluations of the STP and STD.  Software developers may perform the actually testing under the oversight of the TIMS Test Lead, but only in areas that they did not design or implement.

QA and the TIMS CSCI test team have the responsibility for the ensuring independence during the testing.  QA provides independent progress assessments to the TIMS IPT Leader and other management.  QA monitors the conduct of all CSCI Qualification Testing, inspects the documentation of the testing, and certifies the test results.  QA is also responsible for conducting periodic independent evaluations of the CSCI qualification test activities and products.

### 5.9.2  Testing on the Target Computer System

#### 5.9.2.1  Testing on the Target Computer System (FTD)

FTD CSCI testing is performed in-plant on  the prototype FTD computers (or in an environment closely replicating the prototype computers) prior to connection to the FTD hardware environment.

#### 5.9.2.2  Testing on the Target Computer System (TIMS)

TIMS CSCI testing is conducted in-plant on the software development and network equipment which is modeled to closely approximate the delivered operational equipment.  CSCI testing is conducted using machines which are equivalent to those being delivered (see Section 5.2.1 for further details about SEE equipment and upgrades).

### 5.9.3  Preparing for CSCI Qualification Testing

Preparation for CSCI qualification testing starts during the initial software requirements analysis process.  Each IPT examines the software requirements for clarity and testability, develops the test plans (SDRL G028 or G035), and plan/defines the CSCI test environment.  During design, implementation, and unit integration testing, the IPT’s testers develop detailed test procedures, participates in peer reviews, and monitors design, code, unit testing, and integration testing for impacts to the CSCI detailed test procedures.

Test plans (TP, SDRL G028 or STP, SDRL G035) are reviewed at component PDRs.  The test plans document the participating organizations, personnel, high level test information, data recording, reduction, and analysis techniques, and test schedules including locations.  The IPTs then proceed to define test cases and the traceability from the software requirements, which are documented in software test descriptions (STD, SDRL G036) or developmental test procedures (DTP, SDRL G027).  The preliminary test procedures documentation is reviewed at CDR.  The final version of the STD/DTP is delivered 30 days prior to the TIMS CSCI Test Readiness Review (TRR).  The STD/DTP provides further refinement for each test presented and describes:

- the hardware and software preparation,

- detailed test descriptions (requirements addressed by test, prerequisite conditions, test inputs, expected results, and criteria for evaluating results).

- detailed test procedures (operator actions or steps, expected results for each step, actions to follow for errors, and procedures to reduce or analyze the data).

Each IPT records test case traceability information in the DOORS database.  Reference SDP section 5.8.1 for further information about preparation activities for all levels of testing.  Each IPT reviews and coordinates schedules for CSCI testing with the GBTS PMO, Raytheon and with the UFT community at each major review.

The final step in preparing the CSCI test site is to record and verify the site configuration and load any necessary test tools and test databases.  All  equipment, including the software code, any tools, the computers, and the operating system will be configuration controlled prior to the start of CSCI qualification testing.  Section 5.2.2 describes further details about the configuration of the test environment during testing.  CM is responsible for controlling the test site until all testing has been completed.  The TIMS IPT conducts a CSCI TRR meeting approximately 2 days prior to the start of formal testing.

### 5.9.4  Dry Run of CSCI Qualification Testing

Each IPT normally conducts dry runs of the final in-plant CSCI qualification tests prior to the actual recorded qualification testing.  The dry runs ensure that current test procedures are complete and accurate and ensure that the software is ready for the witnessed test.  Results of dry runs will be recorded in STFs/SDFs.  Each IPT has the responsibility for recording any problems encountered during dry run testing in the problem tracking database.  If possible, the CSCI testers conduct final dry runs with CM controlled equipment (software and hardware).

### 5.9.5  Performing CSCI Qualification Testing

#### 5.9.5.1  Performing CSCI Qualification Testing (FTD)

FTD CSCI qualification testing is intended to prove that the individual CSCs can function and are ready for integration with the system hardware.  CSCI qualification testing:

- Will commence with a full system build using developmental configuration components.

- Will confirm that CSU to CSU interfaces function properly.

- Will be conducted on the actual target hardware system, or one configured identically.

- Will confirm that sufficient mass storage, memory and processing time are available on the target hardware configuration.

- Will be tested to the level required to gain confidence in the CSCI’s probability of successful integration with the system hardware, other CSCIs, and/or CSCs ported into other interfacing computer systems.

FTD CSCI qualification testing is normally an internal activity, however, Raytheon and/or Government representatives are invited to witness FTD CSCI testing.

#### 5.9.5.2  Performing CSCI Qualification Testing (TIMS).  (SOW 5030.5.1)

TIMS CSCI qualification testing is performed to demonstrate to the acquirer that CSCI requirement have been met.  TIMS CSCI qualification testing covers the requirements in the SRS and any associated IRS.  The TIMS CSCI test team performs the CSCI qualification testing in a controlled environment using the approved STD.  The test environment (equipment and software) is documented and under CM control.  The test procedures are reviewed, approved, and under CM control.  Raytheon, the IV&V contractor, and/or Government representatives are invited to witness the in-plant formal CSCI qualification testing.  After the TIMS test team completes CSCI qualification testing, Raytheon and Government representatives are invited to participate in CSCI testing.  The Raytheon and Government participants are invited to conduct all or portions of the STD.  The TIMS IPT will also support a hands-on period of free play.

### 5.9.6  Revision and Retesting

During testing, any deviations from the test procedures (test documentation errors, not software defects) will be documented as red-lines to the STD/DTP and corrected prior to on-site system testing.  The IPT testers document all software defects in problem reports, which are entered into the problem tracking database.  If the CSCI qualification testers encounter critical problems which prevent further testing, the qualification testing may be suspended until the software developers solve the problem.

Updates are done as part of the corrective action system (see Section 5.17 for further details).  Updates undergo internal IPT CCB review to ensure that the update fixes the problem, does not introduce new problems, and includes all relevant documentation updates.  QA does independent monitoring of updates and evaluates updates for completeness and correctness.

### 5.9.7  Analyzing and Recording CSCI Qualification Test Results.  (SOW 5020.1.3.1, 5030.1.6)

The IPT testers analyze CSCI qualification test results to verify that the software is performing properly.  The test team compares the actual test results to expected test results documented in the STD/DTP.  The CSCI qualification test results are stored in STFs/SDFs.  The STFs/SDFs include a list of the configuration controlled units, compile and link instructions and results, test cases, test data, test environment, test procedures, test results, and problems detected during the CSCI qualification testing.  QA periodically audits the STFs/SDFs to verify that all items are properly recorded.  The FTD IPT documents test results in a informal test report, which are available for Raytheon/Government review.  The TIMS IPT documents test results in a Software Test Report (STR), which is available for Raytheon/Government review.  The test reports contain the following information:

- an overview of the test results,

- an assessment of differences and effects of testing in the test environment versus the operational system,

- recommended improvements to testing,

- detailed results for each test (including any problems or deviations)

- a test log (contains date, time, location, hardware/software configuration information, and sequence information)

## 5.10  CSCI/HWCI Integration and Testing (SOW 5030.1.3)

CSCI/HWCI integration and testing is a process which involves integrating the CSCI with actual target hardware.

### 5.10.1  Preparing for CSCI/HWCI Integration and Testing (SOW 5020.1.3.1)

Preparing for CSCI/HWCI integration and testing is part of the broader preparation for the integration and test process flow represented in Figure 5.10.1-1.  The IPTs place hardware, software, and all test documentation under configuration control before the start of the CSCI/HWCI integration testing.  The IPTs also perform a test readiness reviews prior to the start of the CSCI/HWCI integration testing.

### 5.10.2  Performing CSCI/HWCI Integration and Testing.

#### 5.10.2.1  Performing CSCI/HWCI Integration and Testing (FTDs).
(SOW  5030.2.1, 5030.2.1.1, 5030.2.1.5)

FTD CSCI/HWCI integration and testing is a two step process (See Figure 4.1.1.1-1):

- Each individual computer system’s software is integrated into its respective hardware suite and tested as a “stand-alone” item during component HW/SW integration and test.

- The integrated HW/SW components are linked together and formally tested as a complete FTD IAW Development Test Procedures during Device Integration and Test.

FTD CSCI/HWCI integration and device integration are performed in plant by the FTD IPT’s developers..  Component testing is also performed in-plant by the FTD IPT.  Integrated device testing is performed in-plant informally by the FTD IPT’s developers and Q/A, and formally by a test team consisting of personnel from the FTD IPT and the T&E PST.  The testing will include an internal FTD IPT dry-run and a formal IPT/T&E test team conducted activity.  Raytheon and the Government are included in the test team for the formal phase.  The FTD CSCI/HWCI and Device integration testing are performed to demonstrate that the FTD software and hardware are operating in concert to satisfy the SS and FTD PUSD development specification requirements.  CSCI/HWCI and device  integration testing:

- Will be conducted using deliverable hardware.

- Will include the running of all formal tests documented in the DTPs.

- Will include subjective testing and free play by surrogate users or SMEs to establish that the system is robust.

- Will be conducted to the level required to demonstrate complete satisfaction of system requirements.

Prior to formal device testing, the FTD IPT will conduct a Test Readiness Review (TRR) and make the training devices available to Raytheon and Government test team for a minimum of five operational hours, so that the Raytheon/Government test team can accomplish a Functional Mission Assessment (FMA).

FIGURE 5.10.1-1  Process Flow Diagram for CSCI/HWCI Integration and Test

#### 5.10.2.2  Performing CSCI/HWCI Integration and Testing (TIMS).  (SOW 5030.5.1)

TIMS CSCI/HWCI integration testing is performed on-site at Randolph AFB as part of the first site installation.  The CSCI/HWCI integration testing is performed using delivered operational hardware.  Raytheon and the Government or a Government representative are invited to witness all TIMS on-site integration testing.  The TIMS CSCI/HWCI testing demonstrates that the TIMS software and hardware meet and satisfy system requirements (from the SS and TIMS PUSD) and ensures that the TIMS system is ready for on-site TIMS component Acceptance Testing.  The TIMS IPT testers perform all or a subset of the TIMS STDs.

### 5.10.3  Revision and Retesting

Problems encountered during CSCI/HWCI integration and testing are documented in discrepancy reports and entered into the corrective action system (see Section 5.17 for further details).  IPT software developers update the design, code or test procedures as necessary and perform unit/CSCI retesting to confirm fixes for software problems.  TIMS or FTD IPT hardware engineers are responsible for updates to hardware.  All TIMS updates and all FTD updates during formal testing are reviewed by the test team before the CSCI or HWCI is made available for further CSCI/HWCI testing.

SQA has independent responsibility for evaluating updates for completeness and correctness and for periodically monitoring the CSCI/HWCI activities and process.  The DOORS database is used to identify all the existing test cases and procedures related to requirements in the changed units.  The IPT testers analyze the traceability database to help determine which test procedures are candidates for retest or regression testing, and recommend those procedures to the test team.  Regression testing (done in accordance with LEIB SEG-009 for TIMS and SEPP 5.00 section 5.5 for FTDs) ensures that the changes in the software or hardware are fixed, that fixes do not degrade the resulting system, and that the system still performs its overall requirements.  The IPT CSCI/HWCI integration testers are also responsible for analyzing changes and  recommending any needed additional tests for test team performance.

### 5.10.4  Analyzing and Recording CSCI/HWCI Integration and Test Results.

FTD actual test results are analyzed and compared to expected test results documented in the Developmental Test Procedures (SDRL G027).  The TIMS actual test results are compared to the expected test results documented in the TIMS STD (SDRL G036).  CSCI/HWCI integration test results are stored in the STFs/SDFs.  The test results include a list of the configuration controlled items to be integrated, integration (compile and link) instructions, integration compile and link results, test cases, test data, test environment, test procedures, test results, and problems detected.  SQA has the responsibility to periodically audit the STFs/SDFs to verify that all items are properly recorded.  The result of the final CSCI/HWCI integration testing is documented in test reports.

## 5.11  System Qualification Testing (SOW 5030.2.1.6, 5030.5.1.1-5030.7)

System qualification testing is performed to verify that system requirements documented in the SS and PUSD have been met and that each CSCI is installed, operates, and interfaces with the Government provided facilities and safety systems.  Prior to the start of system testing, each IPT corrects discrepancies and deficiencies, which were unresolved during in-plant testing.  System testing is documented in Acceptance Test Procedures (ATPs) which are a subset of the STDs/DTPs.  The process flow for system qualification testing is described in Figure 5.11-1 below.

FIGURE 5.11-1  Process Flow Diagram for System Testing

### 5.11.1  Independence in System Qualification Testing

System testing is performed by Raytheon and Government personnel with the support of the T&E  PST and component IPT test members.  QA also monitors the conduct of all formal System Testing, inspects the documentation of the testing, and certifies the test results.  QA is responsible for evaluating system qualification test activities and products using LSIS890297 procedure QAP 2-17 or QAM-1000 procedure H-6000.

### 5.11.2  Testing on the Target Computer System (SOW 5030.2.1.6)

System testing is performed at Randolph AFB using delivered operational equipment in an operational environment.

### 5.11.3  Preparing for System Qualification Testing (SOW 5030.5.1, 5030.3.2.1.1)

As early as possible, the IPTs identify system test support personnel and coordinates system testing with Raytheon and Government test personnel.  The T&E PST and SMEs will perform ATD testing and be involved in the tracking and correction process.  Each IPT’s system test personnel coordinate with the JPATS GBTS Site Activation IPT to identify the test environment and other needed equipment.  Any deviations or waivers associated with system components are  identified and their impact documented.  The GBTS IPTs’ system test planning is documented in a Integrated Test Plan.  The on-site system test procedures are a mutually agreed on subset of the procedures in the IPT STDs/DTPs, which are designated as the Acceptance Test Procedures (ATPs).  T&E PST personnel, Raytheon and the Government monitor the on-going component CSCI and CSCI/HWCI testing to assess progress and readiness for system testing.  The IPTs’ system test support personnel coordinate with  Raytheon and Government personnel to develop detailed daily schedules for on-site acceptance test activities.

### 5.11.4  Dry Run of System Qualification Testing

#### 5.11.4.1  Dry Run of System Qualification Testing (FTDs)  (SOW 5030.2.1.6, 5030.2.1.7)

After components are delivered and installed at the operation site and the site is under configuration control, the T&E PST performs dry runs to verify that the system test cases and test procedures are accurate and that the system is ready for Raytheon and Government testing.  The dry run activities include the final GBTS integration testing of  the components not available during in-plant testing and verification of corrective action taken during in-plant testing.  The dry run tests results are documented and analyzed.  Results of dry runs will be recorded in the system test folder.  Test failures due to equipment failures are re-run following equipment repair.  Test failures due to problems are recorded on discrepancy reports and entered into the corrective action system.  Procedural failures result in red-lines to test procedures.  Red-lines are subjected to internal reviews (which include Raytheon and Government personnel) and approved before proceeding with the final system tests.  Dry run test results are documented in informal test reports which are available for Raytheon and Government review.  Available test results are also reviewed at TRRs before the start of formal component system acceptance testing.

#### 5.11.4.2  Dry Run of System Qualification Testing (TIMS) (SOW 5030.5.1.1)

The TIMS hardware and software are delivered and installed as part of the TIMS CSCI/HWCI integration testing.  The TIMS dry runs are the CSCI/HWCI integration testing (see SDP, Section 5.10.2).  Prior to the start of TIMS on-site acceptance testing,  the TIMS IPT conducts a simulated “day of training” where all functions of the TIMS are exercised and demonstrated (or simulated as necessary).  After the simulated “day

of training”, the TIMS IPT conducts a Test Readiness Review (TRR) to review CSCI/HWCI integration testing (dry-run) results and to access whether TIMS is ready for on-site acceptance testing.

### 5.11.5  Performing System Qualification Testing  (SOW 5030.2.1.8)

#### 5.11.5.1  Performing System Qualification Testing (FTDs)

FTD System Qualification Testing consists of Raytheon/Government performing on-site acceptance testing IAW the appropriate FTD ATPs.  This testing is performed on-site on the fully integrated, installed prototype FTDs.  FTD T&E and software personnel will support FTD formal qualification testing as required.  Raytheon and the Government provide provisional DD250s at the end of each FTD acceptance testing event.  Post acceptance software support is provided for Small Group Tryouts (SGTO), System Level Formative Evaluation (SLFE) and GBTS integration testing.

#### 5.11.5.2  Performing System Qualification Testing (TIMS)

The TIMS system testing support involves three elements:  (1)TIMS on-site Acceptance Testing, (2) TIMS SLFE support, and (3) TIMS participation in GBTS integration testing.

##### 5.11.5.2.1  On-Site Acceptance Testing (TIMS)

TIMS on-site system acceptance testing is performed by Raytheon and Government test personnel  in accordance with the configuration controlled ATPs (including the red-lines from the dry runs).  The steps of each test procedure are executed and the test results are recorded.  The TIMS IPT SQA monitors the system tests for compliance with the test documents.  The TIMS IPT members support Raytheon and Government testing as required.  Raytheon and the Government provide a provisional DD250 at the end of the TIMS component acceptance testing.

##### 5.11.5.2.2  SLFE Support (TIMS)

After on-site acceptance testing, the TIMS IPT supports SLFE testing, which is the acceptance testing for the Courseware.  Before the start of SLFE support, the entire TIMS system (operational TIMS and TIMS-SS) has been fielded and tested.  In addition to SLFE Courseware support, the TIMS IPT intends to conduct formal tests (from the DTPs) to show that TIMS correctly manages other undergraduate flight training courses (i.e., T-37, T-38, etc) for courses at Randolph AFB and other bases.  The TIMS IPT will run TIMS in parallel with a subset of the operational training programs with real or simulated data.

##### 5.11.5.2.3  TIMS Participation in GBTS Integration Testing.  (SOW 5030.7)

After SLFE testing is completed, the TIMS IPT supports the final GBTS integration testing.  The GBTS Integration Testing if the final formal testing and is intended to demonstrate that all parts of GBTS coordinate smoothly under a maximum student loading scenarios.  GBTS Integration Testing concentrates on testing performance, response times, and interfaces (internal and external).  Raytheon and the Government perform GBTS Integration Testing with support from the various GBTS IPTs.

### 5.11.6  Revision and Retesting

Test failures due to equipment failures are re-run following equipment maintenance.  Test failures due to software problems are documented in discrepancy reports and entered into the corrective action system (see Section 5.17 for further details).  If problems require software revisions, the software and any needed documentation are updated, internally tested, and re-released in accordance with change control procedures.  The component IPT CCBs, the GBTS CCB, component IPT SQA, and PST QA are responsible for monitoring and evaluating updates for completeness and correctness.

The IPTs use the DOORS database to identify all the existing test cases and procedures related changes.  Analysis of the tests and procedures helps determine which test procedures are candidates for retest or regression testing.  Regression testing ensures that the changes in the software/hardware are fixed, that changes do not degrade the resulting system, and that the system still performs its overall requirements.  Retest at the system test level will then occur after changed units complete developer re-integration and retest.  QA and the customer are notified of any retest date and time.  Non-critical problems may be deferred and/or fixed in subsequent releases.

### 5.11.7  Analyzing and Recording System Qualification Test Results

The IPTs support Raytheon and Government testers in analyzing test results.  The results from each level of testing are analyzed to verify that the actual results match the expected results of the ATPs and to ensure that no other adverse side effects are being produced.  Problems are documented in discrepancy reports and entered into the corrective action system.  System test data, test results and test problem reports are recorded in a STFs or SDFs.  Test reports are written at the end of component acceptance testing and at the end of the GBTS integration testing.  The test reports summarize all results, including any deviations or waivers required because of test failures.  The report also lists all test failures and problems.

## 5.12  Preparing for Software Use (SOW 5.20.1.7.3)

Although the TIMS IPT is developing the TIMS software in three increments, due to complexity and cost of site activation, the TIMS software is not delivered until after the final TIMS CSCI/HWCI testing.  Subject to government approval, and following initial installation and testing at Randolph AFB, TX, the FlightSafety team intends to activate TIMS (hardware and software components) at each base in parallel.

### 5.12.1  Preparing the Executable Software

CM is responsible for preparing the executable software for all official deliveries.  The delivery also includes any batch files, command files, data files, or other files needed to install and operate the software on the GBTS computers.  The following configuration management procedures provide guidelines for preparation of the TIMS executable software products.

- LSIS900213A CMP 2-2-1  CM Numbering, Marking, Labels and Configuration Identifiers

- LSIS900213A CMP 2-3  Media Identification/Preparation

- LSIS900213A CMP 2-4  Computer Program Identification Number (CPIN) Preparation

- LSIS900213A CMP 3-1-2 Engineering Release System

FTD CM procedural requirements for preparing executable software for release are given in SEPP 7.00 Section 5.6.

### 5.12.2  Preparing Version Descriptions for User Sites

IPT CM is responsible for compiling  the Software Version Description (SVD) for each software component delivered to a user site.  The SVD information is documented in the SPS.  IPT SQA has the responsibility to perform an  independent product evaluation of the SVD and the software delivery to ensure that all files required for installation and operation are included.  The SVD contains the following information:

  - Detailed inventory of  the  materials being release, including:

    - identifying numbers, titles, abbreviations, dates, version numbers, and release numbers

    - all physical media, including listings, tapes, disks, etc.

    - associated documentation that make up the software version being released

    - applicable security and privacy considerations

    - safeguards for handling the delivery material

    - restrictions regarding duplication and license provisions

  - Detailed inventory of  software contents, including:

    - identifying numbers, titles, abbreviations, dates, version numbers, and release numbers

    - all computer files that make up the release

    - applicable security and privacy considerations

  - Changes, including a list of all changes since last version release

  - Site-unique information

  - Related documentation, not included in the release

  - Installation instructions

  - Possible problems or known errors

### 5.12.3  Preparing User Manuals

The TIMS IPT software includes on-line HELP as well as a hardcopy TIMS Software Users Manual (SUM) (DI-IPSC-81443, SDRL G020).  The TIMS software developers prepare the SUM in increments along with the code.  The on-line HELP feature and the SUM are internally peer reviewed and CM controlled prior to each incremental CSCI test.  The SUM is used and red-lined during the increment CSCI and increment CSCI/HWCI test activities.  During the next increment’s development, the software developers update the on-line HELP and SUM to fix any red-line comments and to add the next increment’s functional capability descriptions.  By building the SUM as the software development proceeds and using the on-line HELP and SUM during the test activities, the TIMS IPT develops a more accurate and useful document and help feature.  Prior to any official delivery of the SUM, SQA has the responsibility to conduct an independent product evaluation on the SUM.  For COTS products, the IPTs plan to use and deliver commercial manuals.

The ATDSS Software Users Manual (SUM) (DI-IPSC-81443, SDRL G020) will be delivered with the ATDSS development environment equipment and software.  The SUM is produced and assembled by the software developers, FTD Project Engineer and GBTS Software Engineer during the software development process.  The SUM is reviewed during the ATDSS PCA.

### 5.12.4  Installation at User Sites (SOW 5080.2-2.6)

Each IPT is responsible for coordinating their installation within the overall JPATS GBTS installation schedule.  Products include both the software as well as numerous hardware components.  The GBTS PMO identifies GBTS site installation personnel as early as possible in the GBTS development process.  The GBTS installation personnel support the JPATS GBTS Site Activation IPT, which includes hardware engineers, system engineers, software developers, the Government, contractor personnel, training and integration test personnel.  During early development, the JPATS GBTS Site Activation IPT performs site surveys and documents results in Site Evaluation Reports and Facilities Requirement Documents.

The JPATS GBTS Site Activation IPT coordinates the site delivery and, with the support of  IPT members, is responsible for GBTS installation, check out and training.  Before activation, the installation team will contract locally with building modification firms and inside- and outside-plant network contractors for facilities work identified and coordinated during Engineering & Manufacturing Development (EMD) site activation planning.  The TIMS IPT expects outside-plant network lines to be the long-lead facility change at most bases, requiring careful coordination with base civil engineering and the base communications squadron for buried cable installation and manhole systems integration.  The JPATS GBTS Support Site Activation Plan provides additional details about site installation of the GBTS.

The JPATS Courseware Development IPT is responsible for developing administrative courses for users of the TIMS system.  The TIMS IPT will provide the on-line HELP and SUM information, as well as any other necessary technical support needed to develop and deliver these training course.

## 5.13  Preparing for Software Transition (SOW 5020.1.3.3, 5080.2.1-2.6, SOW 5020.1.7.3)

The GBTS PMO and PST Software Process Manager are responsible for coordinating the GBTS product software transition within the overall JPATS GBTS schedule.  The GBTS PMO identifies GBTS software transition personnel as early as possible in the GBTS development process.  These personnel support the JPATS GBTS Site Activation IPT, which include hardware engineers, system engineers, software developers, the Government, contractor personnel, training and integration test personnel.

The IPTs maintain all software during the development and test program until acceptance of the GBTS by Raytheon and the Government and turnover of configuration management responsibility to the Contractor Logistics Support (CLS) IPT. A final product will be delivered to Raytheon which is free from patches and deficiencies is delivered.

During early development, the JPATS GBTS Site Activation IPT performs site surveys and documents results in Site Evaluation Reports and  Facilities Requirement Documents.  The JPATS GBTS Support Site Activation Plan and the Integrated Support Plan provide additional details about transition of the software to the Government maintenance facility.  The Modification and Update System (MUSS) is used to support maintenance for the operational system.  The MUSS contains the elements need to support the TIMS and ADT software.

The ADT Support System (ATD-SS) is the ATD software transition product.  ATD-SS is part of the MUSS system delivery and includes all elements required to support the operational ATDs.  including system administration functions, configuration management, and maintenance functions.  The current planning for ATD-SS has the FTD SEE and visual database generation systems being transitioned to the MUSS.

The TIMS Support System (TIMS-SS) is the TIMS software transition product.  TIMS-SS is part of the MUSS system delivery and includes all elements of the operational TIMS plus all of the software development environment including system administration functions, configuration management, and maintenance functions.  The current planning for TIMS-SS also has the TIMS SEE being transitioned to the MUSS.

### 5.13.1  Preparing the Executable Software

CM is responsible for preparing the executable software for all official deliveries.  The executable delivery also includes any batch files, command files, data files, or other files needed to install and operate the software on the TIMS distributed PC-network computers.  FTD CM uses the procedures outlined in the software CM plan.  TIMS CM uses LSI900213A procedure CMP 3-2-2 as a guideline for preparing the software for transition.

### 5.13.2  Preparing Source Files

CM is responsible for preparing the source files for all official deliveries.  The source delivery includes listings of any batch files, command files, data files, or other files needed to install and operate the software on the GBTS distributed PC-network computer.  The delivery also includes any other files necessary to support the regeneration of the executable software from the source.

### 5.13.3  Preparing Version Descriptions for the Support Site

CM is responsible for preparing the Software Version Description (SVD) for each GBTS delivery to a support site.  The SVD information is documented in the SPS.  QA has the responsibility to perform an independent product evaluation of the SVD and the software delivery to ensure that all files required for support site activities and operation are included.  Section 5.12.2 contains additional information about the contents of the SVD.

### 5.13.4  Preparing the “as-built” CSCI Design and Other Software Support Information

As part of the support site delivery, the IPT software developers are responsible for updating the final Software Product Specification (SPS) (DI-IPSC-814441,  SDRL G019) to reflect the “as-built” design and implementation.  SQA is responsible for conducting an independent product evaluation of the SPS prior to any official delivery.  During the design phases, the design information is documented in an appendix of the SPS.  The SPS undergoes peer reviews during the design and implementation phases.  The SPS is updated as each increment proceeds through the development process.  The IPTs use this approach to minimize documentation activities at the end of the program and to ensure a better and more useful product.  CM, test personnel, and SQA all have a responsibility to review these interim versions for accuracy and completeness.  The SPS design is baselined after the initial design phase; changes are controlled by the GBTS Change Control Board (CCB).  The SPS implementation data is baselined after the final formal GBTS CSCI testing.  The GBTS CCB is responsible for evaluating changes that result from defects discovered and fixed as part of the final formal GBTS CSCI/HWCI testing or the formal GBTS System test.  The GBTS CCB, as part of closing a problem report, examines all changes and  ensures that all appropriate documentation updates have also been completed.

### 5.13.5  Updating the System Design Description

Prior to delivery to the support site, the TIMS IPT has the responsibility to ensure that final TIMS System/Subsystem Design Description document is updated to reflect the “as-built” configuration of the CSCI.  The TIMS SSDD is baselined after the SDR; however, throughout the subsequent TIMS development life-cycle, TIMS system engineers and software engineers are responsible for ensuring that this document is kept up-to-date and accurately reflects changes that inevitably occur during a development.  FTD software engineers are responsible for ensuring the PUSD documents are kept up-to-date and accurately reflects changes that occur during development.  Corrections to the documentation are tracked as part of the change control process.

### 5.13.6  Preparing Support Manuals

The GBTS PMO has no plans for any other support manuals, other than the on-line HELP features of TIMS and the SUM described in section 5.12.3.  MUSS operations information is documented in an appendix of the SUM.  The SUM includes COTS product user and support manuals.

### 5.13.7  Transition to the Designated Support Site

Long range plans call for most of the IPT members to gradually transition to the maintenance CLS IPT at the MUSS support site(s).  The developers will become the maintainers.  This approach provides a smooth approach to the software transition and eliminates the need for training new personnel.  After all software and files are transitioned to the maintenance site the maintenance team demonstrates that the deliverable software can be regenerated and maintained.  The Integrated Support Plan contains additional details about the transition of GBTS.

## 5.14  Software Configuration Management (SOW 5020.2.5)

The GBTS  Configuration Management Process Manager (CMPM) will bear primary responsibility for all CM issues, be the focal point for RAC/Government interfaces to the GBTS PMO for CM issues, and will establish, implement, and maintain a Software Configuration Management Plan (SCMP) using MIL-STD-498, paragraphs 5.14 and its subparagraphs, as a guide.  The SCMP is an appendix to the GBTS Configuration Management Plan (CMP).  The SCMP includes the approach to maintaining configuration control of items built by subcontractors and the interface control process.  (Separate planning documents will be used for Logicon and FlightSafety.)

The configuration management organization, consisting of the CMPM and CM personnel within each IPT, is responsible for establishing and maintaining configuration identification, control, and status accounting for the software releases and associated products, including fielded releases and releases under development.  CM has the responsibility to coordinate and perform the following tasks:

- establish documented CM procedures and standards

- maintain a history of software and their changes

- maintain all versions of released software and supporting documentation

- verify that authorized changes are properly identified, defined, processed, and approved

- set-up and maintain the SDL

- control and secure all masters (media, documentation, and software)

- control access of masters to authorized individuals

- establish and maintain status accounting needs and issue periodic status accounting reports

- distribute software and its associated documentation

- make necessary copies of the software, documents, and media

- participate in QA audits of CM and maintain historical records

- support the change control process with media tracking, status accounting, and maintaining the problem report/change request database.

The GBTS configuration management plan delivered as part of the contract award process controls all configuration management activities.  Requirements of this plan are flowed down to all software components address in this SDP.

FTD CM functions are invoked by FlightSafety SEPP 7.00.  The FTD IPT uses the SEPP 7.00 CM procedures listed in Table 5.14-1 as guidelines for the generation of a project-unique Software Configuration Management Plan (SCMP)

| SEPP 7.00 Section | Title |
| --- | --- |
| 5.1 | Software CM Planning |
| 5.2 | Software Identification |
| 5.3 | Software Configuration Control |
| 5.4 | Software Configuration Status Accounting |
| 5.5 | Software Configuration Audits |
| 5.6 | Software Release Procedures |

TABLE 5.14-1  FTD Configuration Management Procedures

The TIMS CM function is mandated by LEIB Practice 9.51 and LEIB Software Engineering Directive SED- 012.  The TIMS CM group uses the Logicon configuration management procedures listed in Table 5.14-2 as guidelines for TIMS product development.  As part of the initial planning for TIMS, CM in coordination with the TIMS IPT Leader, tailors these configuration management procedures to reflect specific TIMS contract requirements.  The tailored procedures then become part of the TIMS project instruction binder.

| LSIS900213A CM Procedure No. | Title |
| --- | --- |
| Planning |  |
| CMP 1-1-1 | Software CM Planning |
| CMP 1-1-2 | Hardware CM Planning |
| CMP 1-2 | Reviews and Audits of the CM Program |
| Identification |  |
| CMP 2-2-1 | CM Numbering, Marking, Labels, and Configuration Identifiers |
| CMP 2-3 | Media Identification/Preparation |
| CMP 2-4 | Computer Program Identification Number (CPIN) Preparation |
| Configuration Control |  |
| CMP 3-1-2 | Engineering Release System |
| CMP 3-2 | Software Change Control Process |
| CMP 3-2-1 | Quick Fix Processing |
| CMP 3-2-2 | Code Baseline Certification |
| CMP 3-3 | Preparation/Evaluation of Engineering Change Proposals |
| CMP 3-3-1 | ACSN, SCN, and NOR Preparation |

TABLE 5.14-2  TIMS Configuration Management Procedures

| LSIS900213A CM Procedure No. | Title |
| --- | --- |
| Configuration Control (Continued) |  |
| CMP 3-4 | Establish and Maintain Software Development Library (SDL) |
| CMP 3-4-1 | Preparation/Evaluation of Formal Deviations/Waivers |
| CMP 3-5 | Interface Control Process |
| Status Accounting |  |
| CMP 4-1 | Baseline Configuration Status Accounting |
| CMP 4-2 | Internal Control CSA |
| CMP 4-3 | Tools Configuration Status Accounting |
| Audits |  |
| CMP 5-1 | Preparation for and Conduct of Formal Configuration Audits |
| Miscellaneous |  |
| CMP 6-2-1 | Archive Process |

TABLE 5.14-2  TIMS Configuration Management Procedures (Continued)

### 5.14.1  Configuration Identification (SOW 5020.1.7-1.7.3)

The CM organization uses configuration identification to provide systematic development, identification, and baselining of the specifications and products required for a complete technical description of the software.  The GBTS configuration identification conforms to MIL-STD-973 paragraphs 4.4, 5.3.1, 5.3.2, and 5.3.4.1.  The software configuration consists of the software code, databases, data files, data, procedures, and associated documentation for the formal and developmental configuration baselines.  Section 5.14.1.1 describes the formal baselines; Section 5.14.1.2 describes the developmental baselines.  The TIMS CM organization uses Logicon LSIS900213A procedures CMPs , 2-2-1, 2-3, and 2-4 as guidelines for identifying software product configuration baselines.

CM identifies each CSCI release by a unique identification number IAW MIL-STD-973 paragraph 5.3.6.1.3.  Specification numbers provided by the Government are used exactly.  When the Government does not provide specification numbers, the specification and document numbering are defined by MIL-STD-973 for the FTD and by LSIS900213A procedure CMP 2-2-1 for the TIMS.  CM uses the configuration status accounting process to formally track and identify specification releases and revisions.  Configuration status accounting reports list the names and numbers for all items in the current configuration and summarize the interrelationship between related baseline items.  Specification revisions are identified with the basic number and a revision letter starting with "A." Between major revisions, specification versions are identified by the previous revision and approved specification change notices.  Status accounting reports list all change requests, along with dispositions and status for each baselined specification.

Table 5.14.1-1 provides a list of the minimum documentation for each baseline.

| Baseline | JPATS GBTS SOW Reference | Software Related Documents |
| --- | --- | --- |
| Functional | 5020.1.7.1 | System Specification |
| Allocated | 5020.1.7.2 | PUSD Development Specifications for: TIMS, FTD, MUSS, and CBTS. SSDD for: TIMS and FTD. SRS for: TIMS and FTD. IRS for: TIMS |
| Product | 5020.1.7.3 | SPS (including SDD, SVD) for: FTD, TIMS, MUSS, and CBTS. SUM for: FTD, TIMS, MUSS, CBTS. |

TABLE 5.14.1-1  GBTS Configuration Baseline Documentation

#### 5.14.1.1  Formal Configuration Identification

Formal software baselines consist of the functional, allocated, and product baselines.  They are established upon receipt of approval from RAC.  Changes to an approved formal baseline are processed through the GBTS PMO CCB with an engineering change request (ECR), discrepancy report, or a software change request (SCR) as the initiating document, with the formal request to RAC being documented in an ECP (SOW 5020.2.5.1).The functional baseline is established with the approval of the JPATS GBTS system specification (contract award)PUSD.  The allocated baseline is established with the approval of PUSD development specifications, the Software Requirements Specification and Interface Requirement Specifications.  The software product baseline is established after the approval by RAC and the Government of the respective final Software Product Specifications and User’s Manuals.

#### 5.14.1.2  Developmental Configuration Identification

FSI and Logicon use a three-level configuration control process to support the orderly progression of GBTS software development.  This approach provides appropriate internal control on the software products, and sufficient visibility into and authority over the proposed changes for Raytheon and the Government.  Table 5.14.1-2  identifies the items to be placed under CM control, the level of control, the major activities in the life cycle during which the item is placed under control, and the approval required.  Level 1 control provides the ability to retrieve an earlier version of a document or software without the burden of reviewing and approving the changes.  It is applicable to internal baselines for which management visibility is not required for changes.  The Level 2 control is the essence of the change process documented in LSIS900213A procedure CMP 3-2 and the FSI SCMP.  Changes are documented on the SCR form and must be approved by the GBTS Configuration Control Board (CCB) prior to implementation.  For baselines that are under level 3 control, Government review and approval is required.  This additional Government sign-off is added to ensure that the Government is kept abreast of the progression of the baselines and to provide incremental review of the baseline items.

| SDP, Section 5.14.2 describes the change process. Baseline Item | Level of Control | Life Cycle Activity During which Control Starts | Criteria for Start of Control |
| --- | --- | --- | --- |
| Software Development Plan (SDRL G018) | 2 | Final with proposal | Contract Award |
| Engineering Incremental Builds | 1 | Unit integration and testing | Verification of build functionality |
| Releases | 2 | Issuance of release certification | Verification of functionality |
| System Specification (SS) | 1 | Final with proposal | Contract Award |
| Program Unique Specification Document (PUSD): Development Specifications (SDRL G030) - All except FTD | 1 2 3 3 3 | Draft delivered with proposal, draft update due 45 days prior to GBTS SDR, and 45 days prior to component PDR. Final due 45 days before component PDR Final update, 20 days after receipt of Raytheon/Government comments at CDR Updates to final 75 days before PCA PCA comments 20 days after receipt | Raytheon/Government approval |
| PUSD: Development Specification for FTD (SDRL G030) | 3 | Final with proposal Updates to final 75 days before PCA PCA comments 20 days after receipt | Contract Award Raytheon/Government Approval |
| TIMS System/Segment Design Document | 1 2 | Draft available 5 days prior to TIMS SDR, updates 5 days prior to PDR. Final available at CDR | Non deliverable, available as part of GBTS data repository |
| TIMS and FTD Software Requirements Specification | 1 2 | Draft available 5 days prior to SSR Final (incorporating government comments) at PDR | Non deliverable, available as part of GBTS data repository |
| TIMS Interface Requirements Specification (SDRL G037) | 1 2 | Draft 30 days prior to SSR Final 45 days prior to PDR | Delivery of SDRL Delivery of SDRL |
| Test Plans/Test Procedures (SDRL G027 & G028) | 1 2 3 | draft plan 45 days prior to component PDR draft procedures 60 days prior to GBTS in-plant testing Final procedures 30 days prior to GBTS on-site testing | Delivery of SDRL(s) Delivery of SDRL(s) |
|  | 3 | Final Test Plan 30 days prior to CDR |  |
| Test/Inspection Reports | 1 | 30 days after test completion | Delivery of report |
| Software Test Plan (SDRL G035) | 1 2 | Draft plan 45 days prior to PDR Final Test Plan 30 days prior to CDR | Delivery of SDRL(s) Delivery of SDRL(s) |
| TIMS Software Test Description (SDRL G036) | 1 2 | Draft plan 45 days prior to CDR Final STD 30 days prior to Test Readiness Review | Delivery of SDRL(s) Delivery of SDRL(s) |
| Software Product Specification (SDRL G019) | 1 2 3 | Internal drafts available before PDR, CDR, internal incremental CSCI testing Component preliminary 15 days prior to Component PCA Component final 30 following notification of successful PCA | not delivered, available as part of GBTS data repository Delivery of SDRL |
| Software Users Manual (SDRL G020) | 1 2 3 | Internal drafts available before incremental CSCI testing Component drafts available 30 days prior to Component PCA 30 days before TRR Component final following notification of successful PCA | not delivered, available as part of GBTS data repository Delivery of SDRL |

TABLE 5.14.1-2  Identification of Developmental Configuration Baselines

### 5.14.2  Configuration Control

Configuration control of developmental software is the responsibility of the affected Training System IPTs and is exercised through configuration status accounting tasks and configuration audits performed by the Training System IPT’s software development teams under the direction of the Software Configuration Manager.  Within each of the Training System IPTs, an internal Software Development CCB is established to address informal changes and problems encountered during the software development process.  Membership of the Training System IPT CCBs consists of the IPT Leader, the lead software engineer, and the Software Configuration Manager.  The Training System IPT CCBs are responsible for:

- evaluating change request and determining disposition (approve/reject/hold)

- determining the change priority and defect type

- task assignment

- evaluating schedule impacts and priorities

- evaluating feasibility

- evaluating interface impacts

The IPT CCBs approve all formal deliverables.  Each IPT conducts internal peer reviews before each delivery; and SQA is responsible for doing independent evaluations before each deliverable.  Once products are baselined, the GBTS CCB must approve all changes.  As with hardware CM activities, all Class I changes are considered first by the GBTS CCB, and if approved, are forwarded to the Raytheon  joint CCB for final approval.

The Training System IPTs and their CCBs, while exercising autonomous responsibility for configuration management of their respective products, are responsible to the Program Manager and the GBTS CCB (Figure 5.14.2-1) for conducting periodic technical and management reviews IAW MIL-STD-1521 and MIL-STD-973.

| CORE MEMBERSHIP | ASSOCIATE MEMBERSHIP |
| --- | --- |
| GBTS Program Manager (Chairman) | Raytheon GBTS Project Manager |
| Configuration Manager (Vice Chairman) | Subcontractor Configuration Managers: |
| Systems Engineer | FSI/Simulation Systems Division |
| Logistics IPTs Leaders | Logicon, Inc. |
| HQ AETC MUSS Manager | Apex |
| CNATRA MUSS Manager |  |

FIGURE 5.14.2-1  GBTS CCB Membership

The GBTS Configuration Manager (Vice Chairman of the GBTS CCB) has oversight responsibility for configuration control of the developmental software and exercises this responsibility through the Software Configuration Managers assigned to each IPT.  The Software Configuration Managers are members of the Training System IPT CCBs and report directly to the GBTS Configuration Manager on matters relating to configuration control of developmental software.

Both FTD and TIMS have established guidelines for handling releases and change control as stated in the following two sections.

#### 5.14.2.1  TIMS Configuration Control

The TIMS configuration control process supports software development activities and software support activities.  TIMS CM uses the following Logicon procedures from LSIS900213A for guidelines to the configuration control process:

- CMP 3-1-2 describes the engineering release system

- CMP 3-2, CMP 3-2-1, and CMP 3-2-2 define the program software change control process

- CMP 3-2-1 defines the quick fix, emergency change request process

#### 5.14.2.2  FTD Configuration Control

The FTD configuration control process supports FTD software development activities and software support activities.  FTD CM uses the following FlightSafety procedures from SEPP 7.00 for guidelines to the configuration control process:

- Section 5.6 describes the software release system

- Section 5.3 defines the program software change control process

### 5.14.3  Configuration Status Accounting

CM is responsible for periodic configuration status accounting activities.  CM uses identification data and change control records to capture and report the configuration status of the designed, developed, and delivered software and products.  TIMS CM uses the LSIS900213 procedures CMP 4-2, and CMP 4-3 as guidelines for performing configuration status accounting.

At the beginning of development, CM in conjunction with the IPT Leader defines a database that captures all the required data elements, and defines a set of reports to automated and summarize the system configuration baseline status, the status of the change requests, and related revision records for both the developmental configuration and the formal configuration baselines.  The CCB reviews and approves the contents and format of the reports.  CM is responsible for updating the database after each CCB meeting and after the receipt of dispositions or directions on change documents from the Raytheon or FlightSafety Subcontracts Managers.

Configuration status accounting reports include the status of documents, specifications, software units, databases, data files, data and procedures comprising a software release and their associated products, and the authorized changes for each item.  For each baseline, the reports show the date and status (such as opened, in work, approved, disapproved, closed) of all change requests on the baseline.  For approved change requests, the status report also shows the version number of the document or software containing the updates.

### 5.14.4  Configuration Audits

Configuration audits consist of formal and informal Functional Configuration Audits (FCAs) and Physical Configuration Audits (PCAs).  The CM organization is responsible for preparing and conducting the audits, with participation by other key software and system engineering personnel.  Informal audits are conducted during CSCI qualification test.  Formal audits are conducted at the end of System Acceptance Testing.  The audits are compliant with MIL-STD-973, paragraph 5.6, and follow the guidelines in FSI SEPP 7.00, Section 5.5 (FTDs)  and LSIS900213, CMP 5-1 (TIMS).

The functional configuration audits are completed when a complete assessment of the system and/or software’s actual performance against the release/build’s requirements is accomplished and approved.  The configuration analyst verifies that all required change requests are closed, all remaining problems are identified and documented, and all applicable SDRL deliveries have been made.  The physical configuration audits are completed with the verification that the system and/or software is reflected in associated documentation.  This is accomplished through a detailed audit of the hardware and software products, including drawings, related software media, software specifications, version description documents, technical data, and test documentation.

### 5.14.5  Packaging, Storage, Handling, and Delivery

CM retains master copies of software media and documentation (both hard and soft copy) in the SDL (see Section 5.2.3).  Backup media and documentation are retained in separate areas (usually off-site) in accordance with SDL procedures.  Master and backup copies are maintained for the duration of the program.

CM uses protective covering (e.g., tape straps, diskette holder, etc.) during transportation to safeguard media delivered from one site to another.  Prior to transport, data is appropriately marked and protected.  Software media and documentation are delivered to the customer in accordance with SDRL instructions and the JPATS GBTS security procedures.

## 5.15  Software Product Evaluation (5020.1.4.2)

Assurance of a quality product is a team effort.  The IPTs have fully integrated independent software product evaluations into its program.  Evaluations are conducted by individuals, peer review groups, during informal meetings, during inspections, and during formal reviews.  Evaluation inputs are collected from technical leads, other developers, test personnel, QA, and Raytheon personnel and the Government.  Evaluation inputs may also be collected from other internal technical experts or outside consultants.

### 5.15.1  In-Process and Final Software Product Evaluations

The IPT teams conduct in-process evaluations throughout the software development life-cycle.  In addition, management and QA perform evaluation on each product before it is delivered.  SQA follows the guidelines in LSIS890297 procedure QAP 2-13 (Logicon - TIMS) and QAM-1000 procedure Q-3000 (FlightSafety - FTDs) for product evaluations and uses checklists to evaluate deliverable documents prior to each official delivery (see Tables 5.15.1-1 and -2).  The SQA checklists associated with document product evaluations evaluate compliance, at a minimum, with the following criteria:

- Compliance with contractual and contractor requirements and applicable data item descriptions (DIDs) criteria.

- Internal consistency:  No two statements in a document contradict one another, a given term means the same throughout, a given item or concept is referred to by the same name or description throughout.

- Understandability:  Documentation promotes understanding by applying the rules of grammar, symbols, notation and writing style.

- Technical adequacy:  The approach is logical and consistent, and requirements of the program are clear technically and practically.

- Degree of completeness appropriate to the phase:  Constituent parts are present and addressed in adequate detail.  In process reviews evaluate products at varying degrees of completeness.

- Testability:  Documentation identifies requirements that are testable so that an objective test can be designed to verify and validate the requirements.

- Traceability:  All specifications, design documentation, code, test plans/procedures are reviewed to provide agreement with all predecessor documents to which a hierarchical relationship is required.

Table 5.15.1-3 contains a summary of the evaluation criteria for IPT products (documentation, code, design, testing, etc.)  Except for SDF audits and reviews, the product evaluations are event driven and are triggered by a delivery of the product.  At the beginning of the design phase, SQA builds an SDF sampling schedule and does periodic sampling of SDF files during the software design, implementation, and unit integration phases.  The intent is that every SDF is reviewed at least once during software development.

| QAM-1000 Checklist Identifier Number | Checklist Title |
| --- | --- |
| Q-4010 | Document Review (general checklist applicable for any document) |
| Q-8020 | Software Requirements Specification (SRS) Review |
| Q-8020 | Interface Requirements Specification (IRS) Review |
| S-8030 | Preliminary Design Checklist |
| S-8040 | Detailed Design Checklist |
| S-8010 | Software Test Plan (STP) Review |
| S-8010 | Software Test Description (STD) Review |
| S-8010 | Software Test Report (STR) Review |
| Q-4010 | Software Product Specification (SPS) Review |
| Q-4010 | Software Version Description (SVD) Review |
| Q-4010 | Software User’s Manual (SUM) Review |

TABLE 5.15.1-1  FlightSafety QA Product Evaluation Checklists (used on FTD products)

| LSIS890297 QAP checklist identifier number | Checklist Title |
| --- | --- |
| 2-13.1(2.0) | Document Review (general checklist applicable for any document) |
| 2-13.27(2.0) | System/Segment Design Document (SSDD) Review |
| 2-13.28(2.0) | Software Requirements Specification (SRS) Review |
| 2-13.29(2.0) | Interface Requirements Specification (IRS) Review |
| 2-13.33(2.0) | Software Test Plan (STP) Review |
| 2-13.34(2.0) | Software Test Description (STD) Review |
| 2-13.35(2.0) | Software Test Report (STR) Review |
| 2-13.36(2.0) | Software Product Specification (SPS) Review |
| 2-13.37(2.0) | Software Version Description (SVD) Review |
| 2-13.38(2.0) | Software User’s Manual (SUM) Review |

TABLE 5.15.1-2  Logicon QA Product Evaluation Checklists (used on TIMS products)

| Software Product (SDP paragraph reference) | Evaluation Criteria |
| --- | --- |
| Software Development Plan (5.1.1) | Contains all applicable information in SDP DID Meets SOW, if applicable Meets SDRL G018 Understandable Internally consistent and consistent with other project plans Contains updates as needed Covers all activities/deliverables in SOW and SDRL Presents a sound approach to the development |
| Software Test Plan (5.1.2, 5.1.3) | Contains all applicable information in STP DID Meets SOW, if applicable Meets SDRL G035 Understandable Internally consistent and consistent with other project plans Follows SW development plan Covers all activities/deliverables in SOW and SDRL Covers all requirements for the items under test Presents a sound approach to the testing |
| Support Site Activation Plan (5.1.4, 5.1.5) | Contains all applicable information in applicable DID Meets SOW, if applicable Meets SDRL G013 Understandable Internally consistent and consistent with other project plans Follows SW development plan Covers all user site installation activities in SOW Presents a sound approach to the installation |
| System Specification & Prime Item Development Specifications (5.3.2, 5.3.3) | Contains all applicable information in applicable DID Meets SOW, if applicable Meets SDRL G030 Understandable Internally consistent Follows SW development plan Feasible Testable Covers the operational concept |
| TIMS System/Subsystem Design Specification (5.4.1, 5.4.2) | Meets SOW, if applicable Understandable Internally consistent Follows SW development plan Consistent with system requirements Consistent with system-wide design decisions Feasible |

TABLE 5.15.1-3  Software Products and Associated Evaluation Criteria

| Software Product (SDP paragraph reference) | Evaluation Criteria |
| --- | --- |
| Software Requirement Specification and TIMS Interface Requirements Specifications (5.3.3, 5.5) | IRS contains all applicable information in IRS DID Meets SOW, if applicable IRS Meets SDRL G037 Understandable Internally consistent Follows SW development plan Covers system requirements allocated to the CSCI Feasible Testable |
| Software Design and Interface Design (5.6.1, 5.6.2, 5.6.3) | Documented in SPS (design appendix). Contains all applicable information in SPS DIDs Meets SOW, if applicable Meets SDRL G019 Understandable Internally consistent Follows SW development plan Consistent with CSCI requirements Consistent with CSCI-wide design decisions Covers CSCI requirements allocated to each unit Feasible |
| Implemented software (code) (5.7.1) | Meets SOW, if applicable Meets SDRL, if applicable Understandable Internally consistent Follows SW development plan Covers CSCI detailed design |
| TIMS CSCI qualification test descriptions (5.9.3) | Contains all applicable information in STD DIDs Meets SOW, if applicable Meets SDRL G036 Understandable Internally consistent Follows SW development plan Covers all CSCI requirements |
| CSCI qualification test results (5.9.7) | Meets SOW, if applicable Understandable Internally consistent Follows SW development plan Covers all planned CSCI qualification test cases Shows evidence that the CSCI meets its SRS and IRS requirements |
| TIMS System qualification test descriptions (5.11.3) | Contains all applicable information in STD DIDs Meets SOW, if applicable Meets SDRL G036 Understandable Internally consistent Follows SW development plan Covers all system requirements |

TABLE 5.15.1-3  Software Products and Associated Evaluation Criteria (Continued)

| Software Product (SDP paragraph reference) | Evaluation Criteria |
| --- | --- |
| System qualification test results (5.11.7) | Meets SOW, if applicable Understandable Internally consistent Follows SW development plan Covers all planned system qualification test cases Shows evidence that the system meets its SS and PUSD requirements |
| Executable software (5.12.1, 5.13.1) | Meets SOW, if applicable Meets SDRL, if applicable Understandable Internally consistent Follows SW development plan Meets delivery requirements All software necessary for execution is present Version exactly matches version that passed testing Delivery media accurately labeled |
| Software version descriptions (5.12.2, 5.13.3) | Documented in SPS; contains all applicable information in SPS DID Meets SOW, if applicable Meets SDRL G019 Understandable Internally consistent Follows SW development plan Accurately identifies the version of each software component (file, unit, CSCI, etc.) delivered Accurately identifies the changes incorporated in the version |
| Software user manuals (5.12.3.1) | Contains all applicable information in SUM DID Meets SOW, if applicable Meets SDRL G020 Understandable Internally consistent Follows SW development plan Accurately describes software installation and use to the intended audience of this manual |

TABLE 5.15.1-3  Software Products and Associated Evaluation Criteria (Continued)

| Software Product (SDP paragraph reference) | Evaluation Criteria |
| --- | --- |
| Source files (5.13.2) | Contains all applicable information in SPS DID Meets SOW, if applicable Meets SDRL G019 Understandable Internally consistent Follows SW development plan Meets delivery requirements All required software is present Version exactly matches version that passed testing Delivery media accurately labeled |
| Software Product Specification (“As built” CSCI design and related information ) (5.13.4) | Contains all applicable information in SPS DID Meets SOW, if applicable Meets SDRL G019 Understandable Internally consistent Follows SW development plan Accurately describes the “as build” design of the CSCI Accurately describes the compilation/build procedures Accurately describes modification procedures Source files cover all units in the CSCI design Measured resource utilization meets CSCI requirements |
| TIMS System/Subsystem Design Description (“As built” System design) (5.13.5) | Contains all applicable information in SSDD DID Meets SOW, if applicable Meets SDRL, if applicable Understandable Internally consistent Follows SW development plan Accurately describes the “as build” system design |
| Sampling of software development files and test folders (5.7.2, 5.7.3, 5.8.1, 5.8.4, 5.9.4, 5.10.1, 5.10.4, 5.11.4) | Meets SOW, if applicable Understandable Internally consistent Follows SW development plan Contents are current with the ongoing effort Adequate unit test cases/procedures/data/results Adequate unit integration test cases/procedures/data/results Adequate CSCI qualification dry run results Adequate CSCI/HWCI integration test cases/procedures/data/results Adequate system qualification dry runt results |

TABLE 5.15.1-3  Software Products and Associated Evaluation Criteria (Continued)

### 5.15.2  Software Product Evaluation Records, Including Items to be Recorded

SQA maintains records from evaluations (including meeting minutes, completed checklists, action items, SQA Quality Evaluation Records (QERs), DRs, etc.) to provide objective evidence that the evaluations were conducted.  SQA attaches QA checklists to the QER, which summarizes the evaluation results and lists any action items as a result of the review.

### 5.15.3  Independence in Software Product Evaluation

The IPT product evaluation activities are structured to provide independent evaluations of all deliverable software products.  Formal reviews, technical interchange meetings, and peer reviews always have product reviewers that are independent of the individuals responsible for developing the product.  For instance, test personnel are responsible for reviewing requirements and developers are responsible for reviewing test documents.  In addition, SQA personnel, who are independent of all software development and software test, have the responsibility to all review all software products and updates.

## 5.16  Software Quality Assurance (SOW 5020.1.4.2)

Responsibility for the quality of all GBTS software lies with the GBTS PST Software Process Manager (SPM).  Responsibility for verifying the quality of all GBTS software lies with the GBTS PST Quality Assurance Process Manager (QAPM).  Implementation of software quality occurs within the IPTs, who also maintain IPT-internal software quality verification programs.  The SPM ensures that IPTs follow this SDP and the IPT-internal standards and procedures referenced herein.  Both the SPM and QAPM review test plans and procedures and formal baseline software products; monitor monthly IPT progress/status reports; and participate in IPT level reviews, walk-throughs and testing events on an as desired or as required basis.  The QAPM works closely with, or is a member of, test teams conducting formal development and acceptance testing activities.  Process managers and IPT personnel also interact on an informal basis to resolve potential quality problems at the earliest possible time.

FTD SQA functions are mandated by QAM-1000 and set forth in SEPP-1000 .  The TIMS SQA functions are mandated by the LEIB Software Engineering Directive SED-011 and are set forth in Logicon’s Quality Assurance Procedures (QAPs).

SQA is an important contributor to the overall software development process.  The purpose of Software Quality Assurance is to provide management with appropriate visibility into the products being built and into the process being used by the software project.  SQA works with the software project during its early stages to establish plans, standards, and procedures that will add value to the software project and satisfy the constraints of the project and the organization's policies.  By participating in establishing the plans, standards, and procedures, SQA helps ensure they fit the project's needs and verifies that they will be usable for performing reviews and audits throughout the software life cycle.

During development, SQA tracks, evaluates and suggests improvements for development performance.  SQA also ensures that established policies, procedures, methods, and standards are followed, and provides independent status to the IPT Leaders and other management.  Throughout the entire life-cycle, SQA uses proven corporate policies, procedures, and practices for it methodology (reference Tables 5.16-1 - FTDs, and 5.16-2 - TIMS).  SQA participates in formal reviews and internal peer reviews for system requirements, system design, software requirements, software design, code, unit testing, and integration testing.  During CSCI testing, CSCI/HWCI testing and System testing, SQA is responsible for monitoring all formal testing and collecting, bonding and certifying the formal test results.

SQA addresses compliance issues first within the IPT and attempts to resolve any problems at the IPT level if possible.  For issues not resolvable within the IPT,  SQA escalates the issue to an appropriate level of management for resolution.

| QAM-1000 Identifier | Application Schedule | Title |
| --- | --- | --- |
| S-1000 | @ SDP delivery | Software Management & Engineering Practices |
| Q-3515 | Prior to Placement of PMO | Quality Survey of Candidate Supplier |
| Q-3520 | Prior to Award of Subcontracts | Quality Survey of Candidate Supplier or Subcontractor |
| S-1510 | Monthly | Software Development Library Audit |
| S-3000 | Quarterly | Software Environment Audit Procedures |
| S-3010 | Quarterly | Version Control Audit |
| S-4010 | Prior to HSI, ATP & PCA | Software Code and Software Development Files Certification |
| S-8020 | Prior to SRR | Software requirements Audit |
| S-8030 | Prior to SW PDR | Software Preliminary Design Audit |
| S-8040 | Prior to SW CDR | Software Detail Design Audit |
| S-8010 | @ STP, DTP & ATP deliveries | Review of Software Test Documents |
| H-6000 | @ SW baseline promotions | Inspection and Testing |

TABLE 5.16-1  FTD SQA Procedures

| LSIS890297 QAP Identifier | Application Schedule | QAP Title |
| --- | --- | --- |
| QAP 1-1 | Document delivery | Evaluate the Software Development Plan (SDP) |
| QAP 1-5-1 | Semi-annual | Evaluate Software Configuration Management: Configuration Identification Process |
| QAP 1-5-2 | Semi-annual | Evaluate Software Configuration Management: Configuration Control |
| QAP 1-5-3 | Semi-annual | Evaluate Software Configuration Management: Configuration Status Accounting/Reporting |
| QAP 1-6 |  | Software Quality Planning |
| QAP 1-7 | Quarterly | Management Review of the Software Quality Program |
| QAP 2-1 | Semi-annual | Evaluate Software Development Library (SDL) |
| QAP 2-2 | 30 days after submission of SDP, then once every major activity cycle (req. analysis, design, etc) | Evaluate Risk Management |
| QAP 2-3 | Bi-monthly during req. analysis | Evaluate Software Requirements Analysis Activities and Products |
| QAP 2-4 | Bi-monthly during design | Evaluate Preliminary Design Activities and Products |
| QAP 2-5-2 | Event driven by changes | Evaluate Updated Code and Design Documentation |
| QAP 2-6 | Bi-monthly during design | Evaluate Detailed Design Activities and Products |
| QAP 2-7-1 | Once per phase | Software Development Files |

TABLE 5.16-2  TIMS SQA Procedures

| QAM-1000 Identifier | Application Schedule | Title |
| --- | --- | --- |
| QAP 2-7-2 | According to SDF audit schedule. Schedule due at start of design phase | SDF Audit |
| QAP 2-8 | Bi-monthly during coding and unit testing | Evaluate Coding and CSU Testing Activities and Products |
| QAP 2-9 | Bi-monthly during unit integration & test | Evaluate CSC Integration and Testing Activities and Products |
| QAP 2-11 | Bi-monthly during CSCI testing | Evaluate CSCI Testing Activities and Products |
| QAP 2-12 | Continuous during formal testing | Formal Test Monitoring |
| QAP 2-13 | Event driven by document deliveries | Document Review (see Table 5.15.1-2 for list of checklists) |
| QAP 2-14 | Event driven | Milestone Review and Audits Preparations |
| QAP 2-17 | Bi-monthly during CSCI/HWCI and System testing activities | Evaluate System Integration and Testing Activities and Products |
| QAP 2-19 | Bi-monthly during system requirements analysis and design | Evaluate System Requirements Analysis/Design Activities and Products |
| QAP 3-1 | Continuous, monthly trend analysis reports | Implement Corrective Action System |
| QAP 3-2 | Quarterly | Evaluate Corrective Action System |
| QAP 3-3 | Event driven | Quality Evaluation Records |
| QAP 4-1 | Event driven | Evaluate Documentation and Media Distribution |
| QAP 4-2 | Event driven | Evaluate Storage, Handling, and Delivery |
| QAP 5-1 | Quarterly | Evaluate Non-Deliverable Software |
| QAP 7-1 | Quarterly | Evaluate Non-Developmental Software |
| QAP 8-1 | Quarterly starting at 4 months into contract | Evaluate Interface with Software IV&V Contractor |
| QAP 10-1 | Quarterly | Evaluate Deliverable Elements of the Software Engineering and Test Environments |

TABLE 5.16-2  TIMS SQA Procedures (Continued)

### 5.16.1  Software Quality Assurance Evaluations

SQA performs process evaluations to ensure that the software development processes, as defined in the SDP and SEMP, are carried out.  Process evaluations may be conducted on a scheduled basis or through event participation.  Examples of SQA process evaluations include evaluations of the software requirements analysis activities, evaluations of the software design activities, evaluations of the code and unit test activities, etc.  A summary of the results of each evaluation are documented on QERs and submitted to the IPT Leader and FSI and Logicon management organizations.

SQA performs event driven product evaluations to ensure the quality of the products, both deliverable and non-deliverable.  Checklists are usually used to perform evaluations of software plans, standards, procedures, and technical documentation (see SDP, Section 5.15.1 for further details about product evaluations).

SQA performs periodic process evaluations of the CM system to ensure:

- Only approved changes are implemented.

- Each software problem is categorized.

- Analysis is performed on software changes requests to identify trends.

- Approved changes are verified for resolution and implementation without introducing new problems.

- There is objective evidence, prior to use, that non-developmental software meets requirements.

- Data rights are followed.

SQA does periodic process evaluations of the SDL to assure that:

- The environment is controlled to minimize degradation of the physical media.

- There are regularly scheduled backups of all media.

- There are adequate provisions for disaster recover.

- Controls are exercised on the internal distribution of media and documents.

- Only authorized access to software is allowed.

- The build process is controlled and repeatable.

SQA evaluates the developer unit testing, and the CSC and CSCI integration testing to ensure satisfactory completion of the requirements and readiness for qualification testing.  SQA performs SDF audits.  SQA participates in software qualification/ acceptance test activities from the beginning of the program.  As a major player in the CSCI qualification test process, QA performs the following activities.

- Review the development of requirements acceptance criteria.

- Review each version of acceptance test plans.

- Review test procedures to ensure they are complete and that they adequately test each requirement.

- Monitor the development and test of test software that is needed in the acceptance test.

- Witness the dry run of the acceptance test.

- Attend test readiness and post test reviews.

- Review the software configuration prior to dry run and acceptance test to ensure that the same version of software is run.

- Witness the acceptance test.

- Review test reports to certify that reported test results reflect the actual finding of the tests.

- Retain the master copy of all media and documentation used in testing.

The SQA system is also subject to periodic evaluations through self-assessment and assessment by other FlightSafety and Raytheon SQA experts.  These assessment are done to determine if the quality program plan is consistent with standards, is tailored for the program, and is implemented according to its plans.  Any non-conformance is documented, reported to management, and entered into the corrective action process.

### 5.16.2  Software Quality Assurance Records, Including Items to be Recorded

Each IPT uses forms to summarize results of various SQA checklist evaluations.  These forms provide a written account of each software quality evaluation performed and serve as inputs to the corrective action system.  IPTs use the appropriate checklist to document and summarize results.  As SQA evaluations are performed, any non-compliances, inadequacies, or inconsistencies detected in the processes used in software development and the resulting software and associated documentation are documented.  Corrective actions are coordinated with applicable parties for agreement on the appropriate resolution and a due date.  QA monitors the corrective actions to completion.  Reference Section 5.17 for further details about the corrective action system.

Figure 5.16.2-1 shows a sample FSI Inspection/Evaluation Checklist form.  Figure 5.16.2-2 shows a sample TIMS QER form.  TIMS SQA maintains the completed checklists and the QERs which summarize the quality assurance evaluations in a project SQA file.  Copies of  SDF evaluation checklists are also placed in the appropriate SDF.  SQA also maintains a log noting the date and time of each evaluation.

### 5.16.3  Independence in Software Quality Assurance

Each IPT’s SQA organization has an independent direct reporting line to senior quality assurance management, as well as its normal reporting line to the IPT Leader.   Each IPT’s SQA function prepares an informal status report and submits it to the IPT Leader and SQA’s upper management.  These reports enable management to maintain visibility into the health of the software quality activities on the program.  Each IPT’s SQA provides monthly status reports to SQA’s upper management, the IPT Leader, and the GBTS QA PST.  The status report summarizes the overall activities performed during the previous month and includes the QERs and status of any open corrective action items.

## 5.17  Corrective Action (SOW 5030.1.4)

The IPTs establish a closed loop corrective action process in order to ensure that action items and  problems detected during software development are documented, tracked, and resolved.  Multiple sources serve as inputs to the corrective action process in order to ensure that all detected problems, regardless of how they are found, are entered into the single correction process.  Detected problems are categorized and prioritized in order to determine the sequence in which problems will be addressed and to facilitate the analysis of trends in problems detected.  Problems are analyzed for adverse trends to permit identification and correction of overall conditions that are resulting in specific problems detected.  The correction of problems are then evaluated to ensure that the problems and adverse trends are corrected and to determine whether additional problems have been introduced in the process.

The corrective action process provides a structured way to report, track, and resolve the problems detected during the software development process and requires the active participation of all organizational areas, including management.  The corrective action databases will be integrated with the Raytheon databases.

### 5.17.1  Problem/Change Reports

#### 5.17.1.1  TIMS Problem/Change Reports

The TIMS IPT will initiate and control changes to established IPT-level baselines utilizing the appropriate change reports.  Each report describes the problem, the priority, the classification, corrective action needed and the action taken to correct the problem.  Table 5.17.1-1 provides a list of categories and Table 5.17.1-2 lists priorities.  Software Change Requests (SCRs) are used to report problems detected in level 2 or level 3 controlled documentation.  Quality Evaluation Records (QERs) are used to report problems encountered during QA evaluations.  Action Items (AIs) are used to report problems encountered during informal and formal reviews and audits.  Problem reports or discrepancy reports are used to report all problems encountered during testing.  In general problem reports are used prior formal baseline qualification and promotion for developmental controlled items.  Discrepancy reports are used starting with formal CSCI testing.  A corresponding SCR and/or ECR is prepared for each problem reported on a QER, Action Item, or Problem/Discrepancy reports that affects GBTS CCB or Government controlled documentation (Level 2 or 3).

FIGURE 5.16.2-1  Blank FSI Quality Assurance Inspection/Evaluation Checklist

*****************************************************************

QER No:

QUALITY EVALUATION		EVALUATOR:

DATE:

RECORD

PROGRAM:

*****************************************************************

ITEM OR ACTIVITY EVALUATED:

EVALUATION DATE(S):            N-PROCESS EVALUATION:   ___

FINAL EVALUATION:   ___

PARTICIPANTS:

CONCLUSIONS:   ___  ACCEPTED

___  NOT ACCEPTED

ACCEPTED PENDING RESOLUTION

___   OF ACTION ITEMS

EVALUATION CRITERIA:

RESULTS:

RECOMMENDATIONS:

ACTION ITEM No     	DESCRIPTION                    DUE DATE

**

** REQUEST EXTENSIONS, IN WRITING, PRIOR TO DUE DATE IN THE EVENT THAT 	CORRECTIVE ACTION CANNOT BE FINALIZED BY THAT DATE.

QA ENGINEER:				 DATE CLOSED		:

COMMENTS:

*****************************************************************

FIGURE 5.16.2-2  Sample TIMS QER Form

All problems are maintained in a database by type, category, and priority.  The TIMS IPT reviews status at periodic meetings.  The TIMS IPT is responsible for reviewing SCRs and ECRs and authorizing approval to close and resolve problems.  Problems are classified by category and priority as follows:

| Category | Applies to problems in: |
| --- | --- |
| - Plans | One of the plans developed for the project |
| - Concept | The operational concept |
| - Requirements | The system or software requirements |
| - Design | The design of the system or software |
| - Code | The software code |
| - Database/data file | A database or data file |
| - Test information | Test plans, test descriptions, or test reports |
| - Manuals | The user, operator, or support manuals |
| - Other | Other software products |

TABLE 5.17.1-1  Categories To Be Used For Classifying Problems In Software Products

| Priority | Applies if a problem could: |
| --- | --- |
| 1 | - Prevent the accomplishment of an operational or mission essential capability - Jeopardize safety, security, or other requirement designated "critical" |
| 2 | - Adversely affect the accomplishment of an operational or mission essential capability and no work-around solution is known - Adversely affect technical, cost, or schedule risks to the project or to life cycle support of the system, and no work-around solution is known |
| 3 | - Adversely affect the accomplishment of an operational or mission essential capability but a work-around solution is known - Adversely affect technical, cost, or schedule risks to the project or to life cycle support of the system, but a work-around solution is known |
| 4 | - Result in user/operator inconvenience or annoyance but does not affect a required operational or mission essential capability - Result in inconvenience or annoyance for development or support personnel, but does not prevent the accomplishment of those responsibilities |
| 5 | Any other effect |

TABLE 5.17.1-2  Priorities To Be Used For Classifying Problems

#### 5.17.1.2  FTD Problem/Change Reports

The FTD IPT will initiate and control changes to established IPT-level baselines utilizing appropriate change reports as set forth in Table 5.17.1-3.  Each report describes the problem, the priority, the classification, corrective action needed and the action taken to correct the problem.

| Report | Applies to : | Generated By |
| --- | --- | --- |
| Problem Report | Problems found during informal testing of CM level 1 or 2 or IPT level 3 controlled software | Any IPT member, generally developers or SQA |
| Quality Evaluation Records | Problems found during QA Evaluations | Software or Corporate QA |
| Action Item | Problems found during reviews and audits | Any participant |
| Discrepancy Report | Problems found during formal testing of CM level 2 or IPT level 3 software, or any problem detected by the user with a GBTS level 3 controlled software product | Formal test participants, post delivery users |

TABLE 5.17.1-3  Categories To Be Used For Classifying Problems In FTD Software Products

Once software is under internal or GBTS level 3 configuration control, an Engineering Change Request (ECR) or Software Change Request (SCR) is generated by the IPT to initiate modification of software in response to any of the reports called out in Table 5.17.1.1.  An SCR is generated for software-only changes, an ECR for combined software/hardware changes.

### 5.17.2  Corrective Action System

The TIMS and FTD IPTs use the CASE tool PureDDTS to control and document discrepancies and change requests throughout the development life cycle.  PureDDTS, a companion product to the ClearCase CM tool, provides a pre-defined collection of change request states (for example, "Assigned" or "Resolved"), and the transitions that are allowed as a change requests moves from one state to another.  Actions (for example, E-mail notification) and rules that govern the life cycle are also provided.  An overview of PureDDTS  capabilities is shown below.  The product provides reports and queries for all discrepancies and change requests.

The corrective action system consists of the following functions:

- Reporting detected problems.  Problems are documented by SQA, developers, the customer, and independent testing groups and turned into the corrective action system for entry into a centralized ClearCase database.  The description of a software problem will include:  the conditions, inputs, and equipment configuration under which the problem arose; a description of the activities leading up to the problem; sufficient information to permit duplication and analysis of the problem; and any suspected relationship to other reported problems and modifications.  Problems are documented on forms as outlined in Section 5.17.1.

- Analyzing problems.  Each identified problem is assigned to a specific engineer for analysis.  SQA verifies that the analyst’s name and telephone number are recorded on the problem report.

- Classifying problems by category and priority.  SQA verifies that once analysis is complete, problems are classified by category and priority and recorded with the problem report.

- Identifying necessary corrective action.  The analyst suggests the recommended solution and coordinates with the originator of the problem report.  The recommended solution and later, the implemented solution are recorded on the problem report.

- Identifying trends.  SQA utilizes the corrective action database to identify trends in both the development process and the developed product.  The IPT Leaders and PST Software Process Manager also use the corrective action system to collect and analyze metrics associated with software specification, design, coding, testing, and error density.

- Analyzing trends.  SQA prepares reports summarizing the analysis of trends and makes recommendations based on that analysis.  Metric data to support trend analysis is maintained in a metrics database.  Quantitative analysis techniques will be used to analyze and present trends.

- Authorizing implementation of corrective steps.  The component IPT CCBs review recommendations made by analysts when the analysis of the problem is completed.  The component IPT CCBs are responsible for determining whether to implement a change, pass the problem up to the GBTS CCB, defer the problem for further analysis, or close a problem.

- Documenting corrective actions.  SQA verifies that the approved corrective action is taken, the solution is implemented, and appropriate records (databases) are annotated accordingly.  SQA evaluates whether adverse trends are reversed, that documentation updates are correct, and that no additional problems are introduced.

- Tracking and closing out problems.  The status of all outstanding defects or problems will be provided to appropriate organizations.  Overdue resolutions will be highlighted.  QA ensures problems are corrected though witnessing tests, attending peer reviews, etc.  When all action is complete, the IPT CCB and QA certify problem closure.

- Provide Government visibility into critical problems.  The defects/problems are entered into the centralized corrective action system database and are accessible to FlightSafety, Raytheon, and the Government.  In addition, the IPT reviews the status of major problems at joint technical and management reviews.

## 5.18  Joint Technical and Management Reviews(SOW 5020.1.1 - 1.1.16)

The IPTs conduct periodic technical and management reviews in accordance with MIL-STD-1521 (review) MIL-STD-973 (audits), LEIB procedure SEP-11, and SEPP-1000 procedure 2.03.  These procedures contain guidelines for conducting:  formal reviews;  technical reviews; and management reviews to be used on the JPATS GBTS program.  Raytheon and the Government are advised of all reviews and are invited to participate.

### 5.18.1  Joint Technical Reviews (SOW 5020.1.1.1 - 1.1.16)

Joint technical reviews include both interim technical interchange meetings and specific formal reviews.  Joint technical reviews are conducted:

- to assess status and progress

- to review evolving software products (for example the SRS or IRS)

- to demonstrate that relationships, interactions, interdependencies, and interfaces between required items and system elements have been addressed

- to assess and resolve technical issues

- to resolve conflicts or inconsistencies among system requirements, functional alternatives, and design solutions

- to surface near-term and long-term risks and arrive at agreed on strategies to minimize the identified risks

- to ensure on-going communications between the customer and the developer technical personnel

The IPTs are responsible for preparing for reviews, including establishing the schedule, publishing an agenda and coordinating the scope with the appropriate attendees.  The IPTs conduct reviews both electronically and in face-to-face meetings.  If necessary, a dry run is conducted for formal reviews to facilitate coordination, to ensure review readiness, and to ensure compliance with program requirements.

Review minutes, decisions, agreements and approved action items are recorded and signed by the appropriate managers.  Action items are entered into a tracking database.  Open action items are tracked to closure.

Informal technical interchange meeting are performed between formal reviews on an as needed basis.  In addition, the JPATS GBTS PMO will conduct a number of formal reviews.  Formal reviews are specified in Table 5.18.1-1.

| Review | Purpose |
| --- | --- |
| Program Guidance Conference (PGC) (SOW 5020.1.1.16) | Conducted to formalize the overall data management process and to finalize the FlightSafety team’s requirements for Raytheon aircraft data. |
| Systems Engineering Guidance Conference (SEGC) (SOW 5020.1.1.10) | Held to review and update the SDP, SEMP, and Courseware Development Plan |
| Integrated Baseline Review (IBR) (SOW 5020.1.1.9) | Held within 120 days of contract award. The IBR is used to familiarize RAC and Government personnel with the GBTS subcontractor’s EVMS system. The meeting is used to validate the performance measurements baseline and the performance data. |
| JPATS GBTS System Requirement Review (SRR) (SOW 5020.1.1.11 | Conducted to assess the adequacy of efforts in defining system requirements and their responsiveness to the statement of work and system/segment requirements. An SRR is conducted when a significant portion of the system functional requirements has been established and the preliminary requirements have been allocated. |
| JPATS GBTS System Design Review (SDR) (SOW 5020.1.1.13) | Conducted to evaluate the optimization, traceability, correlation, completeness, and the risks associated with the allocated technical requirements, including the corresponding test requirements, in fulfilling the total system/segment requirements. The system design, analysis, and modeling that have been performed will be assessed as to whether the proposed software system architecture will meet functional requirements. An SDR may be conducted when the system requirements have been allocated to hardware configuration items (HWCIs), software configuration items (CSCIs), and manual operations, and the preliminary software and interface requirements have been identified. The JPATS GBTS preliminary Functional Baseline is established no later than the satisfactory completion of an SDR and approval/authentication of the System/Segment Design Description, Prime Item Development Specification, or Critical Item Specification. |
| JPATS GBTS Component Specification Reviews (CSRs) (SOW 5020.1.1.12) | Conducted to assess the adequacy of efforts to refine the system requirements as documented in the component PUSD. The CSR is conducted after the SDR when the system design has been finalized. The component PUSD are baselined after the component CSR. The JPATS GBTS preliminary Functional Baseline is established no later than the satisfactory completion of an SDR and approval/authentication of the System/Segment Design Description, Prime Item Development Specification, or Critical Item Specification. |
| TIMS Software Specification Review (SSR) | Conducted to evaluate the adequacy of the operational concept and finalized requirements as specified in the Software Requirements Specifications (SRS) and the associated Interface Requirements Specification (IRS). An SSR is normally conducted after the System Design Review but prior to the start of TIMS preliminary design. The Allocated Baseline is established upon the satisfactory completion of an SSR and the initial approval/authentication of the SRS and IRS. At the end of the SSR, the IPT in conjunction with the JPATS community prioritizes and categories the requirements and comes to a consensus on how to allocate the requirements into three increments. |

TABLE 5.18.1-1  Formal Reviews

| Review | Purpose |
| --- | --- |
| Preliminary Design Review (PDR) (SOW 5020.1.1.14) | Conducted to evaluate the preliminary design (documented in the SPS) against the requirements allocated from the higher-level documents (i.e., SS, PUSD, SRS, and IRS) to demonstrate that the software requirements have been satisfied. The high-level structure of the CSCI (i.e., its CSCs) is reviewed and evaluated to determine whether the approved design methodology has been used. During the PDR a technical understanding is reached on the validity and the degree of completeness of the software design. The test plans are reviewed to demonstrate that adequate test criteria have been established and that the test criteria address all specified requirements. A PDR is conducted at the conclusion of the preliminary design activities prior to the start of detailed design. |
| Critical Design Review (CDR) (SOW 5020.1.1.15) | Conducted to evaluate the detailed design (documented in the SPS) against the requirements allocated from the higher-level documents (i.e., SS, PUSD, SRS, and IRS) to demonstrate that all software requirements have been satisfied. The low-level structure of the CSCI (i.e., its CSUs) is reviewed and evaluated to determine whether the approved design methodology has been used. During the CDR a determination is reached on the consistency of the updated detailed design and the acceptability of the test plans for the formal qualification tests. A CDR is conducted at the conclusion of the detailed design activities prior to the start of CSU coding and testing. |
| System Integration Review (SIR) (SOW 5020.1.1.16) | Conducted after the completion of all the component CDRs. During the SIR a determination is made as to whether the CI designs agreed to in the CDRs are integrated to meet the overall GBTS requirements and user expectations. The SIR includes representatives from all IPTs. The agenda centers on the GBTS system level testing and unique requirements for MOT&E. |
| Test Readiness Reviews (TRR) | A formal TRR is conducted before the start of all formal GBTS testing. The TRR is designed to determine whether the formal qualification test procedures are complete and accurate and to determine that the software is ready for formal system qualification testing. The software test descriptions are evaluated for compliance with the software test plans and for adequacy in accomplishing test requirements. A successful TRR is predicated on a determination that the test procedures and results of informal software testing form a satisfactory basis for proceeding into formal GBTS qualification testing. |
| Site Test Readiness Reviews (STRR) (SOW 5020.1.1.6) | The STRR’s are held at each base, after all required assets have been received for start of student training. These reviews are conducted by the Government with GBTS PMO and IPTs support. |
| Functional Configuration Audit (FCA) (SOW 5020.1.1.9) | This audit is conducted by the Government to verify that CSCI actual performance complies with the requirements specified in the SRS and IRS. This is accomplished by a detailed review of the formal qualification test procedures, data, and reports. In addition, a technical understanding is reached on the validity and the degree of completeness of the operational and support documents, such as the SUM. An FCA is conducted at the completion of component System Acceptance Testing. |
| Physical Configuration Audit (PCA) (SOW 6020.1.1.4) | This audit is conducted by the Government to verify that the as-built version of a component reflects an up-to-date physical representation of the Specifications and approved design of the CSCI. The PCA includes a detailed audit of engineering drawings, specifications, technical data and tests utilized in production of the media for the software. The PCA also includes a detailed audit of the Software Product Specification (SPS) and Software Version Description (SVD). A PCA is conducted at the completion of the component System Acceptance Testing The Product Baseline is established upon the satisfactory completion of an FCA and PCA and the initial or conditionally approved/authenticated SPS. |

TABLE 5.18.1-1  Formal Reviews (Continued)

### 5.18.2  Joint Management Reviews (SOW 5020.1.1 -1.1.1, 5020.1.1.7, 6020.1.1.1)

The GBTS PMO is responsible for preparing for reviews, establishing schedules, publishing an agenda, and coordinating the scope with the appropriate attendees.  Reviews are held approximately every two months and provide cost, schedule, technical status and discuss earned value issues.  Joint Management reviews are held to:

- Present project status, directions being taken, technical agreements which have been reached, and overall evolving software products

- Resolve issues not raised or resolved at joint technical meetings

- Arrive at agreed-on mitigation strategies for near- and long-term risks

- Obtain commitments and customer approvals needed for timely accomplishment of the project.

- Present project size, effort, cost and schedule status

Preparation for reviews includes schedule, agenda and scope coordination with the appropriate attendees.  Reviews may be conducted both electronically and in face-to-face meetings.  Material is reviewed by technical and program managers internally before it is released to external participants.

Review minutes, decisions, agreements and approved action items are recorded and signed by the appropriate managers.  Action items are entered into a tracking database.  Open action items are tracked to closure.

## 5.19  Other Software Development Activities (SOW 5020)

The GBTS PMO and IPTs perform the necessary actions to accomplish the GBTS activities contained in the IMP and the GBTS tasks listed in the SOW.  The GBTS PMO supports the Integrated Product Development program.  The GBTS program is managed using earned value concepts for cost, schedule, and technical performance measurements.

### 5.19.1  Risk Management

The GBTS  risk management program is a dynamic and integral  part of our system engineering and software development processes and is discussed within the SEMP.  Risk management is an on-going process throughout the software development.

Each IPT establishes a Risk Management Team which meets at least monthly.  The Risk Management Team is headed by the IPT Leader, technical leads and SQA.  The teams receive additional support from upper management, who review the “watch list”, evaluate status, and maintain direct involvement in mitigation activities.  Each IPT Leader is responsible for reporting risks and risk status to the GBTS Program Manager and GBTS Risk Management Team on a routine (monthly report) or priority basis depending upon the circumstances.

The risk management program consists of the following activities:  risk identification, risk analysis, risk planning, risk tracking and control, and risk communications.

#### 5.19.1.1  Risk Identification

Risk identification is the first step in risk management.  All IPT members, including Raytheon and Government representatives are involved in this activity.  The IPTs use an approach to risk identification, which is based on a process developed by the Software Engineering Institute and documented in “Taxonomy-Based Risk Identification”, CMU/SEI-93-TR-6.  Central to this approach is the taxonomy of software development risks (shown in Table 5.19.1-1), which is organized into three major classes:

- Product Engineering - The technical aspects of the work to be accomplished.

- Development Environment - The methods, procedures, and tools used to produce the environment

- Program Constraints - The contractual, organizational, and operational factors within which the software is developed.

Each IPT clarifies, categorizes, and documents risks.  Software risk identification is a part of the planning process for each major activity process (i.e., system requirements analysis, system design, software requirements analysis, etc.)  Each IPT also repeats the risk identification process whenever there are significant changes to the characteristics of the software process or product.

| Risk Areas | Risk Factors | Program Constraints |
| --- | --- | --- |
| Requirements | Development Process | Resources |
| Stability Completeness Clarity Validity Feasibility Precedent Scale | Formality Suitability Process Control Familiarity Product Control | Schedule Staff Budget Facilities |
| Design | Development System | Contract |
| Functionality Difficulty Interface Performance Testability Hardware Non-Developmental Software | Capacity Suitability Usability Familiarity Reliability System Support Deliverability | Type of contract Restrictions Dependencies |
| Code and Unit Test | Management Process | Program Interfaces |
| Feasibility Testing Coding/Implementation | Planning Project Organization Management Experience Program Interfaces | Customer Associate Contractors Subcontractors Prime Contractor Corporate Management Vendors Politics |
| Integration and Test | Management Methods |  |
| Environment Product System | Monitoring Personnel Management Quality Assurance Configuration Management |  |
| Engineering Specialties | Work Environment |  |
| Maintainability Reliability Safety Security Human Factors Specification | Quality Attitude Cooperation Communication Morale |  |

TABLE 5.19.1-1  Taxonomy of Software Development Risks

#### 5.19.1.2  Risk Analysis.

After risks are identified, each IPT performs analysis and investigation on each risk to rate the risk and define the risk level.  Risk levels (minimal (none), low, medium, and high are defined as the combined effect of the probability of an adverse outcome and the program penalty (performance, cost,  and schedule impacts) associated with the outcome.  The IPTs use the risk analysis techniques defined in the SEMP, Section 3.2.1.  The TIMS IPT will use the COTS tool Opera (an extension to Open Plan) for risk analysis.  Opera performs risk analysis using a Monte Carlo simulation to estimate the effects of probability distribution on project dates and costs.  Opera data also produces reports and feeds the Open Plan schedules.  This risk control process provides direct interface and coordination with the Raytheon JPATS risk management system.

#### 5.19.1.3  Risk Planning

Once the quantitative risk assessment is complete, each IPT plans and implements a formal risk reduction program.  Nominal risk items present no special concern as there is sufficient tracking and control to address these risks in the normal development process.  Low, medium and high risk items require special monitoring activities.  The IPTs uses metrics to monitor low, medium and high risks.  For medium and high risk, an IPT Risk Management Team may direct that a detailed risk management plan be developed by the technical leads.  The Risk Management Team is responsible for formally approving these detailed plans.

Risk reduction planning includes:

- Identification and definition of the primary technical solution and the time-phased development/test program to alleviate identified issues and concerns.  Key technical performance measures and thresholds (e.g., bytes/SLOC, MIPS, function points, etc.) are identified and tracked to ensure satisfactory progress is being made toward system requirements.

- Identification of lower risk “fallback” technical solutions to be used in case the primary system fails to meet critical objectives.

- Decision milestones and criteria to be met for choosing between primary and alternate systems.  These depend on the progress of meeting the risk reduction technical objectives and timing requirements such as deadlines for fielding.

Examples of specific tasks for software risk reduction are:

- Performing algorithm development work early in the program

- Building prototypes of a product to demonstrate capabilities

- Building prototype displays to test and verify human machine interfaces

- Demonstrating critical software and hardware implementations and technologies

- Using modeling tools to design physical architectures

#### 5.19.1.4  Risk Tracking and Control

Each IPT’s Risk Management Team is responsible for managing and tracking the identified risks.  The team also maintains oversight over all risk mitigation activities.  Typical tracking involves the use of product, process, and progress metrics and/or Technical Performance Measurements.  Thresholds are usually specified as a combination of a percentage figure and a dollar or hour value (e.g., 10% and 100 hours for a labor variance).

The size, effort, cost and schedule status of each of the software components are monitored and tracked as a cooperative effort by the cost account managers manager and technical leads.  To the greatest extent possible, automated tools are used to collect metrics.  The IPT cost account managers receive automated cost management system reports every month for use in their status reviews.  The cost management system detects any cost account whose variance exceeds specified threshold values.  The cost account manager must generate variance analysis report for any accounts which exceed specified thresholds.  The cost account manager is required to analyze the variance by identifying the problems, assessing the potential impact on the program, and defining corrective actions and criteria for completion of the corrective action.  SQA and upper management have a responsibility to monitor and help resolve corrective actions if problems are not resolved within a timely fashion.

### 5.19.1.5  Risk Communication

Each IPT’s Risk Management Team is responsible for investigating risks and for identifying risks to all the IPT members, upper management (FlightSafety/Logicon), Raytheon and the Government.  The status of significant high and medium risks are presented and discussed at internal management reviews and joint technical and management reviews.  Each IPT Leader also reports risks and risk status to the GBTS Program Manager and GBTS Risk Management Team on a routine (monthly report) or priority basis depending upon the circumstances.

### 5.19.2  Software Management Indicators (SOW 5020.2.3-2.4)

The IPTs use management indicators and the Earned Value Management System (EVMS) to provide an objective, concrete assessment of actual progress (real accomplishments, results, and content) against the plan.  The IPTs track the status of technical activities, software work products, users of computer resources, effort and funds expended, and schedules.  The GBTS PMO and IPTs use management indicators for project planning and managing, to improve quality and productivity, and for improving customer satisfaction.  The management indicators (see 5.19.2-1 below) help promptly spot problems, help to more accurately quantify and prioritize risks, and help in the formulation of corrective actions.  Regularly recorded measurements of these indicators, along with lessons learned, are also an essential ingredient for improving the software development process.

| Management Indicator | Metric | Collection Input Parameter | Points when data is collected | Analysis Factors | Reporting Criteria | Organizations to which data is reported |
| --- | --- | --- | --- | --- | --- | --- |
| Development Status | Design complete | Planned vs Actuals s/w units/CSC which have design completed over time | weekly/ monthly during design process (per build) | When actuals exceed planned by more than 10%, mgmt initiates corrective actions (re-planning, tools, training, or prioritization of rqmts for the current build) | Activity flow, bar chart, or table indicating units/CSC planned and completed information | Reported to mgmt monthly, updated weekly in central database. |
|  | Code complete | Planned vs. actuals s/w units/CSC which have been coded and unit tested over time | weekly/ monthly during code and unit test process (per build) | When actuals exceed planned by more than 10%, mgmt initiates corrective actions (re-planning, tools, training, or prioritization of rqmts for the current build) | Activity flow, bar chart, or table indicating units/CSC planned and completed information | Reported to mgmt monthly, updated weekly in central database. |
|  | Integration completed | Planned vs. actuals s/w units/CSC/ CSCI/HWCI which have been completed integration testing over time | weekly/ monthly during unit integration process (per build), CSCI integration, CSCI/HWCI integration, and system integration | When actuals exceed planned by more than 10%, mgmt initiates corrective actions (re-planning, tools, training, prioritization of rqmts for the current build, added unit level testing). Analysis also allows identification and mitigation of h/w problems, cm procedures, test environment, and build procedures. | Activity flow, bar chart, or table indicating units/CSC/ CSCI/HWCI planned and completed information | Reported to mgmt monthly, updated weekly in central database. |

TABLE 5.19.2-1  Management Indicators

| Management Indicator | Metric | Collection Input Parameter | Points when data is collected | Analysis Factors | Reporting Criteria | Organizations to which data is reported |
| --- | --- | --- | --- | --- | --- | --- |
|  | Validation complete | Planned vs. actual s/w verification tests successfully completed over time | weekly during CSCI and System formal test | When actuals exceed planned by more than 10%, mgmt initiates corrective actions (re-planning, tools, training, or added staff. Rqmts could be prioritization and deferred to another build or increment. Analysis also allows identification and mitigation of h/w problems, cm procedures, test environment, and build procedures. | Activity flow, bar chart, or table indicating tests planned and completed information | Reported to customer and mgmt monthly. Updated weekly in database. |
| Schedules, Critical Paths, and Critical Dependencies | Schedule performance vs. critical dependencies | Planned vs. actual performance. Dates of critical dependencies delivery if external. | weekly | When actuals exceed planned by more than 10%, mgmt initiates corrective actions (replanning, added staff, etc.) | Activity flow, bar chart, or table. | Reported to mgmt monthly. Updated weekly in database. |
|  | Software Schedule | S/W tasks completion. Actuals vs. planned | Weekly/monthly | When actuals exceed planned by more than 10%, mgmt initiates corrective actions (replanning, added staff, etc.) | Planning charts and activity flow diagrams | Reported monthly to mgmt. Higher level schedules reported to customer at reviews. Detailed schedule updated weekly in database. |
| Staffing, Effort and Cost Profiles | Staffing profiles over time | Planned vs. actual | monthly | When actuals exceed or are less than 10% of planned, mgmt initiates corrective actions (replanning, adding or removing staff) | Activity flow, bar chart, or table. | Reported to mgmt monthly. |

TABLE 5.19.2-1  Management Indicators (Continued)

| Management Indicator | Metric | Collection Input Parameter | Points when data is collected | Analysis Factors | Reporting Criteria | Organizations to which data is reported |
| --- | --- | --- | --- | --- | --- | --- |
|  | Earned value | BCWS, BCWP, ACWP | monthly | Used to determine progress in terms of amount of budget that was planned to do that amount of work | Table showing budgets, actuals, and variances | Monthly to program manager |
|  | Variances | Schedule/ Cost Variances | Monthly | Id and reason for schedule or cost variance. Positive variance means ahead of schedule or work performed with less expenditures. Negative various means behind schedule or overrun of expenditures | Written explanation for variances | Monthly to program manager |
| Software Work Product Size | Software Size | Estimates vs. actual (SLOC or function points. Reference SEP-005) | Monthly during design and coding. Also when requirements change | When actuals exceed planned by more than 10%, management initiates corrective actions (replanning, added staff, etc.) | Written explanation for variances | Monthly to Program Manager |
|  | Rqmts. completion/ stability | New/changed rqmts released over time | Monthly | Analysis of rqmt stability. Used quarterly to access risks and need for further risk mgmt approaches and to perform stability trending. | List of rqmts added or changed with an indicator of the complexity factor associated with implementing the rqmt. | Reported to customer at reviews. Maintained in central database. Reported to upper mgmt monthly. |
| Build Content | Rqmts allocated to each build | Planned Vs actual | Monthly | Use to assess whether each build contains all originally planned functional capability. | List of requirements per build. List of requirements added or deleted since last report | Reported to mgmt monthly. Maintained in database. |

TABLE 5.19.2-1  Management Indicators (Continued)

| Management Indicator | Metric | Collection Input Parameter | Points when data is collected | Analysis Factors | Reporting Criteria | Organizations to which data is reported |
| --- | --- | --- | --- | --- | --- | --- |
| Critical Computer Resources and Performance Measures | CPU usage, memory usage, I/O channel usage, database response time, throughput | Estimates Vs planned budgets. Actuals Vs planned budgets. | Estimates updated monthly during design and coding. Actuals collected monthly during integration, CSCI test, and system test | Used to monitor potential technical risk areas. When estimates or actuals exceed thresholds, additional trade studies, prototyping, risk mitigation or allocation of reserve is performed. | Graph or table of estimates. Graph or table of actuals. Confidence in estimate, estimate accuracy, expected error distribution. Identification of methods to relieve stress. | Reported to customer at reviews. Reported to mgmt monthly. Maintained in database |
| Software Quality Measures | Open vs. Closed problem reports | Cumulative number of open and closed problems/change reports | Weekly/ Monthly | Shows stability of S/W change process. Shows change work in progress at a given point in time | Graph of cumulative number of open and closed problems | Reported to customer at major reviews. Reported monthly to mgmt. Maintained in corrective action database |
|  | Problem Fault Analysis | Number of problems opened sorted by cause (req. design, coding) | Weekly/ Monthly | Helps identify adverse trends. Design and code errors may indicate need for more thorough peer reviews. | Graph/bar chart of problem opened by cause | Reported monthly to IPT. |
|  | Defect Point of detection distribution | Number of defects discovered in each phase (reqs., design, coding, etc.) | Monthly | To reveal how early or late defects are detected. | Discrete distribution graph showing total number of defects per phase | Reported monthly to IPT. |

TABLE 5.19.2-1  Management Indicators (Continued)

### 5.19.3  Security and Privacy (SOW 7010.4.1)

The GBTS development complies with Government security procedures for all areas containing ATDs, CBTS and the MUSS.  Safeguards are maintained for all Government property and equipment.

### 5.19.4  Subcontractor Management

Subcontractor contract requirements are contractually set forth via statement of work, functional specification, program schedule, and product support documents.  Formal methods of determining satisfactory subcontractor performance involve monthly status reports, design reviews, and acceptance testing.  Project engineers are assigned to each subcontract to coordinate, monitor, assist in technical progress and to provide a further visibility into subcontractor progress and problems.

The GBTS team maintains both formal and extensive informal interfaces with subcontractors.  All contractual and administrative interfaces occur through the GBTS PMO organization, and include submission of contractually required reports, plans, procedures, data, etc.

Formal interfaces at functional levels occur during design reviews, acceptance tests, and in response to subcontractor submitted deliverables.  Informal interfacing at both the program and functional level provides for day-to-day resolution to difficulties.  Functional managers are responsible for maintaining a direct interface with their counterparts in the subcontractor’s organization and are authorized to make decisions and resolve all problems in which contract, schedule and/or budget are not involved.

Subcontractor/vendor activities are closely monitored to ensure consistency and enforcement of policies and procedures.  Each subcontractor is required to have procedures for identifying baseline configurations and controlling and documenting changes to that baseline.  Review and audits are conducted during periodic subcontractor program reviews to verify compliance with specifications and other requirements.

### 5.19.5  Interface with Software Independent Verification and Validation (IV&V) Agents

The GBTS PMO will provide a technical point of contact and technical data as required for any JPATS IV&V agent.

### 5.19.6  Coordination with Associate Developers

Not applicable

### 5.19.7  Improvement of Project Processes

The GBTS PMO and  IPTs are  committed to continuous improvement of project processes to improve the quality and timeliness of the software products and activities.  To this end, planning, tracking and oversight are built into all software development process activities.  All participants on the IPTs are responsible for evaluating the current activities for improvements.  IPTs are authorized to initiate product improvement teams, which focus on identifying improvements in key areas.  Each IPT also has a designated Software Engineering (SE) representative who is responsible for collecting and documenting process improvement information and participating in operating group and corporate process assessments.  The representative presents process improvement information to the IPT Leader and corporate personnel for their review and assistance.  The IPTs use company approved process improvement team methodologies.

QA has evaluation checklists that are used to evaluate products produced by the software development processes and to periodically monitor software development activities.  As part of its trend analysis activities, QA makes recommendations for process improvements.  All the process flows (requirements analysis, design, etc.) show a planning and review activity as the first item in the process flow and tracking and oversight as a continuous activity during the process flow.  Also, on exit from each process, the IPTs perform an evaluation of the just finished process flow and suggest improvements (see SDP, Section 5.19.2, Table 5.19.2-1 for a list of quality metrics).

### 5.19.8  Other Activities

Not applicable.

# 6.0  Schedules and Activity Network  (SOW 5020.2.4)

The Master Integrated Program Schedule (MIPS) will be the controlling document.  Milestones of completion criteria are set forth in the MIPS.  Individual software development schedules will be prepared, maintained and reviewed by the responsible IPT.  Software development schedules will be presented at all major reviews.  Figure 5.1-1, presented previously in Section 5.1, contains a high level major milestone schedule.

# 7.0  Project Organization and Resources (SOW 5020.2.1)

The GBTS team consist of one full time on-site representative to the Raytheon Wichita, Kansas facility.  The GBTS on-site representative participates on the Raytheon JPATS Training System IPT and other IPTs as required and provides assistance to ensure the balanced, integrated development, and delivery of Training System components.  The on-site representative is also an associate member of the Raytheon JPATS CCB.  The Raytheon on-site representative will maintain close coordination with the FlightSafety GBTS management.

## 7.1  Project Organization

The overall GBTS program organization is shown in Figure 1.2.1-1, Section 1.2.1.  The product teams (IPTs) produce each of the GBTS components.  Each IPT has total management and engineering responsibility and authority for its product(s), consistent with the system requirements flowed down to that product.  Issues that cross IPT boundaries are coordinated between the IPTs with the support of the PST process managers.  Each IPT is comprised of the appropriate skill mix to produce the required products.  The IPT leaders are responsible for controlling and executing the development of the software and hardware components/products assigned to that IPT.  Each IPT coordinates development, testing and integration.  (Figure 1.2.1-1, in Section 1.2.1 shows the IPT relationships.)

FlightSafety and Logicon operate under a contractor/subcontractor relationship.  Applicable FlightSafety/RAC subcontract tasks are flowed down to Logicon via Statement of Work (SOW) and subcontract data requirements list (SDRL) portions of the FlightSafety/Logicon subcontract.  Logicon manages and provides the software development effort for the OSS IPT.  The OSS IPT produces the TIMS, CBTS and MUSS, with virtually all development taking place for the TIMS.  Logicon’s OSS IPT Leader reports to FSSC’s GBTS Program Manager for JPATS GBTS issues.  FSSC’s process managers (Software, System Engineering, Quality Assurance, Configuration Management, etc.) are members of the OSS IPT, are responsible for ensuring that the IPT operates IAW their stated plans, and participate in their respective portions of the Logicon effort.  FlightSafety’s Software Process Manager (SWPM) will be resident at Logicon’s development facility.  The SWPM will participate daily with Logicon as part of the OSS creative team, will coordinate Technical Performance Measurement (TPM) status reporting with the Logicon OSS IPT Leader, and will monitor progress via direct observation and evaluation of TPM reports.  Additionally, the SWPM will be trained in EVMS and will review Logicon EVMS reports, variance analyses, etc. to ensure appropriate GBTS level surveillance of critical OSS/TIMS software development activities

FIGURE 7.1-1  FSI-SSD FTD IPT Project Organization

### 7.1.2  TIMS Project Organization

The TIMS is being developed by Logicon under a subcontract to FlightSafety.  The TIMS IPT relationship to the Logicon organization is shown in Figure 7.1.2-1.  The TIMS IPT internal structure is shown in Figure 7.1.2-2.  The TIMS IPT Leader has overall responsibility for all TIMS activities including requirements management, cost and schedule management, and risk management for the TIMS product.  The TIMS IPT Leader does technical and cost reporting to the FlightSafety GBTS program management.  The TIMS Software Manager has overall responsibility for the production of the TIMS software products and provides technical leadership in the key areas of requirements analysis, design, product and component interfaces and the development process definition.  The TIMS Test Manager supports the TIMS Software Manager and is responsible for all testing activities, including planning testing, documenting testing, conducting testing through CSCI testing, and supporting Raytheon/Government in-plant and on-site acceptance testing.  The TIMS System Engineer supports the entire TIMS IPT and is responsible for reviewing and coordinating system issues with the GBTS System Engineer and other GBTS IPTs.  SQA supports the entire TIMS IPT and has an independent direct management reporting line to ensure independence.  CM/System Operations supports the entire TIMS IPT structure, is responsible for the SDL, and maintains baselines and the SEE.

FIGURE 7.1.2-1.  Logicon Organization

FIGURE 7.1.2-2  Logicon TIMS IPT Organization

## 7.2  Project Resources

### 7.2.1  Personnel Resources

#### 7.2.1.1  FTD Personnel Resources

Table 7.2.1-1 provides an overview of FTD software development related staffing.  The data represents the maximum number of people assigned during each phase.  Not all personnel are assigned full time.

FTD IPT member qualification requirements are shown in Table 7.2.1-2.

| Responsibility | Sys Req/& Design | SW Req & Prelim Design | SW Detail Design | Code & Unit Test | System Integration & Test |
| --- | --- | --- | --- | --- | --- |
| FTD IPT Leader | 1 | 1 | 1 | 1 | 1 |
| Admin Assistant | 1 | 1 | 1 | 1 | 1 |
| PE/SCM | 1 | 1 | 1 | 1 | 1 |
| QA/Test Manager | 0 | 0 | 0.4 | 0.4 | 1 |
| Flight Dynamics Simulation Engineer | 1.6 | 1.6 | 2.4 | 1.5 | 2.9 |
| Engines Simulation Engineer | 0.4 | 0.4 | 0.5 | 0.4 | 0.7 |
| Aircraft Systems Simulation Engineer | 1.1 | 1.0 | 1.6 | 1.3 | 2.0 |
| Nav/Comm & Visual I/F Simulation Engineer | 1.4 | 1.3 | 2.0 | 1.6 | 2.5 |
| Autopilot/Air data Simulation Engineer | 0.2 | 0.2 | 0.3 | 0.2 | 0.3 |
| Computer Systems Engineer | 2.8 | 2.5 | 4.1 | 3.2 | 5.0 |
| IOS Software Engineer | 1.8 | 2.2 | 4.0 | 4.3 | 2.4 |
| TOTALS | 13.5 | 11.2 | 12.6 | 12.0 | 23.4 |

TABLE 7.2.1-1  FTD IPT Development Staff Loading by Phase (Averages)

| Responsibility | Actual/Anticipated Education Levels (years) | Actual/Anticipated Experience Levels (years) |
| --- | --- | --- |
| FTD IPT Leader | BS | 19 |
| Admin Assistant | HS | 3-5 |
| PE/SCM | BS | 20 |
| SQA/Test Specialist | BS | 10-15 |
| Flight Dynamics Simulation Engineer | BS | 3-5 |
| Engines Simulation Engineer | BS | 3-5 |
| Aircraft Systems Simulation Engineer | BS | 3-5 |
| Nav/Comm & Vis I/F Simulation Engineer | BS | 3-5 |
| Autopilot & Air Data Simulation Engineer | BS | 3-5 |
| Computer Systems Engineer | BS | 5-15 |
| IOS Software Engineer | BS | 3-5 |

TABLE 7.2.1-2  FTD IPT Qualifications

The FTD IPT is organized into functional disciplines that work together to achieve the goals of the project.  A description of the functional organization is given by Table 7.2.1-3.

| FTD Staffing Categories | Description |
| --- | --- |
| FTD IPT Leader | Reports to the GBTS program manager. The FTD IPT Leader is responsible for all requirements management, cost and schedule management, and risk management for the TIMS items. |
| Admin Assistant | Reports to ATD IPT Leader, provides general administrative and clerical support for the staff. |
| Project Engineer & SCM | Reports to the IPT Leader. Provides daily technical direction to the software staff and ensures enforcement of CM policies and procedures. Leads IPT CCA, approves all integration builds. Responsible for tracking & maintaining COTS SW licenses. Ensures IPT compliance with SW procedures. |
| SQA/Test Manager | Reports to the IPT Team Leader. Monitors ATD software development for compliance with JPATS & FSI policies and procedures. Conducts quality audits, ensures operation of corrective action system, maintains test plans and procedures. |
| Flight Dynamics Simulation Engineer | Reports to ATD Team Leader. Responsible for the design, development and testing of Flight, Aerodynamics and Controls System simulation software. |
| Engines Simulation Engineer | Reports to ATD Team Leader. Responsible for the design, development and testing of Propulsion System simulation software. |
| Aircraft Systems Simulation Engineer | Reports to ATD Team Leader. Responsible for the design, development and testing of Ancillary/Utility Systems simulation software. |
| Navigation, Communications & Visual I/F Simulation Engineer | Reports to ATD Team Leader. Responsible for the design, development and testing of Nav/Comm and Avionics simulation software and Visual I/F software. |
| Autopilot & Air Data Simulation Engineer | Reports to ATD Team Leader. Responsible for the design, development and testing of Air Data and Flight Guidance simulation software. |
| Computer Systems Engineer | Reports to ATD Team Leader. Responsible for the design, development and testing of Operating System, Executive System and Utilities software. |
| IOS Software Engineer | Reports to ATD Team Leader. Responsible for the design, development and testing of IOS and applicable RIS simulation, GUI, editor, and TIMS I/F software. |

TABLE 7.2.1-3  FTD IPT Functional Responsibilities

#### 7.2.1.2  TIMS Personnel Resources

Table 7.2.1-4 describes estimated TIMS IPT staff loading by phase and responsibility.  This chart contains TIMS IPT management, administration, and technical software development personnel.  The chart does not contain any staffing for network definition, network installation, and network maintenance activities.

TIMS IPT member qualification requirements are shown in Table 7.2.1-5.

The TIMS IPT is organized into functional disciplines that work together to achieve the goals of the project.  A description of the functional organization is given by Table 7.2.1-6.

| Responsibility | Sys Req | Sys Design | SW Req | Design Arch/ Detailed | Imple-menta-tion | Unit Integ. & Test | CSCI Test | CSCI/ HWCI Integ. | FQT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TIMS IPT Leader | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Program Control Analyst | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Secretary | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 |
| System Engineer | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |
| SQA | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |
| CM/System Ops | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |
| Software Manager | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Test Manager | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| GUI Developer / Tester | 2 | 4 | 7 | 11 | 13 | 13 | 13 | 13 | 1 |
| Database Developer / Tester | 2 | 4 | 7 | 10 | 13 | 13 | 13 | 13 | 2 |
| Application Developer / Tester | 2 | 3 | 5 | 9 | 10 | 10 | 10 | 10 | 2 |
| Technical Writers / Help System Authors | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 0 |
| TOTALS | 16 | 21 | 31 | 43 | 51 | 51 | 51 | 51 | 13 |

TABLE 7.2.1-4  TIMS IPT Development Staff Loading by Phase

| Responsibility | Actual/Anticipated Education Level | Actual/Anticipated Experience Level (years) |
| --- | --- | --- |
| TIMS IPT Leader | PhD | 20 |
| Program Control Analyst | BA | 1-3 |
| Secretary | HS | 3-5 |
| System Engineer | MA/MS | 10 |
| QA | BA/BS | 3-5 |
| CM/System Ops | BA/BS | 1-4 |
| Software Manager | BA/BS | 18 |
| Test Manager |  | 10 |
| GUI Developer / Tester Senior GUI Developer / Tester Mid-Level GUI Developer / Tester Junior GUI Developer / Tester | BA/BS BA/BS BA/BS | 7 5 0-3 |
| Database Developer / Tester Senior Database Developer / Tester Mid-Level Database Developer/Tester Junior Database Developer / Tester | BA/BS BA/BS BA/BS | 7 5 0-3 |
| Application Developer / Tester Senior App. Developer / Tester Mid-Level App. Developer/Tester Junior App. Developer / Tester | BA/BS BA/BS BA/BS | 7 5 0-3 |
| Technical Writers | HS | 5 |

TABLE 7.2.1-5  TIMS IPT Qualifications

| TIMS Staffing Categories | Description |
| --- | --- |
| TIMS IPT Leader | Reports to the GBTS program manager. The TIMS IPT Leader is responsible for all requirements management, cost and schedule management, and risk management for the TIMS items. |
| RAC Software Manager | The RAC on-site Software Manager maintains close coordination with the GBTS subcontractor’s management, participates on the TIMS and OSS IPTs, and provides assistance to the TIMS and OSS development teams to ensure the balanced, integrated development and delivery of the TIMS, CBTS, and MUSS. This includes full involvement in the development processes during all phases of the life-cycle. The RAC GBTS Project Manager also serves as associate member of the GBTS subcontractor’s CCB, and is a performance monitor on RAC’s Award Fee Review Board. |
| FlightSafety Software Process Manager | The FlightSafety on-site Software Process Manager will participate daily in the TIMS and OSS IPTs, will coordinate Technical Performance Measurement (TPM) status reporting with the Logicon OSS IPT Leader, and will monitor progress via direct observation and evaluation of TPM reports. Additionally, the SWPM will be trained in EVMS and will review Logicon EVMS reports, variance analyses, etc. to ensure appropriate GBTS level surveillance of critical OSS/TIMS software development activities. |
| Program Control Analyst | Reports to the TIMS IPT Leader. The Program Control Analyst supports work associated with the EVMS and cost account plans. |
| Secretary | Reports to the TIMS IPT Leader. General secretarial support for entire TIMS staff. |
| System Engineer | Reports to TIMS IPT Leader. Responsible for overseeing reviewing all system requirements and system design activities. Responsible for coordinating system issues and interfaces with other IPTs and the GBTS System Engineer |
| SQA | SQA has management reporting the Logicon upper management and technical reporting to the TIMS IPT Leader. QA monitors TIMS products and processes to ensure compliance with TIMS requirements, software plans, and Logicon procedures. QA audits each deliverable item to ensure quality and acceptability. QA oversees and monitors the corrective action system to ensure that all problems/discrepancies are tracked to closure. |
| CM/System Operations | Reports to the TIMS IPT Leader. Responsible for all CM activities, the SDL and system administrator duties. CM produces all integration, CSCI and system test builds. CM is responsible for distribution of software to all sites during transition to software users and the software support sites (TIMS-SS). CM is also responsible for acquiring, tracking, and maintenance of COTS licenses |
| TIMS Software Manager | Reports to the TIMS IPT Leader. Responsible for planning and overseeing all the software developers and testing. |
| Test Manager | Reports to the TIM Software Manager. Responsible for test planning, test documentation, and test activities for all testing. |
| GUI Developers / Testers | Report to the TIMS Software Manager or Test Manager. Responsible for design, development and testing of the GUI products |

TABLE 7.2.1-6  TIMS IPT Functional Responsibilities

| TIMS Staffing Categories | Description |
| --- | --- |
| Database Developers / Testers | Report to the TIMS Software Manager or Test Manager. Responsible for analysis, design, and testing of databases. |
| Application Programmers / Testers | Report to the TIMS Software Manager or Test Manager. Responsible for analysis, design, and testing of applications (i.e. scheduler, transaction management, etc). |
| Technical Writers | Report to the TIMS Software Manager. Support documentation needs and generation of SDRLs. Duties include authoring the hypertext Help system. |

TABLE 7.2.1-6   TIMS IPT Functional Responsibilities (Continued)

### 7.2.2  Facilities

Locations of development facilities are shown in Table 7.2.2-1.

| Facility | Location |
| --- | --- |
| FlightSafety Services Corporation | 3333 S. Bannock St. Englewood, CO 80110 |
| Logicon | 105 E. Vermijo, Suite 450 Colorado Springs, CO 80903 |
| FlightSafety International Simulation Systems Division | 2700 N. Hemlock Cir. Broken Arrow, OK 74012 |

TABLE 7.2.2-1  Facility Locations

GBTS system requirements analysis and design synthesis are performed by FlightSafety Services Corporation, Logicon RDA, FSI-SSD, and FSI-VSS at their respective facilities.  FTD component and software requirements analysis will be conducted at FSI-SSD.  FTD visual system interface support will be provided by FSI-VSS.

Initial TIMS system requirements analysis and early prototyping will be conducted by Logicon at FlightSafety’s  San Antonio, TX Learning Center facility.  Subsequent TIMS development will be conducted by Logicon at their  Colorado Springs, CO facility.

### 7.2.3  Acquirer-Furnished Equipment and Other Resources

The Government is furnishing the property set forth below and as outlined in the PUSD:

- GFE Courses to be Converted

- GFE TIMS Management Transfer Courses

- Joint Primary Training Syllabus

- AS-IS Logical Model

- Air Force Training System Requirements Analysis

- Chief of Naval Air Training Instructional System Development Analysis

- Current data from other training systems

# 8.0  Notes

## 8.1  Acronyms

| AETC | Air Education and Training Command |
| --- | --- |
| AFB | Air Force Base |
| AFORMS | Air Force Operations Resource Management System |
| AFTMS | Air Force Training Management System |
| AI | Action Item |
| ATD | Aircrew Training Device |
| ATDSS | ATD Support System |
| ATP | Acceptance Test Procedures |
| ATS | Aircrew Training System |
|  | Advanced Training System |
| AV3M | Aviation 3M |
| AWDS | Automated Weather Distribution System |
| CAI | Computer Aided Instruction |
| CAMS | Core Automated Management System |
| CASE | Computer Aided Software Engineering |
| CBTS | Computer Based Training System |
| CCB | Configuration Control Board |
| CDR | Critical Design Review |
| CI | Configuration Item |
| CM | Configuration Management |
| CMP | Configuration Management Procedure |
| CMS | Command Management System |
| CNATRA | Chief of Naval Air Training |
| COTS | Commercial-off-the-shelf |
| CPS | Computer Program System |
| CSC | Computer Software Component |
| CSCI | Computer Software Configuration Item |
| CSOM | Computer System Operator’s Manual |
| CSR | Component Specification Review |
| CSS | Courseware Support System |
| CSU | Computer Software Unit |
| CVT | Contractor Verification Testing |
| DC | Developmental Configuration |
| DDL | Data Definition Language |
| DDN | Defense Data Network |
| DOD | Department of Defense |
| DOORS | Dynamic Object Orientated Requirements System |
| DR | Discrepancy Report |
| DTP | Development Test Procedure |
| ECR | Engineering Change Request |
| EMD | Engineering Manufacturing Development |
| EPT | Egress Procedures Trainer |
| EST | Ejection Seat Trainer |
| EVMS | Earned Value Management System |
| FCA | Functional Configuration Audit |
| FMA | Functional Mission Assessment |
| FTD | Flight Training Device |
| FTHAS | Flying Training History Analysis System |
| FTPAS | Flying Training Programming and Accounting System |
| FTRAP | Flying Training Resource Allocation Program |
| FSI | FlightSafety International |
| GBTS | Ground Based Training System |
| GFE | Government furnished equipment |
| GUI | Graphical User Interface |
| HW | Hardware |
| HWCI | Hardware Configuration Item |
| HSI | Hardware/Software Integration |
| IAW | In Accordance With |
| ICD | Interface Control Document |
| IDD | Interface Design Description |
| IF | Interface |
| IFT | Instructional Flight Trainer |
| IMP | Integrated Master Plan |
| IPD | Integrated Product Development |
| IPT | Integrated Product Team |
| IRS | Interface Requirements Specification |
| ITP | Integrated Test Plan |
| JPATS | Joint Primary Aircrew Training System |
| JPL | Jet Propulsion Lab |
| LAN | Local Area Network |
| LCC | Life Cycle Cost |
| LEIB | Logicon Engineering Instruction Binder |
| LSE | Lead Software Engineer |
| MIME | Multipurpose Internet Main Extension |
| MIPS | Master Integrated Program Schedule |
| MIS | Management Information System |
| MUSS | Modification and Update Support System |
| NAS | Naval Air Station |
| NASA | National Aeronautics and Space Administration |
| NITRAS | Navy Integrated Training Resources Administration System |
| NTSAS | Navigator Training Student Accounting System |
| NTSS | Navigator Training Scheduling System |
| OFT | Operational Flight Trainer |
| OMT | Object Modeling Technique |
| OSS | Operational Support Segment |
| PCA | Physical Configuration Audit |
| PDR | Preliminary Design Review |
| PUSD | Program Unique Specification Document |
| PM | Program/Project Manager |
| PMO | Program Office |
| PPT | Parachute Procedures Trainer |
| PR | Problem Report |
| PST | Product Support Team |
| PTD | Procedure Training Device |
| QA | Quality Assurance |
| QAP | Quality Assurance Procedure |
| QAPP | Quality Assurance Program Plan |
| QAM | Quality Assurance Manual |
| QER | Quality Evaluation Record |
| RAC | Raytheon Aircraft Corporation |
| RDM | Rapid Development Methodology |
| RFC | Request for Comments |
| RFP | Request for Proposal |
| SAP | Site Activation Plan |
| SCR | Software change request |
| SCM | Software Configuration Management |
| SCMP | Software Configuration Management Plan |
| SDD | Software Design Description |
| SDF | Software Development File |
| SDL | Software Development Library |
| SDP | Software Development Plan |
| SDR | System Design Review |
| SDRL | Subcontract Data Requirements List |
| SE | Software or System Engineer |
| SEE | Software Engineering Environment |
| SEMP | System Engineering Management Plan |
| SEP | Software Engineering Procedure |
| SEPP | Software Engineering Practices and Procedures |
| SES | Software Engineering Standard |
| SLC | Software Life Cycle |
| SLE | Software Lead Engineer |
| SLFE | System Level Formative Evaluation |
| SLOC | Source Lines of Code |
| SME | Subject Matter Experts |
| SOF | Supervisor of Flying |
| SOW | Statement of Work |
| SPMO | System Program Office |
| SPR | Software Problem Report |
| SPS | Software Product Specification |
| SQA | Software Quality Assurance |
| SQL | Structured Query Language |
| SRR | System Requirements Review |
| SRS | Software Requirements Specification |
| SS | System Specification |
| SSD | Simulation Systems Division (of FSI) |
| SSDD | System/Subsystem Design Description |
| SSL | Secure Socket Layer |
| SSP | System Safety Plan |
| SSR | Software Specification Review |
| STASS | Standard Training Activity Support System |
| STASS-FLT | STASS - Flight |
| STD | Software Test Description |
| STF | Software Test Folder |
| STP | Software Test Plan |
| STRR | Site Test Readiness Review |
| SUM | Software User’s Manual |
| SVD | Software Version Description |
| SW | Software |
| T&E | Test and Evaluation |
| TBD | To Be Determined |
| TC | Training Configuration |
| TIMS | Training Integrated Management System |
| TD | Test Description |
| TIMS-SS | TIMS Support System |
| TIS | Training Integration System |
| TMS | Training Management System |
| TP | Test Plan |
| TRIM | Time Related Instructional Management |
| TRR | Test Readiness Review |
| UFT | Undergraduate Flight Training |
| USAF | United States Air Force |
| UTD | Unit Training Device |

# APPENDIX A: SDP/MIL-STD 498 TAILORING CROSS-REFERENCE

The following table describes the proposed tailoring to MIL-STD-498:

| Reference Paragraph | Tailoring/Justification |
| --- | --- |
| 5.1.4, 6.2 | Remove DI-IPSC-81428, Software Installation Plan - Software installation plans will be addressed within the Site Activation Plan |
| 5.1.5, 6.2 | Remove DI-IPSC-81429, Software Transition Plan - Software transition planning will be covered in the Site Activation plan for the support site(s) |
| 5.3.2, 6.2 | Remove DI-IPSC-81430, Operational Concept Description - Operational concerns will be addressed in the appropriate PUSD |
| 5.3.3, 6.2 | Replace DI-IPSC-81431, System/Subsystem Specifications with DI-SDMP-81493/T, Program Unique Specification Documents |
| 5.3.3, 6.2 | DI-IPSC-81434, Interface Requirement Specifications will be developed for TIMS only |
| 5.4.1, 5.4.2, 5.13.5, 6.2 | DI-IPSC-81432, System/Subsystem Design Description will be developed for TIMS and FTD only |
| 5.4.1, 5.4.2, 5.6.1, 5.6.2, 5.6.3, 6.2 | Remove DI-IPSC-81436, Interface Design Description - Interface Design data will be contained within the SDD, additional interface documents may be produced as needed. |
| 5.6.1, 5.6.2, 5.6.3, 6.2 | DI-IPSC-81435, Software Design Description will be developed for TIMS and FTD only and will be delivered with the SPS. |
| 5.4.1, 5.6.1, 5.6.3, 6.2 | Remove DI-IPSC-81437, Database Design Description - Databases will be COTS tools |
| 5.9.3, 5.11.3, 6.2 | DI-IPSC-81439, Software Test Descriptions will be utilized for TIMS only. DI-NTDI-80603/T will be used for ATD components. |
| 5.12.2, 5.13.3, 6.2 | Remove DI-IPSC-81442, Software Version Description this data will be a subset of the Software Product Specifications. |
| 5.12.3.2, 6.2 | Remove DI-IPSC-81445, Software Input/Output Manual - pertinent data will be contained within the SUMs |
| 5.12.3.3, 6.2 | Remove DI-IPSC-81444, Software Center Operator Manual - pertinent data will be contained within the SUMs and other operational support documents |
| 5.12.3.4, 6.2 | Remove DI-IPSC-81446, Computer Operation Manual - COTS software will provide for operations manuals and format for additional information. |
| 5.13.6.1, 6.2 | Remove DI-IPSC-81447, Computer Programming Manual - COTS programming manuals will be supplied |
| 5.13.6.2, 6.2 | Remove DI-IPSC-81448, Firmware Support Manual - Necessary data will be contained within the simulators SPS and other support documents |

TABLE A.1-1 MIL-STD-498 Tailoring

# APPENDIX B:  FTD Supplemental Software Planning Data

## B.1  Software Size Estimates

The following table defines the language used, provides the total size, the design reuse size and the code reuse size for each module in the JPATS FTD Central Training Complex (CTC) and Instructor Operator Station (IOS).

| DEPARTMENT | Target Lang. | New LOC | Mod’d LOC | Reuse LOC | COTS/NDI LOC | Data Tabs or GUI Screens |
| --- | --- | --- | --- | --- | --- | --- |
| D61 FLIGHT |  |  |  |  |  |  |
| Initializations | Ada95 | 210 | 0 | 0 | 0 | 0 |
| Auto Test A | Ada95 | 4,360 | 0 | 0 | 0 | 0 |
| Auto Test B | Ada95 | 4,460 | 0 | 0 | 0 | 0 |
| Flt & Aero | Ada95 | 3,120 | 0 | 0 | 0 | 250 |
| CLU | Ada95 | 1,000 | 0 | 0 | 0 | 0 |
| Flight Instruments | Ada95 | 1,790 | 0 | 0 | 0 | 0 |
| Total Flight |  | 14,940 | 0 | 0 | 0 | 250 |
| D62 ENGINES | Ada95 | 550 | 1,400 | 0 | 0 | 190 |
| D63 AIRCRAFT SYSTEMS | Ada95 | 4,700 | 3,750 | 870 | 0 | 110 |
| D64 IOS | C++ | 4,500 | 2,500 | 2,500 | 0 | 250 |
| D65 Navigation & Vis I/F |  |  |  |  |  |  |
| Nav Systems | Ada95 | 3,150 | 2,940 | 3,150 | 0 | 0 |
| Nav D/B Acc | C++ | 1,800 | 0 | 0 | 4,800 | 0 |
| Nav D/B PPI | C++ | 0 | 0 | 0 | 4,600 | 0 |
| Nav D/B PPO | C++ | 0 | 0 | 0 | 4,400 | 0 |
| Nav D/B CPI | C++ | 0 | 0 | 0 | 3,700 | 0 |
| Nav D/B CPP | C++ | 0 | 0 | 0 | 4,300 | 0 |
| Nav D/B CPO | C++ | 0 | 0 | 0 | 2,900 | 0 |
| Visual IF I/F | Ada95 | 2,400 | 0 | 0 | 0 | 0 |
| Visual R/T I/F | Ada95 | 3,650 | 0 | 0 | 0 | 0 |
| Total Navigation & Vis I/F |  | 11,000 | 2,940 | 3,150 | 24,700 | 0 |

TABLE B.1-1  FTD CTC/IOS Sizing Estimates

| DEPARTMENT | Target Lang. | New LOC |  | Mod’d LOC |  | Reuse LOC | COTS/NDI LOC | Data Tabs or GUI Screens |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D68 Computer Systems |  |  |  |  |  |  |  |  |
| Math Utilities | Ada95 | 400 | 300 |  | 1,400 |  | 0 | 0 |
| I/O Software | Ada95 | 2,500 |  | 0 |  | 0 | 0 | 0 |
| Scheduler | Ada95 | 2,000 |  | 3,000 |  | 1,600 | 0 | 0 |
| Task Utilities | Ada95 | 500 |  | 0 |  | 1,000 | 0 | 0 |
| Symbol Table Def'n | Ada95 | 4,900 |  | 1,000 |  | 600 | 0 | 0 |
| Timing S/W | Ada95 | 1,600 |  | 0 |  | 0 | 0 | 0 |
| Record/Playback | Ada95 | 12,100 |  | 0 |  | 0 | 0 | 0 |
| I/O Diagnostics | Ada95 | 2,000 |  | 0 |  | 0 | 0 | 0 |
| Sim'n Monitor | Ada95 | 4,000 |  | 1,000 |  | 0 | 0 | 0 |
| IOS I/F | C++ | 600 |  | 700 |  | 2,000 | 0 | 0 |
| R/T Debugger | Ada95 | 14,000 |  | 0 |  | 0 | 0 | 0 |
| CSG-CM | C++ | 2,400 |  | 0 |  | 0 | 0 | 0 |
| Total Computer Systems |  | 47,000 |  | 6,000 |  | 6,600 | 0 | 0 |
| D69 AUTOFLIGHT/AIR DATA | Ada95 | 820 |  | 670 |  | 0 | 0 | 0 |
| TOTAL FTD 138,590 |  | 83,510 |  | 17,260 |  | 13,120 | 24,700 | 800 |

TABLE B.1-1  FTD CTC/IOS Sizing Estimates (Continued)

# APPENDIX C:  TIMS Supplemental Software Planning Data

## C.1  Software Architecture

The following figure shows initial concepts for TIMS architecture

FIGURE C.1-1  TIMS Architecture

## C.2  Size Estimates

The following table contains preliminary sizing estimates for TIMS components.

| Component | COTS Modules and Products | New Development Modules | New Dev Lang(s) | New Dev KSLOC |
| --- | --- | --- | --- | --- |
| Core/AM | Client Op Sys (NT Workstation) |  |  |  |
|  | Net Op System (NT Server) |  |  |  |
|  | E-mail/board (Exchange Server and Client) |  |  |  |
|  | Virus protection (TBD -- *Dr Solomon's Server and Client) |  |  |  |
|  | RDBMS (MS SQL Server) |  |  |  |
|  | Net mgt (HP OpenView) |  |  |  |
|  | Sys mgt, diagnostics, and net install (MS Sys Mgt Server) |  |  |  |
|  | Net-managed backup (SeaGate Backup Express) |  |  |  |
|  | Help desk (TBD -- *PhD Enterprise) |  |  |  |
|  | Help systems (MS Help) |  |  |  |
|  | Installation scripts (TBD -- *InstallShield licensed in MS toolkits) |  |  |  |
|  | Report Generation (TBD -- *InfoMaker) |  |  |  |
|  | Office Automation (MS Office Pro) |  |  |  |
|  | Event Manager GUI (C++, not counted in SLOC) | Event Manager engine | C++ | 1 |
|  | Security Manager GUI (C++, not counted in SLOC) | Security Manager engine | C++ | 2 |
| Sched Mgt | Fly Plan Gen GUI (Excel) | Fly Plan Gen Engine | C++, Excel | 3 |
|  | PFT Gen GUI (Excel) | FFT Gen Engine | C++, Excel | 3 |
|  | Wing/Sqdn/Flt Actuals Support GUIs (Excel) | Wing/Sqdn/Flt Act Supp Engines | C++, Excel | 6 |
|  | HQ/Wg/Sqdn Schedulers GUIs (Excel) | HQ/Wing/Sqdn Schedulers Engines | C++, Excel | 28 |
|  | Academic Scheduler GUI | Academic Scheduler interface to engine | Ada, PB | 12 |
|  | Flight Scheduler GUI (PB) | Flt Scheduler interface to engine | Ada, PB | 27 |
|  | ROSE (Sched Engine) (reuse/modify 30K of existing source code -- see note re sizing) |  |  | Ada | 2 |
| Res/CM/Log | Personnel/Academic/ATD/AC Resource Managers GUIs (TBD -- *PB) | Personnel/Academic/ATD/AC Resource Managers engines | C++ | 13 |
|  | Purchase Order Mgr GUI (TBD -- *PB) | Purchase Order Mgr engine | C++ | 1 |
|  | TIMS Manager GUI (TBD -- *PB) | TIMS Mgr engine | C++ | 2 |
|  | Airspace Manager GUI (Excel) | Airspace Manager engine | C++, Excel | 2 |
|  | Weather Manager GUI (PB and MS Web Browser) | Weather Manager engine | C++, HTML | 2 |
| Perf Meas | Tng Records (Electronic Gradebook) GUI (PB) | Tng Records engine (including CBTS/FTD interfaces) | C++ | 9 |
|  | Course Evaluator GUI (TBD -- *PB) | Course Evaluator engine | C++ | 4 |
| Curr Mgt | Syllabus Manager (TBD -- Visual WorkFlow) | Syllabus Manager engine | C++ | 4 |
|  | FTD Sortie File Manager GUI (PB) | FTD Sortie File Engine | C++ | 2 |
| TOTALS | N/A | N/A | N/A | 123 |
|  | * indicates placeholder for TBD COTS products |  |  |  |
|  | PB abbrev for PowerBuilder |  |  |  |

TABLE C.2-1  TIMS Software Modules

## C.3  Estimated Use of Critical Computer Resources

The following chart summarized the preliminary TIMS estimates for computer transactions:

|  | Network Location | Key Transaction(s) | Size (Bytes and bits) | Frequency |
| --- | --- | --- | --- | --- |
| Within Workgroups |  |  |  |  |
|  | USAF Flight Room and USN Ready Room | - access gradebook for review - grade sortie and update activity record - view flight schedule | ~ 500KByte (4000Kbit) ~2KByte (16Kbit) ~200KByte (800Kbit) | each transaction type: USAF: Burst, 10-30x times during 30-45 min before/after fly (2-3 periods/day) USN: evenly throughout day; about same total transactions as USAF |
|  | CAI Lab | - Load CAI lesson - Transfer item analysis | ~300 MB (2400 Mbit) ~1 KB (8 Kbit) | At CAI session start (local) At CAI session end |
|  | Sim Center (RIS/IOS) | - access lesson sortie file | ~1 MB (8 Mbit) | Before or during sim sortie |
|  | Wing Ops | - Transfer A/C maintenance schedules - Transfer weather updates | ~800Kbit ~8Kbit | Start of day Start of day & ad hoc |
|  | Squadron Ops | - send/update daily sqdn sched and actuals to flights - send/update daily flight schedule to sqdn | ~1MByte (8Mbit) ~200KByte (800Kbit) | once a day and ad hoc updates once a day and ad hoc updates (surge during changing weather) |
| Between Workgroups (“horizontal” flow) |  |  |  |  |
|  | Flight/ready room <-> Sqdn Ops | - send/update daily sqdn sched and actuals to flight/ready rooms - send/update daily flight schedule to sqdn - replicate gradebooks and activity record at squadron | ~1MByte (8Mbit) ~200KByte (800Kbit) ~4Mbit/gradebook, 16Kbit/activity record | once a day and ad hoc updates once a day and ad hoc updates (surge during changing weather) each transaction type: USAF: Burst, 10-30x times during 30-45 min before/after fly (2-3 periods/day) USN: evenly throughout day; about same total transactions as USAF |
|  | Flight/ready room <-> Sim Center | - access gradebook for review - grade sortie and update activity record | ~4 Mbit/sim ~16 Kbit | During briefing During debriefing |
|  | Flight/ready room <-> CAI Lab | - access reduced gradebook for review - grade CAI and update activity record | 2 Kbyte = 16 Kbit ~16 Kbit | At CAI session start At CAI session end |
|  | Sim Center <-> Acad Ops | - transfer JPATS scenario playback files | ~16 Mbit | At sim sortie end |
| Aggregation (“uphill” flow) |  |  |  |  |
|  | Sqdn --> Wing | - Replicate gradebook and activity records - Transfer sqdn schedule and results | 8Kbit/gradebook, 8Kbit/record 1 MB/8 Mbit | Daily Start of day & ad hoc updates End of day & ad hoc updates |
|  | Wing --> HQ | - Transfer gradebook and activity records - Transfer base schedule and results | 4Kbit/gradebook, 1Kbit/record 40Mbit | End of day End of day |
| Dissemination (“downhill” flow) |  |  |  |  |
|  | HQ --> Wing | - Transfer some courseware updates - Send management data - Exercise TIMS management functions |  |  |

TABLE C.3-1  TIMS Computer Transactions Estimates

## C.4  Preliminary TIMS Database Technical Assessments

To provide distributed database support in a heterogeneous environment, the TIMS IPT addressed the following several key technical database issues

Distribution of data:  TIMS data will be distributed in Microsoft SQL Server databases throughout the TIMS network.  The data will be distributed so that the data owned by a particular organization will reside on the local server for that organization.  For example, grade book data for a flight will be kept on that flight’s server.  This will enhance performance, and simplify update of duplicated data.  Using object-oriented principles,  all of the attributes of an object will be stored together in the same database.  As a result, updates will generally occur locally, with little need to do cross database/cross server updates.  If a remote user who is not the owner needs to update data, then the remote user will send a message to an owner and request update of the data.  After the data is updated, Microsoft SQL Server will automatically duplicate the change in any replicated copies of the data.  SQL Server allows the creation of a single distributed transaction that updates multiple servers while enforcing data integrity and consistency.  If the workstation or any server were to crash, the partial transactions on all other servers would be rolled back automatically.

Data Replication.  Data may be replicated on multiple servers for two reasons: hot backup and performance.  For example to improve performance, we may choose to replicate the wing schedule data on the flight server.  To provide a hot backup in case of server failure, we have decided that all databases will be replicated up to the next higher command level server.  For example, flight databases will be replicated for backup purposes on the squadron server.  Microsoft SQL Server provides support for keeping the replicated databases up-to-date.  The replicated copies will be read-only.  Only the original master “golden” database can be updated and then updates will be distributed automatically by SQL Server to the replicated copies.  Our initial plan for data distribution and replication is described and illustrated in a figure in Vol 1, Section 1.3.2.10 of the proposal.  To support a distributed, hierarchical database structure, a Microsoft SQL Server within each workgroup will store TIMS data, using the product’s replication capabilities to transparently support upward redundancy.  If a primary database fails, the parent is the “hot backup”.  The system performs the switch automatically, without manual intervention to ensure minimal disruption.  Upon restoration, the primary database will resynch with the parent to resolve any write transactions occurring during down time.  Our replication strategy supports real-time mirroring of workgroup database write transactions to the immediate parent and periodic mirroring to higher levels in the hierarchy (e.g., base Archive for flight-level databases).  This strategy minimizes network traffic and processing, while still providing highly reliable service and data integrity.

Data Access  TIMS users will access data stored in Microsoft SQL Server databases using either PowerBuilder generated GUI, InfoMaker, or English Wizard.  These tools will be integrated so that the user will have a common interface to all three capabilities.  The integrated user GUI will interface with Microsoft SQL Server which provides both an SQL and ODBC interface to provide data access.  TIMS users will not need to know SQL to be able to access the data in the databases.  Microsoft SQL Server will insure the data integrity of the data accessed by the user.  In the TIMS application, users need to be able to access data that they have permission to access from any TIMS client terminal, whether it is attached to the server that the data resides on, or attached to another server somewhere else in the network.  One example of this need is to support the instructor’s use of the grade book, stored on the flight’s server, from a TIMS terminal near the simulators.  To accomplish this, the JPATS TIMS application software can identify the appropriate server to connect with.  Microsoft SQL Server provides both an ANSI SQL compliant interface and an ODBC interface.  These interfaces can be used by developers to define stored procedures, triggers, rules, data types, and so forth that provide application data integrity and simplify data access.  While end users could access the data using SQL, they are not required to know SQL to use the PowerBuilder/ InfoMaker/ English Wizard interface which will be provided as part of our TIMS solution.  For TIMS, PowerBuilder will be used to design the user interface to the database, providing forms for data entry of gradebook data and other data to be stored in Microsoft SQL Server.

Data Integrity and Currency.  A critical issue of multi-user distributed database design and implementation is how to control data integrity and concurrency such that: (1)Many users can have coordinated access to the same data at the same time, (2)A user always sees a consistent view of the data and is prevented from making changes that would make the data inconsistent, and (3) Data integrity is enforced within a single server and across multiple servers so that the data always reflects appropriate organizational and business policies.  If a database management system fails to implement the appropriate data concurrency, integrity and consistency features, users can experience significant problems of lost updates, inconsistent data, and inaccurate results.  Microsoft SQL Server 6.5 actively enforces data integrity and concurrency in distributed multi-user environments through dynamic page and row locking, server-enforced data integrity, and advanced distributed database capabilities.  To guard against potential data inconsistency between multiple servers, SQL Server performs distributed updates using a two-phase commit protocol that preserves the integrity of distributed transactions.  This allows an organization to preserve the consistency of data across multiple servers when it is partitioned in a distributed environment.  The TIMS application developers also use triggers, rules, default values, user-defined data types,  and stored procedures to implement business rules and data constraints.  With these capabilities, checks can be made on the data when it is inserted, updated, or deleted, to insure its integrity.  Checks can be made to insure that the right type of data is being entered, and that is appears to be in the correct format.  Semantic checks can also be made to insure that the data follows established business rules.  Triggers prevent incorrect, unauthorized or inconsistent changes to data and allow the developer to enforce data integrity and complex business policies centrally in the server, instead of having to program this logic into individual applications.  Rules enforce data integrity centrally at the individual column level.  Rules can automatically require that a value fall within a particular range, appear within an explicit list, or even match a string pattern.  Default settings cause a standard value to be inserted in a column if the user does not supply one.  The TIMS developers use a well-chosen combination of stored procedures, triggers, rules, defaults, and data types to ensure the integrity of the JPATS data

Data Security  From a security standpoint, TIMS carefully controls access to data.  The only way to view or modify databases is to use the TIMS applications designed to perform those functions.  Only registered users have access to TIMS terminals, and then only to the applications and functions they are authorized to use.  These security features are built into the operating system, network management software, and RDBMS themselves; the only development effort is that associated with configuring those features to meet the unique needs of CNATRA and AETC.  Some of the security features provided by Microsoft SQL Server include a single login ID for network and database which provides enhanced security and reduces administrative complexity,  password and network data steam encryption which improves inter-network data security, and stored procedure encryption to preserve integrity and security of server-based procedural application code.  SQL Server implements comprehensive user-level permissions on tables, views, stored procedures, and SQL commands.  It also supports field-level security.  And, because permissions can also be applied to groups, security is easy to implement and administer.  SQL Server also directly integrates with the Windows NT operating system security to provide a single logon to both network and database resources, with advanced password aging and user account lockout control.  New encryption services provide secure over-the-wire data encryption between clients and servers for the highest level of distributed security.  In addition, the TIMS developers use pre/post-connect SQL statement event handlers to provide an audit trail whenever a user adds, modifies, or deletes which piece of data.

Database Recovery: Database recovery will be insured by several means.  First, every database will be mirrored so that if one server goes down, the mirror copy of the database can be used until the broken-down server can be restarted.  Upon restart, the original database will be synchronized with its temporary replacement and then given back control of the data.  Second, log files will be maintained on the same server as database so that the database can be recovered independently of the rest of the network, if needed.  Third, the databases will be archived on a daily basis, and the archives stored in a separate location, so major disasters can also be recovered from.  In case of system failure (operating system crashes, power outages, etc.), SQL Server's automatic recovery mechanism recovers all databases to the last state of consistency in a matter of minutes, with no administrator intervention.

Database Administration: Microsoft SQL Server databases can be administered using Enterprise Manager and SQL Executive.  Enterprise Manager allows administration of all distributed SQL Servers from a single client and provides a graphical administrative tool that gives the Data Base Administrator a composite view of each copy of SQL Server distributed on a network.  SQL Executive is a task scheduling and alert facility utility that allows the automation of routine maintenance work.  Routine system maintenance, include backups and diagnostic monitoring, are completely automated, fully configurable functions built into the network operating system.  The TIMS System Administrator at each base, together with the operators of the TIMS Support System have access to all system management tools, including those required to remotely configure, diagnose, and control any workstation within their domains.

Heterogeneous Access:  TIMS network and database design support interoperability and data exchange with current future DoD systems in several ways.  The TIMS network and database design supports an open architecture.  All associated COTS products such as the RDBMS and networking protocols, adhere to industry and government standards to include SQL and TCP/IP.  Microsoft SQL Server specifically supports industry standards including ANSI SQL-92 and FIPS 127-2 compliance using the NIST 5.1 certification suite, XA support for managing SQL Server as a resource with XA-compliant transaction processing monitors, and SNMP MIB and SNMP traps for monitoring SQL Server with SNMP-based management tools.  Microsoft SQL Server (sometimes with the aid of some third-party software)  is interoperable with many existing databases.  Heterogeneous replication allows SQL Server data to be automatically published to non-SQL Server systems including IBM DB2®, ORACLE®, SYBASE®, and Microsoft Access.  SQL Server can replicate information dynamically as changes occur (transaction-based) or scheduled ‘snapshots’ of tables and objects including TEXT and IMAGE data types.  ODS-based gateways from Information Builders, Showcase, Micro Decisionware (MDI/Sybase) enable interoperation with DB2, Oracle, Sybase, etc.  ODBC/DRDA drivers in Microsoft SNA Server or from third parties allow SQL Server clients to access DB2 in MVS, SQL/DS in VM, DB2/400 in OS/400.  Furthermore, we are examining the possibility of adding additional middleware to the JPATS TIMS architecture to better support access to heterogeneous distributed databases.  A class of products called database gateways can be an essential form of middleware.  Options that we have considered include database gateways, message-oriented middleware (MOM), object-request brokers, and transaction monitors.

## C.5  Management Practices

The TIMS IPT uses the following management procedures, directives and guidelines (documented in the TIMS Project Instruction Binder) to plan and implement TIMS:

Software Engineering Directive for Software Planning (SED-002),

Software Engineering Procedure for Estimating Software Size (SEP-002)

Software Engineering Procedure for Monitoring Development Status (SEP-003)

Software Engineering Procedure for Reporting Software Size (SEP-005)

Software Engineering Procedure for Defining Software Labor (SEP-007)

Software Engineering Procedure for Reviewing Software Project Commitments (SEP-008),

Software Engineering Procedure for Preparing and Revising Software Development Plans (SEP-009)

Software Engineering Procedure for Estimating Critical Computer Resources (SEP-010).

Software Engineering Procedure for Software Risk Management (SEP-014)

Software Engineering Process Description for Inspections (SER-020)

Software Engineering Process Description for Track and Oversee the Process (SER-022)

Software Engineering Process Description for Prepare Deliverable Documents (SER-023)

Software Engineering Process Description for Conduct Reviews (SER-024)

TABLE C.5-1  TIMS Management Procedures, Directives, and Guidelines

# appendix D:  SDP/SOW Cross reference

| SDP Paragraph | SOW Reference |
| --- | --- |
| 1.2.1 | 5010 |
| 2.0 | 2020 |
| 3.0 | 5020.1.9 |
| 3.1.1 | 5010.3 |
| 3.1.2 | 5010.4 |
| 3.1.2.1 | 5010.4.1 |
| 3.1.2.1.1 | 5010.4.1.1 |
| 3.1.2.1.2 | 5010.4.1.2 |
| 3.1.2.2 | 5010.4.2 |
| 3.1.3 | 5010.4.3 |
| 3.2 | 5020.3.2.4, 5050.3-3.2 |
| 3.6.5 | 5020.2.2 |
| 4.0 | 5020.2.1 |
| 4.1 | 5020.1.3 |
| 4.2.4.2 | 7010.4.1 |
| 4.2.7 | 5020.2.1.1 |
| 5.1 | 5020.1.1.7, 5020.1.9 |
| 5.1.1 | 5020.1.3 |
| 5.1.2 | 5020.1.3.1, 5030.5.1 |
| 5.1.2.1 | 5030.2-2.2.2 |
| 5.1.2.2 | 5030.5-5.1.1 |
| 5.1.2.3 | 5030.5.2, 5030.5.3, 5030.6 |
| 5.1.3 | 5030, 5030.1.5-1.7, 5030.7 |
| 5.1.3.1 | 5030.5.1.1 |
| 5.1.4 | 5080-1.1, 5080.2.1-2.2, 5080.3 |
| 5.1.5 | 5080.2.3, 6040-1.5 |
| 5.3 | 5020.1.1.11, 5020.1.7.1 -1.7.2 |
| 5.3.1 | 5040.1.2 |
| 5.4 | 5020.1.1.13, 5020.1.7.2 |
| 5.5 | 5020.1.7.2 |
| 5.6 | 5020.1.1.14, 5020.1.1.15 |
| 5.6.2 | 5020.1.1.14 |
| 5.6.3 | 5020.1.1.15 |
| 5.7 | 5020.1.3.1 |
| 5.8 | 5020.1.3.1 |
| 5.9.5.2 | 5030.5.1 |
| 5.9.7 | 5020.1.3.1, 5030.1.6 |
| 5.10 | 5030.1.3 |
| 5.10.1 | 5020.1.3.1 |
| 5.10.2.1 | 5030.2.1, 5030.2.1.1, 5030.2.1.5 |
| 5.10.2.2 | 5030.5.1 |
| 5.11 | 5030.2.1.6, 5030.5.1.1-5030.7 |

| SDP Paragraph (Cont’d) | SOW Reference (Cont’d) |
| --- | --- |
| 5.11.2 | 5030.2.1.6 |
| 5.11.3 | 5030.5.1, 5030.3.2.1.1 |
| 5.11.4.1 | 5030.2.1.6 -.7 |
| 5.11.4.2 | 5030.5.1.1 |
| 5.11.5 | 5030.2.1.8 |
| 5.11.5.2.3 | 5030.7 |
| 5.12 | 5020.1.7.3 |
| 5.12.4 | 5080.2-2.6 |
| 5.13 | 5020.1.3.3, 5020.1.7.3, 5080.2.1-2.6 |
| 5.14 | 5020.2.5 |
| 5.14.1 | 5020.1.7-1.7.3 |
| 5.14.1.1 | 5020.2.5.1 |
| 5.16 | 5020.1.4.2 |
| 5.17 | 5030.1.4 |
| 5.18 | 5020.1.1-1.1.16 |
| 5.18.1 | 5020.1.1.1-1.1.16 |
| 5.18.2 | 5020.1.1-1.1.1, 5020.1.1.7, 6020.1.1.1 |
| 5.19 | 5020 |
| 5.19.1.2 | 5020.2.4.1 |
| 5.19.2 | 5020.2.3-2.4 |
| 5.19.3 | 7010.4.1 |
| 6.0 | 5020.2.4 |
| 7.0 | 5020.2.1 |

# APPENDIX E:  ISO-9001 Requirements Compliance Matrix

## E.1  FlightSafety ISO-9001 Requirements Compliance Matrix

Table  E-1 demonstrates the complete coverage of ISO-9001 requirements.

| ISO-9001 Requirements | FSI Compliant Process and Documents |
| --- | --- |
| 4.1 Management responsibility 4.1.1 Quality policy 4.1.2 Organization 4.1.2.1 Responsibility and authority 4.1.2.2 Resources 4.1.2.3 Management representatives 4.1.3 Management review | QAM-1000 Section 3.2 Q-1700: New or Pending Contract Quality Requirements Analysis, QAM-1000 Section 5.3 QAM-1000 Section 3.1 QAM-1000 Section 3.2 - 3.2.3, Q-1300 Q-1710: New or Pending Contract Quality Requirements Analysis QAM-1000 Section 3.1.1, Q--3220: Management Audit of Quality Assurance, Q-1510: Quality Inspection and Evaluation Records Q--3220: Management Audit of Quality Assurance, Q-1510: Quality Inspection and Evaluation Records |
| 4.2 Quality system 4.2.1 General 4.2.2 Quality system procedures 4.2.3 Quality Planning | Q-1700: Quality Planning, Q-3000: Quality Assurance Audits of Products and Systems, Q-4010: Document Certification Procedure Q-1710: New or Pending Contract Quality Requirements Analysis Q-1700: Quality Planning, Q-1710: New or Pending Contract Quality Requirements Analysis QAM-1000 appendices Q-1710: New or Pending Contract Quality Requirements Analysis, Q-1700: Quality Planning, Q-3000: Quality Assurance Audits of Products and Systems, Q-4010: Document Certification Procedure, H-2110: Calibration System Responsibilities, H-2120: Calibration Control and Recall, H-2140: Certification of Measuring & Test Equipment & Test Procedures, Q-10000 through Q-10050: Formal/Informal Review Procedures, H-6100 through H-6140: Inspection and Testing Procedures, Q-2010: Quality Assurance Reports |
| 4.3 Contract review 4.3.1 General 4.3.2 Review 4.3.3 Amendment to a contract 4.3.4 Records | Q-1710: New or Pending Contract Quality Requirements Analysis Q-1710: New or Pending Contract Quality Requirements Analysis Q-1710: New or Pending Contract Quality Requirements Analysis, H-3100: Source Inspection H-7150: Request for Deviation or Waiver Q-7010: Agenda Certification Procedures, Q-10000: Formal Reviews |
| 4.4 Design control 4.4.1 General 4.4.2 Design and development planning 4.4.3 Organizational and technical interfaces 4.4.4 Design input 4.4.5 Design output 4.4.6 Design review 4.4.7 Design verification 4.4.8 Design validation 4.4.9 Design changes | Q-1000: Quality Procedures (Initiation/Revision) Q-1000: Quality Procedures (Initiation/Revision), S-10010: Software Specifications Review S-1000: Software Management and Engineering Practices, S-3000: Software Environment Audit Procedures, S-4010: Software Code and Software Development Files Certification Q-10030: Preliminary Design Review, H-5120: Process Control S-10010: Software Specifications Review Q-4010: Documentation Certification Procedures H-1120: Design Review Participation, Q-4010: Documentation Certification Procedures, S-3000: Software Environment Audit Procedures, S-4010: Software Code and Software Development Files Certification H-5110: In-Process Inspection H-6110: First Article Inspection, Q-4010: Documentation Certification Procedures H-7150: Request for Deviation or Waiver, QAM-1000 Section 5.12, Q-9000: Discrepancy Reporting, Q-9100: Corrective Action Process, Q-9500: Supplier Corrective Action |

TABLE E-1  FlightSafety ISO-9001 Requirements Compliance Matrix

| ISO-9001 Requirements | FSI Compliant Process and Documents |
| --- | --- |
| 4.5 Document and data control 4.5.1 General 4.5.2 Document and data approval and issue 4.5.3 Document and data changes | Q-4010: Documentation Certification Procedures Q-8010: Deliverable Documentation Review, Q-8020: Procurement Document Quality Requirement Review Q-4010: Documentation Certification Procedures, Q-6010: Protecting Product Quality, Q-6020: Data Submittal Certification Procedures, Q-6030: Shipping Audit Q-9100: Corrective Action Process |
| 4.6 Purchasing 4.6.1 General 4.6.2 Evaluation of subcontractors 4.6.3 Purchasing data 4.6.4 Verification of purchased product 4.6.4.1 Supplier verification at subcontractor’s premises 4.6.4.2 Customer verification of subcontracted product | H-3000: Supplier/Subcontractor Quality Compliance H-4130: Receiving Inspection H-6100: Inspection/Test Instructions H-3110: Source Inspection, H-3120: Contracted Source Inspection, H-3130: Supplier Quality Rating Q-3100: Quality Assurance Audits of Subcontractors and Suppliers, Q-3500: Request for Candidate Supplier Quality Evaluation, Q-3510: Inspection at Subcontractor or Vendor Facilities, Q-3515: Quality Survey Candidate Supplier, Q-3520: Quality Survey of Candidate Supplier or Subcontractor, Q-3530: Candidate Supplier/Subcontractor Quality Evaluation Report Q-3520: Quality Survey of Candidate Supplier or Subcontractor, Q-4010: Documentation Certification Procedures Q-3540: Supplier Process Certification, H-4130: Receiving Inspection, H-1210: Indication of Inspection Status Q-3510: Inspection at Subcontractor or Vendor Facilities H-6100: Inspection/Test Instructions |
| 4.7 Control of customer-supplied product | Q-1000: Quality Procedures (Initiation/Revision) |
| 4.8 Product identification and traceability | Q-3210: C&DM Audit Procedures |
| 4.9 Process control | S-1000: Software Management & Engineering Practices, S-3000: Software Environment Audit Procedures, S-3010: Version Control Audit Procedures, S-1510: Software Development Library Audit |
| 4.10 Inspection and testing 4.10.1 General 4.10.2 Receiving inspection and testing 4.10.3 In-process inspection and testing 4.10.4 Final inspection and testing 4.10.5 Inspection and test records | H-6000: nspection and Testing, S-8010: Review of Software Test Documents S-8010: Review of Software Test Documents, H-6000: Inspection and Testing (Whole Section) H-4130: Receiving Inspection H-5110: In-Process Inspection S-10050: Test Readiness Review S-10070: Physical Configuration Audit |
| 4.11 Control of inspection, measuring and test equipment 4.11.1 General 4.11.2 Control procedures | H-2140: Certification of Measuring & Test Equipment & Test Procedures H-6100: Inspection/Test Instructions, H-2110: Calibration System Responsibilities, H-2120: Calibration Control and Recall, H-2140: Certification of Measuring & Test Equipment & Test Procedures H-6100: Inspection/Test Instructions |
| 4.12 Inspection and test status | Q-4010: Documentation Certification Procedures |
| 4.13 Control of nonconforming product 4.13.1 General 4.13.2 Review and disposition of nonconforming product | H-7000: Nonconforming Materials H-7150: Request for Deviation or Waiver, H:7160: Authorization to use Equivalent Item H-7110: Material Review Board, H:7130: Material Review Process |
| 4.14 Corrective and preventive action 4.14.1 General 4.14.2 Corrective action 4.14.3 Preventive action | Q-9000: Discrepancy/Corrective Action Reporting Q-9100: Corrective Action Process Q-9000: Discrepancy Reporting Q-2000: Trend Analysis and Progress Reporting |

TABLE E-1  FlightSafety ISO-9001 Requirements Compliance Matrix

| ISO-9001 Requirements | FSI Compliant Process and Documents |
| --- | --- |
| 4.15 Handling, storage, packaging, preservation and delivery 4.15.1 General 4.15.2 Handling 4.15.3 Storage 4.15.4 Packaging 4.15.5 Preservation 4.15.6 Delivery | Q-6000: Receipt, Shipment, and Data Submittal Procedures, Q-3210: C&DM Audit Procedures, Q-1000: Quality Procedures (Initiation/Revision) |
| 4.16 Control of quality records | Q-2010: Quality Assurance Reports |
| 4.17 Internal quality audits | QAM-1000 Section 4.1 |
| 4.18 Training | Q-1310: Quality Assurance Training and Certification Program |
| 4.19 Servicing | Q-1000: Quality Procedures (Initiation/Revision) |
| 4.20 Statistical techniques 4.20.1 Identification of need 4.20.2 Procedures | Q-2000: Trend Analysis and Progress Reporting Q-2030: Quality Statistical Reporting Q-2040: Corrective Action Monitoring and Trend Reporting |

TABLE E-1  FlightSafety ISO-9001 Requirements Compliance Matrix (Continued)

## E.2  Logicon ISO-9001 Requirements Compliance Matrix

Table E-2 demonstrates the complete coverage of ISO-9001 requirements.

| ISO-9001 Requirements | Logicon Compliant Process and Documents |
| --- | --- |
| 4.1 Management responsibility 4.1.1 Quality policy 4.1.2 Organization 4.1.2.1 Responsibility and authority 4.1.2.2 Resources 4.1.2.3 Management representatives 4.1.3 Management review | Policy 9.03: Software Development Practice 9.03: Software Development Practice 9.51: Product Assurance QA Policy 1: Quality Assurance Program Software Engineering Directive SED-001: Software Engineering SED-007: Integrated Software Management SED-011: Software Quality Assurance SED-012: Software Configuration Management SED-001/Instruction 12: Resources and Monitoring SED-002/Instruction 3: Planning Participants SED-003/Instruction 3: Tracking and Oversight Participants SED-004/Instruction 1: Subcontract Management Responsibilities SED-005/Instruction 4: Requirements Management Resources SED-003/Instruction 7: Senior Management Reviews SED-003/Instruction 8: Formal Customer Reviews SED-002/Instruction 5: Coordination and Review of Commitments SED-003/Instruction 5: Tracking and Corrective Action SED-003/Instruction 6: Revision, Review, and Coordination of Commitments SED-004/Instruction 6: Contract and Commitment Changes SED-004/Instruction 5: Subcontract Tracking and Oversight SED-005/Instruction 5: Requirement and Commitment Changes |
| 4.2 Quality system 4.2.1 General 4.2.2 Quality system procedures 4.2.3 Quality Planning | SED-011: Software Quality Assurance LSIS890297: QUALITY ASSURANCE PROGRAM QA Procedure QAP 1-6: Software Quality Planning SED-002/Instruction 8: Software Develop Plan (SDP) Software Engineering Procedure SEP-009: Preparing and Revising Software Development Plans Software Engineering Guideline SEG-008: Using Earned Value Methods (for Detailed Work/Task Planning) SED-002/Instruction 3: Planning Participants |

TABLE E-2  Logicon ISO-9001 Requirements Compliance Matrix

| ISO-9001 Requirements | Logicon Compliant Process and Documents |
| --- | --- |
| 4.3 Contract review 4.3.1 General 4.3.2 Review 4.3.3 Amendment to a contract 4.3.4 Records | SEP-008: Reviewing Software Project Commitments CM Procedure CMP 3-2: Software Change Control CMP 3-3: Preparation/Evaluation of Engineering Change Proposals (ECPs) |
| 4.4 Design control 4.4.1 General 4.4.2 Design and development planning 4.4.3 Organizational and technical interfaces 4.4.4 Design input 4.4.5 Design output 4.4.6 Design review 4.4.7 Design verification 4.4.8 Design validation 4.4.9 Design changes | SEP-009: Preparing and Revising Software Development Plans QAP 1-6: Software Quality Planning QAP 1-7: Management Review of the Software Quality Program CMP 1-1-1: Software CM Planning CMP 1-1-2: Hardware CM Planning CMP 1-2: Review and Audits of the CM Program Software Engineering Process SER-003 Software Requirements Analysis QAP 2-19: Evaluate System Requirements Analysis/Design Activities and Products QAP 2-3: Evaluate Software Requirements Analysis Activities and Products CMP 3-5: Interface Control Process SER-004: Software Architectural Design QAP 2-4: Evaluate Preliminary Design Activities and Products SER-005: Detailed Design QAP 2-6: Evaluate Detailed Design Activities and Products SER-006: Code and Unit Test QAP 2-8: Evaluate Coding and CSU Testing Activities and Products SER-011 Unit Integration and Test QAP 2-9: Evaluate CSC Integration and Testing Activities and Products SER-012: CSCI Qualification Test QAP 2-11: Evaluate CSCI Testing Activities and Products CMP 2-2-1: CM Numbering, Marking, Labels and Configuration Identifiers CMP 3-2: Software Change Control Process |
|  | CMP 3-2-1: Quick Fix Processing QAP 1-5-1: Evaluate Software Configuration Identification Process QAP 1-5-2: Evaluate Software Configuration Control QAP 1-5-3: Evaluate Software Configuration Status Accounting/Reporting SEP-011: Conducting Formal Reviews QAP 2-14: Milestone Review and Audits Preparations QAP 2-5-1: Design and Code Walkthroughs |
| 4.5 Document and data control 4.5.1 General 4.5.2 Document and data approval and issue 4.5.3 Document and data changes | QAP 1-1: Evaluate the SDP QAP 2-13: Document Review QAP 2-5-2: Evaluate Updated Code and Design Documentation CMP 3-2: Software Change Control Process CMP 3-3-1: ACSN, SCN and NOR Preparation CMP 3-4: Software Development Library (SDL) Control QAP 2-1: Evaluate SDL QAP 2-7-1: Software Development Files (SDFs) QAP 2-7-2: SDF Audit |
| 4.6 Purchasing 4.6.1 General 4.6.2 Evaluation of subcontractors 4.6.3 Purchasing data 4.6.4 Verification of purchased product 4.6.4.1 Supplier verification at subcontractor’s premises 4.6.4.2 Customer verification of subcontracted product | SEP-013: Managing Software Subcontractor QAP 6-1 Evaluate Subcontractor Management QAP 7-1: Evaluate Non-Developmental Software QAP 10-1: Evaluate Deliverable Elements of the Software Engineering and Test Environment QAP 5-1: Evaluate Non-deliverable Software QAP 9-1: Government Review at Contractor, Subcontractor, or Vendor Facility |
| 4.7 Control of customer-supplied product | LSIS 940034: Procedures for Control of Government Property |
| 4.8 Product identification and traceability | CMP 2-2-1: CM Numbering, Marking, Labels and Configuration Identifiers CMP 3-1-2: Engineering Release System |

TABLE E-2  Logicon ISO-9001 Requirements Compliance Matrix (Continued)

| ISO-9001 Requirements | Logicon Compliant Process and Documents |
| --- | --- |
| 4.9 Process control | Software Engineering Standard SES-001: C Programming Standard SES-002: COBOL Programming Standard SES-003: FOCUS Programming Standard SES-004: Ada Programming Standard SES-005: REXX Programming Standard SES-007: FORTRAN Programming Standard SIS-PD-004: Process Description for Inspections QAP 2-17: Evaluate System Integration and Testing Activities |
| 4.10 Inspection and testing 4.10.1 General 4.10.2 Receiving inspection and testing 4.10.3 In-process inspection and testing 4.10.4 Final inspection and testing 4.10.5 Inspection and test records | SER-12: CSCI Qualification Test QAP 2-12: Formal Test Monitoring QAP 2-14: Milestone Review and Audits Preparations QAP 10-1: Evaluate Deliverable Elements of the Software Engineering and Test Environment QAP 5-1: Evaluate Non-deliverable Software QAP 7-1: Evaluate Non-Developmental Software CMP 5-1: Preparation for and Conduct of Formal Configuration Audits CMP 3-1-2: Engineering Release System SIS-PD-004: Process Description for Inspections QAP 2-5-1: Design and Code Walkthroughs SER-011: Unit Integration and Test CMP 3-2-2, Code Baseline Certification QAP 2-13: Document Review QAP 3-3: Quality Evaluation Records |
| 4.11 Control of inspection, measuring and test equipment 4.11.1 General 4.11.2 Control procedures | QAP 10-1: Evaluate Deliverable Elements of the Software Engineering and Test Environment QAP 5-1: Evaluate Non-deliverable Software QAP 7-1: Evaluate Non-Developmental Software CMP 3-2-2, Code Baseline Certification QAP 2-12: Formal Test Monitoring |
| 4.12 Inspection and test status | QAP 2-12: Formal Test Monitoring |
| 4.13 Control of nonconforming product 4.13.1 General 4.13.2 Review and disposition of nonconforming product | QAP 2-13: Document Review CMP 3-2-2, Code Baseline Certification QAP 2-12: Formal Test Monitoring QAP 2-5-2: Evaluate Updated Code and Design Documentation CMP 3-2: Software Change Control Process |
| 4.14 Corrective and preventive action 4.14.1 General 4.14.2 Corrective action 4.14.3 Preventive action | SED-003/Instruction 5: Tracking and Corrective Action QAP 3-1: Implement Corrective Action System QAP 3-2: Evaluate Corrective Action System QAP 3-3: Quality Evaluation Records |
| 4.15 Handling, storage, packaging, preservation and delivery 4.15.1 General 4.15.2 Handling 4.15.3 Storage 4.15.4 Packaging 4.15.5 Preservation 4.15.6 Delivery | QAP 4-1: Evaluate Documentation and Media Distribution QAP 4-2: Evaluate Storage, Handling, and Delivery CMP 3-4: SDL Control CMP 6-2-1: Archive Process CMP 3-1-2: Engineering Release System |
| 4.16 Control of quality records | QAP 3-3: Quality Evaluation Records |
| 4.17 Internal quality audits | QAP 1-7: Management Review of the Software Quality Program |
| 4.18 Training | Practice 7.53: Training Program SED-013: Software Engineering Directive for Training Program |
| 4.19 Servicing | CMP 3-1-2: Software Change Control Process CMP 3-2-1: Quick Fix Processing CMP 3-3: Preparation/Evaluation of Engineering Change Proposals (ECPs) CMP 3-3-1: ACSN, SCN and NOR Preparation |

TABLE E-2  Logicon ISO-9001 Requirements Compliance Matrix (Continued)

| ISO-9001 Requirements | Logicon Compliant Process and Documents |
| --- | --- |
| 4.20 Statistical techniques 4.20.1 Identification of need 4.20.2 Procedures | SEP-002: Estimating Software Development Size, Cost, and Schedule SEP-005: Reporting Software Size SEP-010: Estimating Critical Computer Resources and Performance Measures SEG-004: Guidelines for Computing Software Size Metrics SEG-007: Guidelines for Software Quality Metrics QAP 3-2: Evaluate Corrective Action System QAP 3-3: Quality Evaluation Records |
|  | - CMP 3-2-1: Quick Fix Processing - QAP 1-5-1: Evaluate Software Configuration Identification Process - QAP 1-5-2: Evaluate Software Configuration Control - QAP 1-5-3: Evaluate Software Configuration Status Accounting/Reporting - SEP-011: Conducting Formal Reviews - QAP 2-14: Milestone Review and Audits Preparations - QAP 2-5-1: Design and Code Walkthroughs |
| 4.5 Document and data control 4.5.1 General 4.5.2 Document and data approval and issue 4.5.3 Document and data changes | - QAP 1-1: Evaluate the SDP - QAP 2-13: Document Review - QAP 2-5-2: Evaluate Updated Code and Design Documentation - CMP 3-2: Software Change Control Process - CMP 3-3-1: ACSN, SCN and NOR Preparation - CMP 3-4: Software Development Library (SDL) Control - QAP 2-1: Evaluate SDL - QAP 2-7-1: Software Development Files (SDFs) - QAP 2-7-2: SDF Audit |
| 4.6 Purchasing 4.6.1 General 4.6.2 Evaluation of subcontractors 4.6.3 Purchasing data 4.6.4 Verification of purchased product 4.6.4.1 Supplier verification at subcontractor’s premises 4.6.4.2 Customer verification of subcontracted product | - SEP-013: Managing Software Subcontractor - QAP 6-1 Evaluate Subcontractor Management - QAP 7-1: Evaluate Non-Developmental Software - QAP 10-1: Evaluate Deliverable Elements of the Software Engineering and Test Environment - QAP 5-1: Evaluate Non-deliverable Software - QAP 9-1: Government Review at Contractor, Subcontractor, or Vendor Facility |
| 4.7 Control of customer-supplied product | - LSIS 940034: Procedures for Control of Government Property |
| 4.8 Product identification and traceability | - CMP 2-2-1: CM Numbering, Marking, Labels and Configuration Identifiers - CMP 3-1-2: Engineering Release System |
| 4.9 Process control | - Software Engineering Standard SES-001: C Programming Standard - SES-002: COBOL Programming Standard - SES-003: FOCUS Programming Standard - SES-004: Ada Programming Standard - SES-005: REXX Programming Standard - SES-007: FORTRAN Programming Standard - SIS-PD-004: Process Description for Inspections - QAP 2-17: Evaluate System Integration and Testing Activities |
| 4.10 Inspection and testing 4.10.1 General 4.10.2 Receiving inspection and testing 4.10.3 In-process inspection and testing 4.10.4 Final inspection and testing 4.10.5 Inspection and test records | - SER-12: CSCI Qualification Test - QAP 2-12: Formal Test Monitoring - QAP 2-14: Milestone Review and Audits Preparations - QAP 10-1: Evaluate Deliverable Elements of the Software Engineering and Test Environment - QAP 5-1: Evaluate Non-deliverable Software - QAP 7-1: Evaluate Non-Developmental Software - CMP 5-1: Preparation for and Conduct of Formal Configuration Audits - CMP 3-1-2: Engineering Release System - SIS-PD-004: Process Description for Inspections - QAP 2-5-1: Design and Code Walkthroughs - SER-011: Unit Integration and Test - CMP 3-2-2, Code Baseline Certification - QAP 2-13: Document Review - QAP 3-3: Quality Evaluation Records |
| 4.11 Control of inspection, measuring and test equipment 4.11.1 General 4.11.2 Control procedures | - QAP 10-1: Evaluate Deliverable Elements of the Software Engineering and Test Environment - QAP 5-1: Evaluate Non-deliverable Software - QAP 7-1: Evaluate Non-Developmental Software - CMP 3-2-2, Code Baseline Certification - QAP 2-12: Formal Test Monitoring |

TABLE E-2  Logicon ISO-9001 Requirements Compliance Matrix (Continued)

| ISO-9001 Requirements | Logicon Compliant Process and Documents |
| --- | --- |
| 4.12 Inspection and test status | - QAP 2-12: Formal Test Monitoring |
| 4.13 Control of nonconforming product 4.13.1 General 4.13.2 Review and disposition of nonconforming product | - QAP 2-13: Document Review - CMP 3-2-2, Code Baseline Certification - QAP 2-12: Formal Test Monitoring - QAP 2-5-2: Evaluate Updated Code and Design Documentation - CMP 3-2: Software Change Control Process |
| 4.14 Corrective and preventive action 4.14.1 General 4.14.2 Corrective action 4.14.3 Preventive action | - SED-003/Instruction 7: Tracking and Corrective Action - QAP 3-1: Implement Corrective Action System - QAP 3-2: Evaluate Corrective Action System - QAP 3-3: Quality Evaluation Records |
| 4.15 Handling, storage, packaging, preservation and delivery 4.15.1 General 4.15.2 Handling 4.15.3 Storage 4.15.4 Packaging 4.15.5 Preservation 4.15.6 Delivery | - QAP 4-1: Evaluate Documentation and Media Distribution - QAP 4-2: Evaluate Storage, Handling, and Delivery - CMP 3-4: SDL Control - CMP 6-2-1: Archive Process - CMP 3-1-2: Engineering Release System |
| 4.16 Control of quality records | - QAP 3-3: Quality Evaluation Records |
| 4.17 Internal quality audits | - QAP 1-7: Management Review of the Software Quality Program |
| 4.18 Training | - Practice 7.53: Training Program - SED-002/Instruction 5: Required Training (for Software Project Planning) - SED-003/Instruction 5: Required Training (for Software Project Tracking and Oversight) - SED-004/Instruction 3: Subcontract Management Training - SED-005/Instruction 4: Requirements Management Training |
| 4.19 Servicing | - CMP 3-1-2: Software Change Control Process - CMP 3-2-1: Quick Fix Processing - CMP 3-3: Preparation/Evaluation of Engineering Change Proposals (ECPs) - CMP 3-3-1: ACSN, SCN and NOR Preparation |
| 4.20 Statistical techniques 4.20.1 Identification of need 4.20.2 Procedures | - SEP-002: Estimating Software Development Size, Cost, and Schedule - SEP-005: Reporting Software Size - SEP-010: Estimating Critical Computer Resources and Performance Measures - SEG-004: Guidelines for Computing Software Size Metrics - SEG-007: Guidelines for Software Quality Metrics - QAP 3-2: Evaluate Corrective Action System - QAP 3-3: Quality Evaluation Records |

TABLE E-2  Logicon ISO-9001 Requirements Compliance Matrix (Continued)